## NRR (hidden)
[15 empty] | completed costs | known costs | future costs
Count |  | 108 |  |  |  |  | needs to be edited | [8 empty] | 2134762.46 | 39113666.7341 | 41248429.1941
BOROUGH | PROGRAM AREA | DEVELOPMENT | NRR | Priority Level | RAD/PACT | WORK TYPE | FUNDING SOURCE | CITY FUNDS | FEDERAL FUNDS | TOTAL FUNDS | FUND YEAR | CALENDAR YEAR | FISCAL YEAR | STATUS | COMPLETED | COST | ESTIMATES | RESOURCE | Notes
BROOKLYN | Waste Management | BUSHWICK | Zone 1 | $$ |  | Enlarge Hopper Door | City Expense | 24000 |  | 24000 | 2019 | 2019 | 2020 | IN-CONSTRUCTION |  | 44243.94 |  | JOCS CONTRACTS
BRONX | Waste Management | BUTLER | Zone 1 | $$ |  | Enlarge Hopper Door | City Expense | 18000 |  | 18000 | 2019 | 2019 | 2020 | IN-CONSTRUCTION |  | 0 |  | JOCS CONTRACTS
BRONX | Waste Management | CLAREMONT REHAB (GROUP 3) | Zone 1 | $ | 2025 | Enlarge Hopper Door | NYCHA Operating |  | 24000 | 24000 | 2019 | 2019 | 2020 | IN-CONSTRUCTION |  | 0 |  | JOCS CONTRACTS
BRONX | Waste Management | CLAREMONT REHAB (GROUP 4) | Zone 1 | $ | 2025 | Enlarge Hopper Door | NYCHA Operating |  | 27000 | 27000 | 2019 | 2019 | 2020 | IN-CONSTRUCTION |  | 0 |  | JOCS CONTRACTS
BRONX | Waste Management | JACKSON | Zone 1 | $ |  | Enlarge Hopper Door | City Expense | 21000 |  | 21000 | 2019 | 2019 | 2020 | IN-CONSTRUCTION |  | 0 |  | JOCS CONTRACTS
MANHATTAN | Waste Management | LA GUARDIA | Zone 1 | $$ |  | Enlarge Hopper Door | City Expense | 27000 |  | 27000 | 2019 | 2019 | 2020 | IN-CONSTRUCTION |  | 56519.89 |  | JOCS CONTRACTS
BROOKLYN | Waste Management | LAFAYETTE | Zone 1 | $$$ |  | Enlarge Hopper Door | City Expense | 21000 |  | 21000 | 2019 | 2019 | 2020 | IN-CONSTRUCTION |  | 0 |  | JOCS CONTRACTS
BROOKLYN | Waste Management | MARCY | Zone 1 | $$ | 2027 | Enlarge Hopper Door | City Expense | 210000 |  | 210000 | 2019 | 2019 | 2020 | IN-CONSTRUCTION |  | 0 |  | JOCS CONTRACTS
BRONX | Waste Management | MELROSE | Zone 1 | $ | 2023 | Enlarge Hopper Door | City Expense | 24000 |  | 24000 | 2019 | 2019 | 2020 | IN-CONSTRUCTION |  | 0 |  | JOCS CONTRACTS
BRONX | Waste Management | MORRIS I | Zone 1 | $$ |  | Enlarge Hopper Door | City Expense | 51000 |  | 51000 | 2019 | 2019 | 2020 | IN-CONSTRUCTION |  | 0 |  | JOCS CONTRACTS
BRONX | Waste Management | MORRISANIA AIR RIGHTS | Zone 1 | $ |  | Enlarge Hopper Door | City Expense | 15000 |  | 15000 | 2019 | 2019 | 2020 | IN-CONSTRUCTION |  | 0 |  | JOCS CONTRACTS
BROOKLYN | Waste Management | ROOSEVELT I | Zone 1 | $ |  | Enlarge Hopper Door | City Expense | 18000 |  | 18000 | 2019 | 2019 | 2020 | IN-CONSTRUCTION |  | 0 |  | JOCS CONTRACTS
MANHATTAN | Waste Management | RUTGERS | Zone 1 | $ |  | Enlarge Hopper Door | City Expense | 15000 |  | 15000 | 2019 | 2019 | 2020 | IN-CONSTRUCTION |  | 32007.26 |  | JOCS CONTRACTS
MANHATTAN | Waste Management | SMITH | Zone 1 | $ |  | Enlarge Hopper Door | City Expense | 36000 |  | 36000 | 2019 | 2019 | 2020 | IN-CONSTRUCTION |  | 74933.74 |  | JOCS CONTRACTS
BROOKLYN | Waste Management | SUMNER | Zone 1 | $ |  | Enlarge Hopper Door | City Expense | 72000 |  | 72000 | 2019 | 2019 | 2020 | IN-CONSTRUCTION |  | 148620.14 |  | JOCS CONTRACTS
BROOKLYN | Waste Management | TOMPKINS | Zone 1 | $ |  | Enlarge Hopper Door | NYCHA Operating |  | 36000 | 36000 | 2019 | 2019 | 2020 | IN-CONSTRUCTION |  | 74933.74 |  | JOCS CONTRACTS
BRONX | Waste Management | WEBSTER | Zone 1 | $ |  | Enlarge Hopper Door | City Expense | 15000 |  | 15000 | 2019 | 2019 | 2020 | IN-CONSTRUCTION |  | 0 |  | JOCS CONTRACTS
MANHATTAN | Waste Management | BARUCH HOUSES ADDITION | Zone 1 | $ |  | Food Waste Disposer | NYCHA Operating |  | 129527.5 | 129527.5 | 2019 | 2019 | 2020 | IN-CONSTRUCTION |  | 607266.52 |  | JOCS CONTRACTS
MANHATTAN | Waste Management | MELTZER TOWER | Zone 1 | $ |  | Food Waste Disposer | NYCHA Operating |  | 150567.5 | 150567.5 | 2019 | 2019 | 2020 | IN-CONSTRUCTION |  | 534717.81 |  | JOCS CONTRACTS
MANHATTAN | Waste Management | TWO BRIDGES URA (SITE 7) | Zone 1 | $ |  | Food Waste Disposer | NYCHA Operating |  | 164375 | 164375 | 2019 | 2019 | 2020 | IN-CONSTRUCTION |  | 561519.42 |  | JOCS CONTRACTS
MANHATTAN | Waste Management | LA GUARDIA | Zone 1 | $$ |  | Cardboard Baler | City Expense | 38361.354 |  | 38361.354 | 2019 | 2020 | 2020 | UP-COMING |  |  | 38885.4 | FROM BALER INSTALL
MANHATTAN | Waste Management | RIIS | Zone 1 | $ |  | Cardboard Baler | City Expense | 34083.5661 |  | 34083.5661 | 2019 | 2020 | 2020 | UP-COMING |  |  | 38885.4 | FROM BALER INSTALL
MANHATTAN | Waste Management | VLADECK | Zone 1 | $$ |  | Cardboard Baler | City Expense | 35106.0731 |  | 35106.0731 | 2019 | 2020 | 2020 | UP-COMING |  |  | 38885.4 | FROM BALER INSTALL
MANHATTAN | Waste Management | 45 ALLEN STREET | Zone 1 | $$ |  | Enlarge Hopper Door | NYCHA Operating |  | 3000 | 3000 | 2019 | 2020 | 2020 | UP-COMING |  |  | 0 | JOCS CONTRACTS
MANHATTAN | Waste Management | BARUCH | Zone 1 | $ |  | Enlarge Hopper Door | NYCHA Operating |  | 51000 | 51000 | 2019 | 2020 | 2020 | UP-COMING |  |  | 0 | JOCS CONTRACTS
MANHATTAN | Waste Management | BRACETTI PLAZA | Zone 1 | $ | 2026 | Enlarge Hopper Door | NYCHA Operating |  | 6000 | 6000 | 2019 | 2020 | 2020 | UP-COMING |  |  | 0 | JOCS CONTRACTS
MANHATTAN | Waste Management | CAMPOS PLAZA II | Zone 1 | $$ | 2026 | Enlarge Hopper Door | NYCHA Operating |  | 9000 | 9000 | 2019 | 2020 | 2020 | UP-COMING |  |  | 0 | JOCS CONTRACTS
MANHATTAN | Waste Management | GOMPERS | Zone 1 | $ |  | Enlarge Hopper Door | City Expense | 12000 |  | 12000 | 2019 | 2020 | 2020 | UP-COMING |  |  | 0 | JOCS CONTRACTS
MANHATTAN | Waste Management | LOWER EAST SIDE I INFILL | Zone 1 | $$ |  | Enlarge Hopper Door | City Expense | 3000 |  | 3000 | 2019 | 2020 | 2020 | UP-COMING |  |  | 0 | JOCS CONTRACTS
MANHATTAN | Waste Management | LOWER EAST SIDE II | Zone 1 | $ | 2026 | Enlarge Hopper Door | City Expense | 3000 |  | 3000 | 2019 | 2020 | 2021 | UP-COMING |  |  | 0 | JOCS CONTRACTS
MANHATTAN | Waste Management | LOWER EAST SIDE REHAB (GROUP 5) | Zone 1 | $$ | 2026 | Enlarge Hopper Door | City Expense | 9000 |  | 9000 | 2019 | 2020 | 2021 | UP-COMING |  |  | 0 | JOCS CONTRACTS
MANHATTAN | Waste Management | RIIS | Zone 1 | $ |  | Enlarge Hopper Door | NYCHA Operating |  | 78000 | 78000 | 2019 | 2020 | 2021 | UP-COMING |  |  | 0 | JOCS CONTRACTS
MANHATTAN | Waste Management | SEWARD PARK EXTENSION | Zone 1 | $ |  | Enlarge Hopper Door | City Expense | 6000 |  | 6000 | 2019 | 2020 | 2021 | UP-COMING |  |  | 0 | JOCS CONTRACTS
MANHATTAN | Waste Management | TWO BRIDGES URA (SITE 7) | Zone 1 | $ |  | Enlarge Hopper Door | NYCHA Operating |  | 3000 | 3000 | 2019 | 2020 | 2021 | UP-COMING |  |  | 0 | JOCS CONTRACTS
MANHATTAN | Waste Management | WALD | Zone 1 | $ |  | Enlarge Hopper Door | NYCHA Operating |  | 48000 | 48000 | 2019 | 2020 | 2021 | UP-COMING |  |  | 0 | JOCS CONTRACTS
MANHATTAN |  | 131 SAINT NICHOLAS AVENUE | Zone 2 | $ |  | Exterior Compactors | [5 empty] | 2020 |  |  |  |  | 0
MANHATTAN |  | 335 EAST 111TH STREET | Zone 3 | $ |  | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
MANHATTAN |  | AUDUBON | Zone 3 | $$$$ | 2020 | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
MANHATTAN |  | BETHUNE GARDENS | Zone 3 | $$ | 2020 | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
BROOKLYN |  | BORINQUEN PLAZA II | Zone 3 | $$$ |  | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
BRONX |  | BRONX RIVER | Zone 3 | $ |  | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
MANHATTAN |  | CORSI HOUSES | Zone 2 | $ | 2026 | Exterior Compactors | [5 empty] | 2020 |  |  |  |  | 0
MANHATTAN |  | DOUGLASS ADDITION | Zone 3 | $ |  | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
MANHATTAN |  | DOUGLASS II | Zone 3 | $$$ |  | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
MANHATTAN |  | DREW-HAMILTON | Zone 2 | $ |  | Exterior Compactors | [5 empty] | 2020 |  |  |  |  | 0
MANHATTAN |  | EAST RIVER | Zone 2 | $ | 2024 | Exterior Compactors | [5 empty] | 2020 |  |  |  |  | 0
MANHATTAN |  | FORT WASHINGTON AVENUE REHAB | Zone 3 | $ | 2019 | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
MANHATTAN |  | GRAMPION | Zone 3 | $ | 2019 | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
MANHATTAN |  | GRANT | Zone 2 | $$$$ |  | Exterior Compactors | [5 empty] | 2020 |  |  |  |  | 0
MANHATTAN |  | HARLEM RIVER II | Zone 3 | $$ | 2020 | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
MANHATTAN |  | JOHNSON | Zone 2 | $$$ | 2028 | Exterior Compactors | [5 empty] | 2020 |  |  |  |  | 0
BROOKLYN |  | KINGSBOROUGH | Zone 3 | $ |  | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
MANHATTAN | Waste Management | LA GUARDIA | Zone 1 | $$ |  | Exterior Compactors | Federal |  | 374920 | 374920 | 2019 | 2020 | 2021 | UP-COMING |  |  | 0 | WMP JOCS SOW SELECTION
MANHATTAN |  | MANHATTANVILLE REHAB (GROUP 2) | Zone 3 | $ | 2019 | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
MANHATTAN |  | MANHATTANVILLE REHAB (GROUP 3) | Zone 3 | $ | 2019 | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
MANHATTAN |  | MARSHALL PLAZA | Zone 3 | $$ | 2020 | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
BRONX | Waste Management | MELROSE | Zone 1 | $ | 2023 | Exterior Compactors | Federal |  | 374920 | 374920 | 2019 | 2020 |  | UP-COMING |  |  | 0
MANHATTAN |  | METRO NORTH PLAZA | Zone 2 | $ |  | Exterior Compactors | [5 empty] | 2020 |  |  |  |  | 0
BRONX |  | MOORE | Zone 3 | $$ |  | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
MANHATTAN |  | MORRIS PARK SENIOR CITIZENS HOME | Zone 2 | $$$$ |  | Exterior Compactors | [5 empty] | 2020 |  |  |  |  | 0
MANHATTAN |  | PARK AVENUE-EAST 122ND, 123RD STREETS | Zone 3 | $$ | 2019 | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
MANHATTAN |  | PUBLIC SCHOOL 139 (CONVERSION) | Zone 3 | $ | 2019 | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
MANHATTAN |  | SAMUEL (CITY) | Zone 2 | $$ | 2026 | Exterior Compactors | [5 empty] | 2020 |  |  |  |  | 0
BRONX |  | SOUTH BRONX AREA (SITE 402) | Zone 3 | $$ | 2026 | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
BRONX |  | STEBBINS AVENUE-HEWITT PLACE | Zone 3 | $$$ | 2026 | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
BRONX |  | UNION AVENUE-EAST 163RD STREET | Zone 3 | $ | 2026 | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
BRONX |  | UNION AVENUE-EAST 166TH STREET | Zone 3 | $ | 2026 | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
MANHATTAN |  | UPACA (SITE 6) | Zone 2 | $ |  | Exterior Compactors | [5 empty] | 2020 |  |  |  |  | 0
MANHATTAN |  | WASHINGTON HEIGHTS REHAB PHASE III | Zone 3 | $ | 2019 | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
MANHATTAN |  | WHITE | Zone 2 | $ |  | Exterior Compactors | [5 empty] | 2020 |  |  |  |  | 0
MANHATTAN | Waste Management | LA GUARDIA | Zone 1 | $$ |  | Food Waste Disposer | NYCHA Operating |  | 739529.7 | 739529.7 | 2019 | 2020 | 2020 | UP-COMING |  |  | 1875140.9186 | JOCS CONTRACTS
MANHATTAN | Waste Management | LA GUARDIA ADDITION | Zone 1 | $ |  | Food Waste Disposer | NYCHA Operating |  | 97310 | 97310 | 2019 | 2020 | 2020 | UP-COMING |  |  | 256091.6562 | JOCS CONTRACTS
MANHATTAN | Waste Management | RIIS | Zone 1 | $ |  | Food Waste Disposer | City Expense | 806574.975 |  | 806574.975 | 2019 | 2020 | 2021 | UP-COMING |  |  | 2047014.5133 | JOCS CONTRACTS
MANHATTAN | Waste Management | RIIS II | Zone 1 | $$ |  | Food Waste Disposer | NYCHA Operating |  | 452996.5751 | 452996.5751 | 2019 | 2020 | 2021 | UP-COMING |  |  | 991710.6416 | JOCS CONTRACTS
BRONX |  | DAVIDSON | Zone 3 | $ | 2026 | Interior Compactors | [5 empty] | 73653.3945
MANHATTAN | Waste Management | LOWER EAST SIDE I INFILL | Zone 1 | $$ |  | Interior Compactors | Federal |  | 74191 | 74191 | 2019 | 2020 | 2021 | UP-COMING |  |  |  | WMP JOCS SOW SELECTION
MANHATTAN |  | PARK AVENUE-EAST 122ND, 123RD STREETS | Zone 3 | $$ | 2019 | Interior Compactors | [5 empty] | 0 |  |  |  |  | 0
MANHATTAN |  | PUBLIC SCHOOL 139 (CONVERSION) | Zone 3 | $ | 2019 | Interior Compactors | [5 empty] | 0 |  |  |  |  | 0
MANHATTAN |  | ROBINSON | Zone 2 | $$ |  | Interior Compactors | [5 empty] | 147306.789
MANHATTAN | Waste Management | SEWARD PARK EXTENSION | Zone 1 | $ |  | Interior Compactors | Federal |  | 74191 | 74191 | 2019 | 2020 | 2021 | UP-COMING |  |  |  | WMP JOCS SOW SELECTION
BRONX |  | SOUTH BRONX AREA (SITE 402) | Zone 3 | $$ | 2026 | Interior Compactors | [5 empty] | 0
BRONX |  | STEBBINS AVENUE-HEWITT PLACE | Zone 3 | $$$ | 2026 | Interior Compactors | [5 empty] | 0
BRONX |  | UNION AVENUE-EAST 166TH STREET | Zone 3 | $ | 2026 | Interior Compactors | [5 empty] | 0
MANHATTAN | Waste Management | VLADECK | Zone 1 | $$ |  | Interior Compactors | Federal |  | 3412786 | 3412786 | 2019 | 2020 | 2021 | UP-COMING |  |  |  | WMP JOCS SOW SELECTION
MANHATTAN | Waste Management | VLADECK II | Zone 1 | $ |  | Interior Compactors | Federal |  | 593528 | 593528 | 2019 | 2020 | 2021 | UP-COMING |  |  |  | WMP JOCS SOW SELECTION
MANHATTAN |  | WASHINGTON HEIGHTS REHAB PHASE III | Zone 3 | $ | 2019 | Interior Compactors | [5 empty] | 0 |  |  |  |  | 0
MANHATTAN | Waste Management | LA GUARDIA | Zone 1 | $$ |  | Bulk Crusher | Federal |  | 2725380 | 2725380 | 2019 | 2021 | 2021 | UP-COMING |  |  | 1307070 | WMP JOCS SOW SELECTION | Need to speak to Real Estate about relocating compactors
MANHATTAN | Waste Management | RIIS | Zone 1 | $ |  | Bulk Crusher | Federal |  | 1362690 | 1362690 | 2019 | 2021 | 2021 | UP-COMING |  |  | 1307070 | WMP JOCS SOW SELECTION
MANHATTAN |  | FULTON | Zone 3 | $ |  | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
MANHATTAN |  | JEFFERSON | Zone 2 | $$ | 2026 | Exterior Compactors | [5 empty] | 2020 |  |  |  |  | 0
MANHATTAN |  | LINCOLN | Zone 2 | $$$$ |  | Exterior Compactors | [5 empty] | 2020 |  |  |  |  | 0
BRONX |  | MONROE | Zone 3 | $ |  | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
MANHATTAN |  | RANGEL | Zone 2 | $ |  | Exterior Compactors | [5 empty] | 2020 |  |  |  |  | 0
MANHATTAN |  | WILSON | Zone 2 | $ |  | Exterior Compactors | [5 empty] | 2020 |  |  |  |  | 0
MANHATTAN |  | 335 EAST 111TH STREET | Zone 3 | $ |  | Interior Compactors | [5 empty] | 73653.3945
MANHATTAN |  | CORSI HOUSES | Zone 2 | $ | 2026 | Interior Compactors | [5 empty] | 73653.3945
MANHATTAN |  | GRAMPION | Zone 3 | $ | 2019 | Interior Compactors | [5 empty] | 0 |  |  |  |  | 0
MANHATTAN |  | HARLEM RIVER | Zone 3 | $ | 2020 | Interior Compactors | [5 empty] | 0 |  |  |  |  | 0
MANHATTAN |  | HARLEM RIVER II | Zone 3 | $$ | 2020 | Interior Compactors | [5 empty] | 0 |  |  |  |  | 0
BROOKLYN | Waste Management | 303 VERNON AVENUE | Zone 1 | $ |  | Exterior Compactors | Federal |  | 187460 | 187460 | 2019 | 2020 |  | UP-COMING |  |  | 0
BROOKLYN |  | BORINQUEN PLAZA I | Zone 3 | $$$$ |  | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
MANHATTAN |  | CARVER | Zone 2 | $$ |  | Exterior Compactors | [5 empty] | 2020 |  |  |  |  | 0
BRONX |  | DAVIDSON | Zone 3 | $ | 2026 | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
BRONX | Waste Management | EAST 180TH STREET-MONTEREY AVENUE | Zone 1 | $$ |  | Exterior Compactors | Federal |  | 187460 | 187460 | 2019 | 2020 |  | UP-COMING |  |  | 0
MANHATTAN |  | MANHATTANVILLE | Zone 2 | $ | 2028 | Exterior Compactors | [5 empty] | 2020 |  |  |  |  | 0
BRONX |  | SAINT MARY'S PARK | Zone 3 | $ |  | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
MANHATTAN |  | 131 SAINT NICHOLAS AVENUE | Zone 2 | $ |  | Interior Compactors | [5 empty] | 73653.3945
BRONX |  | CLAREMONT PARKWAY-FRANKLIN AVENUE | Zone 3 | $ | 2026 | Interior Compactors | [5 empty] | 73653.3945
BRONX | Waste Management | EAST 180TH STREET-MONTEREY AVENUE | Zone 1 | $$ |  | Interior Compactors | Federal |  | 74191 | 74191 | 2019 | 147306.789 |  | UP-COMING
BROOKLYN |  | KINGSBOROUGH | Zone 3 | $ |  | Interior Compactors | [5 empty] | 2577868.8075
MANHATTAN |  | RANGEL | Zone 2 | $ |  | Interior Compactors | [5 empty] | 736533.945
MANHATTAN |  | WHITE | Zone 2 | $ |  | Interior Compactors | [5 empty] | 147306.789
BRONX |  | CLAREMONT PARKWAY-FRANKLIN AVENUE | Zone 3 | $ | 2026 | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
MANHATTAN |  | HARLEM RIVER | Zone 3 | $ | 2020 | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
MANHATTAN |  | LEXINGTON | Zone 2 | $ | 2023 | Exterior Compactors | [5 empty] | 2020 |  |  |  |  | 0
MANHATTAN |  | ROBINSON | Zone 2 | $$ |  | Exterior Compactors | [5 empty] | 2020 |  |  |  |  | 0
MANHATTAN |  | UPACA (SITE 5) | Zone 2 | $ |  | Exterior Compactors | [5 empty] | 2020 |  |  |  |  | 0
MANHATTAN |  | WAGNER | Zone 2 | $ |  | Exterior Compactors | [5 empty] | 2020 |  |  |  |  | 0
BRONX | Waste Management | WEBSTER | Zone 1 | $ |  | Exterior Compactors | Federal |  | 374920 | 374920 | 2019 | 2020 |  | UP-COMING |  |  | 0
BRONX | Waste Management | BUTLER | Zone 1 | $$ |  | Interior Compactors | Federal |  | 445146 | 445146 | 2019 | 883840.734 |  | UP-COMING
MANHATTAN |  | JOHNSON | Zone 2 | $$$ | 2028 | Interior Compactors | [5 empty] | 1252107.7065
MANHATTAN |  | TAFT | Zone 2 | $$$ |  | Interior Compactors | [5 empty] | 810187.3395
MANHATTAN |  | CLINTON | Zone 2 | $$$$ |  | Exterior Compactors | [5 empty] | 2020 |  |  |  |  | 0
MANHATTAN |  | DOUGLASS I | Zone 3 | $$$ |  | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
MANHATTAN |  | KING TOWERS | Zone 2 | $$$ |  | Exterior Compactors | [5 empty] | 2020 |  |  |  |  | 0
BRONX |  | PATTERSON | Zone 3 | $$ | 2025 | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
MANHATTAN |  | POLO GROUNDS TOWERS | Zone 2 | $ |  | Exterior Compactors | [5 empty] | 2020 |  |  |  |  | 0
QUEENS |  | QUEENSBRIDGE NORTH | Zone 3 | $ |  | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
QUEENS |  | QUEENSBRIDGE SOUTH | Zone 3 | $ |  | Exterior Compactors |  |  | 0 |  |  | 2020 |  |  |  |  | 0
MANHATTAN |  | SAINT NICHOLAS | Zone 2 | $ |  | Exterior Compactors | [5 empty] | 2020 |  |  |  |  | 0
MANHATTAN |  | TAFT | Zone 2 | $$$ |  | Exterior Compactors | [5 empty] | 2020 |  |  |  |  | 0
MANHATTAN |  | WASHINGTON | Zone 2 | $$$ | 2023 | Exterior Compactors | [5 empty] | 2020 |  |  |  |  | 0
BRONX |  | SAINT MARY'S PARK | Zone 3 | $ |  | Interior Compactors | [5 empty] | 441920.367
MANHATTAN |  | WAGNER | Zone 2 | $ |  | Interior Compactors | [5 empty] | 1620374.679
MANHATTAN |  | CLINTON | Zone 2 | $$$$ |  | Interior Compactors | [5 empty] | 441920.367
MANHATTAN |  | LINCOLN | Zone 2 | $$$$ |  | Interior Compactors | [5 empty] | 1473067.89
MANHATTAN |  | MORRIS PARK SENIOR CITIZENS HOME | Zone 2 | $$$$ |  | Interior Compactors | [5 empty] | 73653.3945
BROOKLYN | Waste Management | BUSHWICK | Zone 1 | $$ |  | Interior Compactors | Federal |  | 220329 | 220329 | 2019 | 589227.156 |  | UP-COMING
MANHATTAN |  | JEFFERSON | Zone 2 | $$ | 2026 | Interior Compactors | [5 empty] | 2504215.413
MANHATTAN |  | KING TOWERS | Zone 2 | $$$ |  | Interior Compactors | [5 empty] | 736533.945
MANHATTAN |  | SAMUEL (CITY) | Zone 2 | $$ | 2026 | Interior Compactors | [5 empty] | 2946135.78
MANHATTAN |  | METRO NORTH PLAZA | Zone 2 | $ |  | Interior Compactors | [5 empty] | 220960.1835
BRONX |  | MONROE | Zone 3 | $ |  | Interior Compactors | [5 empty] | 1325761.101
MANHATTAN |  | SAINT NICHOLAS | Zone 2 | $ |  | Interior Compactors | [5 empty] | 1031147.523
MANHATTAN |  | DOUGLASS I | Zone 3 | $$$ |  | Interior Compactors | [5 empty] | 810187.3395
MANHATTAN |  | DOUGLASS II | Zone 3 | $$$ |  | Interior Compactors | [5 empty] | 441920.367
MANHATTAN |  | BETHUNE GARDENS | Zone 3 | $$ | 2020 | Interior Compactors | [5 empty] | 0 |  |  |  |  | 0
MANHATTAN |  | CARVER | Zone 2 | $$ |  | Interior Compactors | [5 empty] | 957494.1285
MANHATTAN |  | DOUGLASS ADDITION | Zone 3 | $ |  | Interior Compactors | [5 empty] | 73653.3945
MANHATTAN |  | DREW-HAMILTON | Zone 2 | $ |  | Interior Compactors | [5 empty] | 368266.9725
MANHATTAN |  | FULTON | Zone 3 | $ |  | Interior Compactors | [5 empty] | 1399414.4955
BRONX |  | MOORE | Zone 3 | $$ |  | Interior Compactors | [5 empty] | 294613.578
BRONX |  | UNION AVENUE-EAST 163RD STREET | Zone 3 | $ | 2026 | Interior Compactors | [5 empty] | 73653.3945
QUEENS |  | QUEENSBRIDGE SOUTH | Zone 3 | $ |  | Interior Compactors | [5 empty] | 3609016.3305
BRONX |  | BRONX RIVER | Zone 3 | $ |  | Interior Compactors | [5 empty] | 662880.5505
QUEENS |  | QUEENSBRIDGE NORTH | Zone 3 | $ |  | Interior Compactors | [5 empty] | 3461709.5415
MANHATTAN |  | MANHATTANVILLE REHAB (GROUP 2) | Zone 3 | $ | 2019 | Interior Compactors | [5 empty] | 0 |  |  |  |  | 0
MANHATTAN |  | MANHATTANVILLE REHAB (GROUP 3) | Zone 3 | $ | 2019 | Interior Compactors | [5 empty] | 0 |  |  |  |  | 0
BRONX | Waste Management | TWIN PARKS EAST (SITE 9) | Zone 1 | $ |  | Interior Compactors | Federal |  | 74191 | 74191 | 2019 | 73653.3945 |  | UP-COMING
MANHATTAN |  | WILSON | Zone 2 | $ |  | Interior Compactors | [5 empty] | 368266.9725
MANHATTAN |  | POLO GROUNDS TOWERS | Zone 2 | $ |  | Interior Compactors | [5 empty] | 662880.5505
MANHATTAN |  | UPACA (SITE 5) | Zone 2 | $ |  | Interior Compactors | [5 empty] | 73653.3945
MANHATTAN |  | UPACA (SITE 6) | Zone 2 | $ |  | Interior Compactors | [5 empty] | 73653.3945
MANHATTAN |  | AUDUBON | Zone 3 | $$$$ | 2020 | Interior Compactors | [5 empty] | 0 |  |  |  |  | 0
BROOKLYN |  | BORINQUEN PLAZA I | Zone 3 | $$$$ |  | Interior Compactors | [5 empty] | 589227.156
BROOKLYN |  | BORINQUEN PLAZA II | Zone 3 | $$$ |  | Interior Compactors | [5 empty] | 515573.7615
MANHATTAN |  | FORT WASHINGTON AVENUE REHAB | Zone 3 | $ | 2019 | Interior Compactors | [5 empty] | 0 |  |  |  |  | 0
MANHATTAN |  | LEXINGTON | Zone 2 | $ | 2023 | Interior Compactors | [5 empty] | 0 |  |  |  |  | 0
MANHATTAN |  | MANHATTANVILLE | Zone 2 | $ | 2028 | Interior Compactors | [5 empty] | 441920.367
MANHATTAN |  | MARSHALL PLAZA | Zone 3 | $$ | 2020 | Interior Compactors | [5 empty] | 0 |  |  |  |  | 0
MANHATTAN |  | WASHINGTON | Zone 2 | $$$ | 2023 | Interior Compactors | [5 empty] | 0 |  |  |  |  | 0
MANHATTAN |  | EAST RIVER | Zone 2 | $ | 2024 | Interior Compactors | [5 empty] | 0 |  |  |  |  | 0
MANHATTAN |  | GRANT | Zone 2 | $$$$ |  | Interior Compactors | [5 empty] | 1178454.312
BRONX |  | PATTERSON | Zone 3 | $$ | 2025 | Interior Compactors | [5 empty] | 0
BRONX | Waste Management | WEBSTER | Zone 1 | $ |  | Interior Compactors | Federal |  | 370955 | 370955 | 2019 | 368266.9725 |  | UP-COMING
BROOKLYN | Waste Management | HYLAN | Zone 1 | $ |  | Food Waste Disposer | NYCHA Operating |  | 137417.5 | 137417.5 | 2019 |  |  | UP-COMING |  |  | 359215.813
BROOKLYN | Waste Management | LAFAYETTE | Zone 1 | $$$ |  | Food Waste Disposer | NYCHA Operating |  | 632251.8422 | 632251.8422 | 2019 |  |  | UP-COMING |  |  | 1515925.1056
BROOKLYN | Waste Management | MARCY | Zone 1 | $$ | 2027 | Food Waste Disposer | City Expense | 1160763.65 |  | 1160763.65 | 2019 |  |  | UP-COMING |  |  | 2949350.8857
MANHATTAN |  | CARVER | Zone 2 | $$ |  | Bulk Crusher | [10 empty] | 1307070
MANHATTAN |  | CLINTON | Zone 2 | $$$$ |  | Bulk Crusher | [10 empty] | 1307070
MANHATTAN |  | DREW-HAMILTON | Zone 2 | $ |  | Bulk Crusher | [10 empty] | 1307070
MANHATTAN |  | EAST RIVER | Zone 2 | $ | 2024 | Bulk Crusher | [10 empty] | 0
MANHATTAN |  | GRANT | Zone 2 | $$$$ |  | Bulk Crusher | [10 empty] | 1307070
MANHATTAN |  | JEFFERSON | Zone 2 | $$ | 2026 | Bulk Crusher | [10 empty] | 1307070
MANHATTAN |  | JOHNSON | Zone 2 | $$$ | 2028 | Bulk Crusher | [10 empty] | 1307070
MANHATTAN |  | KING TOWERS | Zone 2 | $$$ |  | Bulk Crusher | [10 empty] | 1307070
MANHATTAN |  | LINCOLN | Zone 2 | $$$$ |  | Bulk Crusher | [10 empty] | 1307070
MANHATTAN |  | MANHATTANVILLE | Zone 2 | $ | 2028 | Bulk Crusher | [10 empty] | 1307070
BROOKLYN | Waste Management | MARCY | Zone 1 | $$ | 2027 | Bulk Crusher | Federal |  | 1362690 | 1362690 | 2019 |  |  | UP-COMING |  |  | 1307070
MANHATTAN |  | METRO NORTH PLAZA | Zone 2 | $ |  | Bulk Crusher | [10 empty] | 1307070
BRONX | Waste Management | MORRIS II | Zone 1 | $$$ |  | Bulk Crusher | Federal |  | 1362690 | 1362690 | 2019 |  |  | UP-COMING |  |  | 1307070
MANHATTAN |  | POLO GROUNDS TOWERS | Zone 2 | $ |  | Bulk Crusher | [10 empty] | 1307070
MANHATTAN |  | RANGEL | Zone 2 | $ |  | Bulk Crusher | [10 empty] | 1307070
MANHATTAN |  | SAINT NICHOLAS | Zone 2 | $ |  | Bulk Crusher | [10 empty] | 1307070
MANHATTAN |  | TAFT | Zone 2 | $$$ |  | Bulk Crusher | [10 empty] | 1307070
MANHATTAN |  | WAGNER | Zone 2 | $ |  | Bulk Crusher | [10 empty] | 1307070
BRONX | Waste Management | WEBSTER | Zone 1 | $ |  | Bulk Crusher | Federal |  | 1362690 | 1362690 | 2019 |  |  | UP-COMING |  |  | 1307070
MANHATTAN |  | CARVER | Zone 2 | $$ |  | Cardboard Baler | [10 empty] | 38885.4
MANHATTAN |  | CLINTON | Zone 2 | $$$$ |  | Cardboard Baler | [10 empty] | 38885.4
MANHATTAN |  | DREW-HAMILTON | Zone 2 | $ |  | Cardboard Baler | [10 empty] | 38885.4
MANHATTAN |  | EAST RIVER | Zone 2 | $ | 2024 | Cardboard Baler | [10 empty] | 0
MANHATTAN |  | GRANT | Zone 2 | $$$$ |  | Cardboard Baler | [10 empty] | 38885.4
MANHATTAN |  | JEFFERSON | Zone 2 | $$ | 2026 | Cardboard Baler | [10 empty] | 38885.4
MANHATTAN |  | JOHNSON | Zone 2 | $$$ | 2028 | Cardboard Baler | [10 empty] | 38885.4
MANHATTAN |  | KING TOWERS | Zone 2 | $$$ |  | Cardboard Baler | [10 empty] | 38885.4
MANHATTAN |  | LINCOLN | Zone 2 | $$$$ |  | Cardboard Baler | [10 empty] | 38885.4
MANHATTAN |  | MANHATTANVILLE | Zone 2 | $ | 2028 | Cardboard Baler | [10 empty] | 38885.4
BROOKLYN | Waste Management | MARCY | Zone 1 | $$ | 2027 | Cardboard Baler | City Expense | 33089.6709 |  | 33089.6709 | 2019 |  |  | UP-COMING |  |  | 38885.4
BRONX | Waste Management | MELROSE | Zone 1 | $ | 2023 | Cardboard Baler | NYCHA Operating |  | 34083.5661 | 34083.5661 | 2019 |  |  | UP-COMING |  |  | 0
MANHATTAN |  | METRO NORTH PLAZA | Zone 2 | $ |  | Cardboard Baler | [10 empty] | 38885.4
BRONX | Waste Management | MORRIS I | Zone 1 | $$ |  | Cardboard Baler | City Expense | 33090.8409 |  | 33090.8409 | 2019 |  |  | UP-COMING |  |  | 38885.4
BRONX | Waste Management | MORRISANIA AIR RIGHTS | Zone 1 | $ |  | Cardboard Baler | NYCHA Operating |  | 33090.8409 | 33090.8409 | 2019 |  |  | UP-COMING |  |  | 38885.4
MANHATTAN |  | POLO GROUNDS TOWERS | Zone 2 | $ |  | Cardboard Baler | [10 empty] | 38885.4
MANHATTAN |  | RANGEL | Zone 2 | $ |  | Cardboard Baler | [10 empty] | 38885.4
BROOKLYN | Waste Management | ROOSEVELT I | Zone 1 | $ |  | Cardboard Baler | NYCHA Operating |  | 37244.033 | 37244.033 | 2019 |  |  | UP-COMING |  |  | 38885.4
MANHATTAN |  | SAINT NICHOLAS | Zone 2 | $ |  | Cardboard Baler | [10 empty] | 38885.4
BROOKLYN | Waste Management | SUMNER | Zone 1 | $ |  | Cardboard Baler | NYCHA Operating |  | 38361.354 | 38361.354 | 2019 |  |  | UP-COMING |  |  | 38885.4
MANHATTAN |  | TAFT | Zone 2 | $$$ |  | Cardboard Baler | [10 empty] | 38885.4
MANHATTAN |  | WAGNER | Zone 2 | $ |  | Cardboard Baler | [10 empty] | 38885.4
BRONX | Waste Management | WEBSTER | Zone 1 | $ |  | Cardboard Baler | City Expense | 37244.033 |  | 37244.033 | 2019 |  |  | UP-COMING |  |  | 38885.4
MANHATTAN |  | CARVER | Zone 2 | $$ |  | Electric Tilt Truck | [10 empty] | 37000
MANHATTAN |  | EAST RIVER | Zone 2 | $ | 2024 | Electric Tilt Truck | [10 empty] | 0
MANHATTAN |  | GRANT | Zone 2 | $$$$ |  | Electric Tilt Truck | [10 empty] | 37000
MANHATTAN |  | JEFFERSON | Zone 2 | $$ | 2026 | Electric Tilt Truck | [10 empty] | 37000
MANHATTAN |  | JOHNSON | Zone 2 | $$$ | 2028 | Electric Tilt Truck | [10 empty] | 37000
MANHATTAN |  | KING TOWERS | Zone 2 | $$$ |  | Electric Tilt Truck | [10 empty] | 37000
MANHATTAN |  | LINCOLN | Zone 2 | $$$$ |  | Electric Tilt Truck | [10 empty] | 37000
MANHATTAN |  | RANGEL | Zone 2 | $ |  | Electric Tilt Truck | [10 empty] | 37000
MANHATTAN |  | SAINT NICHOLAS | Zone 2 | $ |  | Electric Tilt Truck | [10 empty] | 37000
MANHATTAN |  | TAFT | Zone 2 | $$$ |  | Electric Tilt Truck | [10 empty] | 37000
MANHATTAN |  | WAGNER | Zone 2 | $ |  | Electric Tilt Truck | [10 empty] | 37000
MANHATTAN |  | 131 SAINT NICHOLAS AVENUE | Zone 2 | $ |  | Enlarge Hopper Door | [10 empty] | 0
BROOKLYN | Waste Management | 303 VERNON AVENUE | Zone 1 | $ |  | Enlarge Hopper Door | NYCHA Operating |  | 3000 | 3000 | 2019 |  |  | UP-COMING |  |  | 0
BROOKLYN | Waste Management | BEDFORD-STUYVESANT REHAB | Zone 1 | $ |  | Enlarge Hopper Door | NYCHA Operating |  | 15000 | 15000 | 2019 |  |  | UP-COMING |  |  | 0
MANHATTAN |  | CARVER | Zone 2 | $$ |  | Enlarge Hopper Door | [10 empty] | 0
BRONX | Waste Management | CLAREMONT REHAB (GROUP 2) | Zone 1 | $ | 2025 | Enlarge Hopper Door | NYCHA Operating |  | 12000 | 12000 | 2019 |  |  | UP-COMING |  |  | 0
BRONX | Waste Management | CLAREMONT REHAB (GROUP 5) | Zone 1 | $ | 2025 | Enlarge Hopper Door | NYCHA Operating |  | 9000 | 9000 | 2019 |  |  | UP-COMING |  |  | 0
MANHATTAN |  | CLINTON | Zone 2 | $$$$ |  | Enlarge Hopper Door | [10 empty] | 0
BRONX | Waste Management | COLLEGE AVENUE-EAST 165TH STREET | Zone 1 | $ | 2025 | Enlarge Hopper Door | NYCHA Operating |  | 3000 | 3000 | 2019 |  |  | UP-COMING |  |  | 0
MANHATTAN |  | CORSI HOUSES | Zone 2 | $ | 2026 | Enlarge Hopper Door | [10 empty] | 0
MANHATTAN |  | DREW-HAMILTON | Zone 2 | $ |  | Enlarge Hopper Door | [10 empty] | 0
BRONX | Waste Management | EAST 180TH STREET-MONTEREY AVENUE | Zone 1 | $$ |  | Enlarge Hopper Door | City Expense | 3000 |  | 3000 | 2019 |  |  | UP-COMING |  |  | 0
MANHATTAN |  | EAST RIVER | Zone 2 | $ | 2024 | Enlarge Hopper Door | [10 empty] | 0
MANHATTAN |  | GRANT | Zone 2 | $$$$ |  | Enlarge Hopper Door | [10 empty] | 0
BROOKLYN | Waste Management | HYLAN | Zone 1 | $ |  | Enlarge Hopper Door | NYCHA Operating |  | 3000 | 3000 | 2019 |  |  | UP-COMING |  |  | 0
MANHATTAN |  | JEFFERSON | Zone 2 | $$ | 2026 | Enlarge Hopper Door | [10 empty] | 0
MANHATTAN |  | JOHNSON | Zone 2 | $$$ | 2028 | Enlarge Hopper Door | [10 empty] | 0
MANHATTAN |  | KING TOWERS | Zone 2 | $$$ |  | Enlarge Hopper Door | [10 empty] | 0
MANHATTAN |  | LEHMAN VILLAGE | 0 | 0 |  | Enlarge Hopper Door | [10 empty] | 0
MANHATTAN |  | LEXINGTON | Zone 2 | $ | 2023 | Enlarge Hopper Door | [10 empty] | 0
MANHATTAN |  | LINCOLN | Zone 2 | $$$$ |  | Enlarge Hopper Door | [10 empty] | 0
MANHATTAN |  | MANHATTANVILLE | Zone 2 | $ | 2028 | Enlarge Hopper Door | [10 empty] | 0
MANHATTAN |  | METRO NORTH PLAZA | Zone 2 | $ |  | Enlarge Hopper Door | [10 empty] | 0
BRONX | Waste Management | MORRIS II | Zone 1 | $$$ |  | Enlarge Hopper Door | City Expense | 3000 |  | 3000 | 2019 |  |  | UP-COMING |  |  | 0
MANHATTAN |  | MORRIS PARK SENIOR CITIZENS HOME | Zone 2 | $$$$ |  | Enlarge Hopper Door | [10 empty] | 0
BRONX | Waste Management | MORRISANIA | Zone 1 | $$$$ |  | Enlarge Hopper Door | City Expense | 6000 |  | 6000 | 2019 |  |  | UP-COMING |  |  | 0
MANHATTAN |  | POLO GROUNDS TOWERS | Zone 2 | $ |  | Enlarge Hopper Door | [10 empty] | 0
MANHATTAN |  | RANGEL | Zone 2 | $ |  | Enlarge Hopper Door | [10 empty] | 0
MANHATTAN |  | ROBINSON | Zone 2 | $$ |  | Enlarge Hopper Door | [10 empty] | 0
BROOKLYN | Waste Management | ROOSEVELT II | Zone 1 | $ |  | Enlarge Hopper Door | NYCHA Operating |  | 9000 | 9000 | 2019 |  |  | UP-COMING |  |  | 0
MANHATTAN |  | SAINT NICHOLAS | Zone 2 | $ |  | Enlarge Hopper Door | [10 empty] | 0
MANHATTAN |  | SAMUEL (CITY) | Zone 2 | $$ | 2026 | Enlarge Hopper Door | [10 empty] | 0
MANHATTAN |  | TAFT | Zone 2 | $$$ |  | Enlarge Hopper Door | [10 empty] | 0
BRONX | Waste Management | TELLER AVENUE-EAST 166TH STREET | Zone 1 | $ | 2025 | Enlarge Hopper Door | NYCHA Operating |  | 6000 | 6000 | 2019 |  |  | UP-COMING |  |  | 0
MANHATTAN |  | UPACA (SITE 5) | Zone 2 | $ |  | Enlarge Hopper Door | [10 empty] | 0
MANHATTAN |  | UPACA (SITE 6) | Zone 2 | $ |  | Enlarge Hopper Door | [10 empty] | 0
MANHATTAN |  | WAGNER | Zone 2 | $ |  | Enlarge Hopper Door | [10 empty] | 0
MANHATTAN |  | WASHINGTON | Zone 2 | $$$ | 2023 | Enlarge Hopper Door | [10 empty] | 0
MANHATTAN |  | WHITE | Zone 2 | $ |  | Enlarge Hopper Door | [10 empty] | 0
MANHATTAN |  | WILSON | Zone 2 | $ |  | Enlarge Hopper Door | [10 empty] | 0
MANHATTAN |  | CARVER | Zone 2 | $$ |  | Mattress Recycling | [10 empty] | 13656
MANHATTAN |  | CLINTON | Zone 2 | $$$$ |  | Mattress Recycling | [10 empty] | 13656
MANHATTAN |  | DREW-HAMILTON | Zone 2 | $ |  | Mattress Recycling | [10 empty] | 13656
MANHATTAN |  | EAST RIVER | Zone 2 | $ | 2024 | Mattress Recycling | [10 empty] | 0
MANHATTAN |  | GRANT | Zone 2 | $$$$ |  | Mattress Recycling | [10 empty] | 13656
MANHATTAN |  | JEFFERSON | Zone 2 | $$ | 2026 | Mattress Recycling | [10 empty] | 13656
MANHATTAN |  | JOHNSON | Zone 2 | $$$ | 2028 | Mattress Recycling | [10 empty] | 13656
MANHATTAN |  | KING TOWERS | Zone 2 | $$$ |  | Mattress Recycling | [10 empty] | 13656
MANHATTAN |  | LINCOLN | Zone 2 | $$$$ |  | Mattress Recycling | [10 empty] | 13656
MANHATTAN |  | MANHATTANVILLE | Zone 2 | $ | 2028 | Mattress Recycling | [10 empty] | 13656
MANHATTAN |  | METRO NORTH PLAZA | Zone 2 | $ |  | Mattress Recycling | [10 empty] | 13656
MANHATTAN |  | POLO GROUNDS TOWERS | Zone 2 | $ |  | Mattress Recycling | [10 empty] | 13656
MANHATTAN |  | RANGEL | Zone 2 | $ |  | Mattress Recycling | [10 empty] | 13656
MANHATTAN |  | SAINT NICHOLAS | Zone 2 | $ |  | Mattress Recycling | [10 empty] | 13656
MANHATTAN |  | TAFT | Zone 2 | $$$ |  | Mattress Recycling | [10 empty] | 13656
MANHATTAN |  | WAGNER | Zone 2 | $ |  | Mattress Recycling | [10 empty] | 13656
MANHATTAN |  | CARVER | Zone 2 | $$ |  | Secondary collection areas | [10 empty] | 133611.6
MANHATTAN |  | EAST RIVER | Zone 2 | $ | 2024 | Secondary collection areas | [10 empty] | 0
MANHATTAN |  | GRANT | Zone 2 | $$$$ |  | Secondary collection areas | [10 empty] | 133611.6
MANHATTAN |  | JEFFERSON | Zone 2 | $$ | 2026 | Secondary collection areas | [10 empty] | 133611.6
MANHATTAN |  | JOHNSON | Zone 2 | $$$ | 2028 | Secondary collection areas | [10 empty] | 133611.6
MANHATTAN |  | KING TOWERS | Zone 2 | $$$ |  | Secondary collection areas | [10 empty] | 133611.6
MANHATTAN |  | LINCOLN | Zone 2 | $$$$ |  | Secondary collection areas | [10 empty] | 133611.6
BROOKLYN | Waste Management | MARCY | Zone 1 | $$ | 2027 | Secondary collection areas | Federal |  | 800958.9 | 800958.9 | 2019 | [5 empty] | 133611.6
MANHATTAN |  | RANGEL | Zone 2 | $ |  | Secondary collection areas | [10 empty] | 133611.6
MANHATTAN |  | SAINT NICHOLAS | Zone 2 | $ |  | Secondary collection areas | [10 empty] | 133611.6
MANHATTAN |  | TAFT | Zone 2 | $$$ |  | Secondary collection areas | [10 empty] | 133611.6
MANHATTAN |  | WAGNER | Zone 2 | $ |  | Secondary collection areas | [10 empty] | 133611.6
MANHATTAN |  | WASHINGTON | Zone 2 | $$$ | 2023 | Secondary collection areas | [10 empty] | 0

## all
520345101.2309
| Data Source: | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 8 | 1 | 6 | 6 | 3 | 3 |  | 5 | 2,4 | 1,4 | 1,4 | 1,4 |  | 7
TDS | DEVELOPMENT | BOROUGH | MANAGED BY | NRR | Priority Level | RAD/PACT | Is RAD/PACT w/in 5yr | DUs | Is in the Newtown Creek Watershed? | # Buildings | # Interior Compactors | # Interior Compactors to Replace | # Exterior Compactors | # Exterior Compactors to Replace | # Bulk Crushers | # Bulk Crushers to Install | FWD Estimate | EHD Estimate | Interior Compactor Estimate | Waste Yard Estimate | SUM per Development | Notes
180 | 1010 EAST 178TH STREET | BRONX | MURPHY | 0 | 0 |  |  | 218 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 7435.6435 | 73653.3945 | 1159792.78 | 1240881.818
242 | 104-14 TAPSCOTT STREET | BROOKLYN | REID APARTMENTS | 0 | 0 | 2021 | Yes | 30 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 14871.287 | 0 | 0 | 14871.287
233 | 1162-1176 WASHINGTON AVENUE | BRONX | CLAREMONT CONSOLIDATED | 0 | 0 | 2025 |  | 65 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 7435.6435 | 0 | 0 | 7435.6435
154 | 131 SAINT NICHOLAS AVENUE | MANHATTAN | TAFT | Zone 2 | $ |  |  | 98 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 7435.6435 | 73653.3945 | 1159792.78 | 1240881.818
214 | 1471 WATSON AVENUE | BRONX | SOTOMAYOR HOUSES | 0 | 0 | 2021 | Yes | 96 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 14871.287 | 0 | 0 | 14871.287
359 | 154 WEST 84TH STREET | MANHATTAN | KRAUS MANAGEMENT (PRIVATE - M/B 1) | 0 | 0 |  |  | 35 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 7435.6435 | 73653.3945 | 1159792.78 | 1240881.818
156 | 303 VERNON AVENUE | BROOKLYN | SUMNER | Zone 1 | $ |  |  | 234 | Yes | 1 | 2 | 2 | 0 | 0 | 0 | 1 | 402184.2117 | 14871.287 | 147306.789 | 1159792.78 | 1724155.0677
203 | 335 EAST 111TH STREET | MANHATTAN | JEFFERSON | Zone 3 | $ |  |  | 66 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 7435.6435 | 73653.3945 | 1159792.78 | 1240881.818
185 | 344 EAST 28TH STREET | MANHATTAN | STRAUS | 0 | 0 |  |  | 225 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 386715.5882 | 7435.6435 | 73653.3945 | 1159792.78 | 1627597.4062
265 | 45 ALLEN STREET | MANHATTAN | GOMPERS | Zone 1 | $$ |  |  | 107 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 183904.7464 | 7435.6435 | 73653.3945 | 1159792.78 | 1424786.5644
196 | 572 WARREN STREET | BROOKLYN | WYCKOFF GARDENS | 0 | 0 |  |  | 200 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 14871.287 | 147306.789 | 1159792.78 | 1321970.856
150 | 830 AMSTERDAM AVENUE | MANHATTAN | DOUGLASS | 0 | 0 |  |  | 158 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 14871.287 | 147306.789 | 1159792.78 | 1321970.856
118 | ADAMS | BRONX | ADAMS | 0 | 0 |  |  | 924 | 0 | 7 | 7 | 7 | 2 | 2 | 0 | 1 | 0 | 52049.5045 | 515573.7615 | 1591050.02 | 2158673.286
31 | ALBANY | BROOKLYN | ALBANY | 0 | 0 | 2025 |  | 823 | Yes | 6 | 6 | 6 | 0 | 0 | 0 | 1 | 1414519.6847 | 44613.861 | 0 | 0 | 1459133.5457
85 | ALBANY II | BROOKLYN | ALBANY | 0 | 0 | 2025 |  | 400 | Yes | 3 | 3 | 3 | 3 | 3 | 0 | 1 | 687494.379 | 22306.9305 | 0 | 0 | 709801.3095
22 | AMSTERDAM | MANHATTAN | AMSTERDAM | Zone 4 | 0 |  |  | 1084 | 0 | 13 | 24 | 24 | 3 | 3 | 0 | 1 | 0 | 178455.444 | 1767681.468 | 2022307.26 | 3968444.172
187 | AMSTERDAM ADDITION | MANHATTAN | AMSTERDAM | 0 | 0 |  |  | 175 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 14871.287 | 147306.789 | 1159792.78 | 1321970.856
210 | ARMSTRONG I | BROOKLYN | ARMSTRONG I | Zone 1 | $ |  |  | 369 | Yes | 11 | 6 | 6 | 0 | 0 | 0 | 1 | 634213.5646 | 44613.861 | 441920.367 | 1159792.78 | 2280540.5726
228 | ARMSTRONG II | BROOKLYN | ARMSTRONG I | Zone 1 | $ |  |  | 248 | Yes | 5 | 10 | 10 | 0 | 0 | 0 | 1 | 426246.515 | 74356.435 | 736533.945 | 1159792.78 | 2396929.675
26 | ASTORIA | QUEENS | ASTORIA | 0 | 0 | 2024 | Yes | 1104 | 0 | 22 | 22 | 22 | 3 | 3 | 0 | 1 | 0 | 163584.157 | 0 | 0 | 163584.157
256 | ATLANTIC TERMINAL SITE 4B | BROOKLYN | WYCKOFF GARDENS | 0 | 0 |  |  | 299 | 0 | 1 | 2 | 2 | 1 | 1 | 0 | 1 | 0 | 14871.287 | 147306.789 | 1159792.78 | 1321970.856
125 | AUDUBON | MANHATTAN | HARLEM RIVER | Zone 3 | $$$$ | 2020 | Yes | 167 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
202 | BAILEY AVENUE-WEST 193RD STREET | BRONX | FORT INDEPENDENCE | 0 | 0 |  |  | 232 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 7435.6435 | 73653.3945 | 1159792.78 | 1240881.818
91 | BAISLEY PARK | QUEENS | BAISLEY PARK | 0 | 0 |  |  | 381 | 0 | 5 | 5 | 5 | 0 | 0 | 0 | 1 | 0 | 37178.2175 | 368266.9725 | 1159792.78 | 1565237.97
60 | BARUCH | MANHATTAN | BARUCH | Zone 1 | $ |  |  | 2193 | Yes | 17 | 17 | 0 | 0 | 0 | 0 | 1 | 3769187.9326 | 126405.9395 | 0 | 1159792.78 | 5055386.6521
198 | BARUCH HOUSES ADDITION | MANHATTAN | BARUCH | Zone 1 | $ |  |  | 197 | Yes | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1159792.78 | 1159792.78
92 | BAY VIEW | BROOKLYN | BAY VIEW | 0 | 0 |  |  | 1609 | 0 | 23 | 23 | 23 | 4 | 4 | 0 | 1 | 0 | 171019.8005 | 1694028.0735 | 2453564.5 | 4318612.374
165 | BEACH 41ST STREET-BEACH CHANNEL DRIVE | QUEENS | BEACH 41ST STREET-BEACH CHANNEL DRIVE | 0 | 0 |  |  | 712 | 0 | 4 | 6 | 6 | 1 | 1 | 0 | 1 | 0 | 44613.861 | 441920.367 | 1159792.78 | 1646327.008
311 | BEDFORD-STUYVESANT REHAB | BROOKLYN | SUMNER | Zone 1 | $ |  |  | 84 | Yes | 3 | 5 | 5 | 0 | 0 | 0 | 1 | 144373.8196 | 37178.2175 | 368266.9725 | 1159792.78 | 1709611.7896
345 | BELMONT-SUTTER AREA | BROOKLYN | BOULEVARD | 0 | 0 |  |  | 72 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1159792.78 | 1159792.78
52 | BERRY | STATEN ISLAND | BERRY | 0 | 0 |  |  | 506 | 0 | 8 | 15 | 15 | 1 | 1 | 0 | 1 | 0 | 111534.6525 | 1104800.9175 | 1159792.78 | 2376128.35
357 | BERRY STREET-SOUTH 9TH STREET | BROOKLYN | TOMPKINS | 0 | 0 |  |  | 150 | Yes | 4 | 1 | 1 | 1 | 1 | 0 | 1 | 257810.3921 | 7435.6435 | 73653.3945 | 1159792.78 | 1498692.2101
160 | BETHUNE GARDENS | MANHATTAN | HARLEM RIVER | Zone 3 | $$ | 2020 | Yes | 210 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
54 | BLAND | QUEENS | LATIMER GARDENS | 0 | 0 |  |  | 399 | 0 | 5 | 5 | 5 | 0 | 0 | 0 | 1 | 0 | 37178.2175 | 368266.9725 | 1159792.78 | 1565237.97
243 | BORINQUEN PLAZA I | BROOKLYN | BORINQUEN PLAZA I | Zone 3 | $$$$ |  |  | 509 | Yes | 8 | 8 | 8 | 2 | 2 | 0 | 1 | 874836.5972 | 59485.148 | 589227.156 | 1591050.02 | 3114598.9212
271 | BORINQUEN PLAZA II | BROOKLYN | BORINQUEN PLAZA I | Zone 3 | $$$ |  |  | 425 | Yes | 7 | 7 | 7 | 0 | 0 | 0 | 1 | 730462.7776 | 52049.5045 | 515573.7615 | 1159792.78 | 2457878.8236
189 | BOSTON ROAD PLAZA | BRONX | PELHAM PARKWAY | 0 | 0 | 2022 | Yes | 232 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
138 | BOSTON SECOR | BRONX | BOSTON SECOR | 0 | 0 |  |  | 538 | 0 | 4 | 4 | 4 | 2 | 2 | 0 | 1 | 0 | 29742.574 | 294613.578 | 1591050.02 | 1915406.172
46 | BOULEVARD | BROOKLYN | BOULEVARD | 0 | 0 | 2020 | Yes | 1424 | 0 | 18 | 29 | 29 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
346 | BOYNTON AVENUE REHAB | BRONX | BRONX RIVER | 0 | 0 |  |  | 82 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 1 | 0 | 22306.9305 | 220960.1835 | 1159792.78 | 1403059.894
264 | BRACETTI PLAZA | MANHATTAN | LOWER EAST SIDE CONSOLIDATED | Zone 1 | $ | 2026 |  | 108 | Yes | 1 | 2 | 2 | 0 | 0 | 0 | 1 | 185623.4823 | 14871.287 | 147306.789 | 1159792.78 | 1507594.3383
56 | BREUKELEN | BROOKLYN | BREUKELEN | 0 | 0 | 2021 | Yes | 1592 | 0 | 30 | 89 | 89 | 4 | 4 | 0 | 1 | 0 | 661772.2715 | 0 | 0 | 661772.2715
65 | BREVOORT | BROOKLYN | BREVOORT | 0 | 0 |  |  | 894 | Yes | 13 | 26 | 26 | 2 | 2 | 0 | 1 | 1536549.937 | 193326.731 | 1914988.257 | 1591050.02 | 5235914.945
32 | BRONX RIVER | BRONX | BRONX RIVER | Zone 3 | $ |  |  | 1245 | 0 | 9 | 9 | 9 | 3 | 3 | 0 | 1 | 0 | 66920.7915 | 662880.5505 | 2022307.26 | 2752108.602
157 | BRONX RIVER ADDITION | BRONX | BRONX RIVER | 0 | 0 |  |  | 226 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 147306.789 | 1159792.78 | 1307099.569
325 | BROWN | BROOKLYN | GARVEY | 0 | 0 |  |  | 200 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 147306.789 | 1159792.78 | 1307099.569
16 | BROWNSVILLE | BROOKLYN | BROWNSVILLE | 0 | 0 |  |  | 1336 | 0 | 27 | 46 | 46 | 3 | 3 | 0 | 1 | 0 | 342039.601 | 3388056.147 | 2022307.26 | 5752403.008
235 | BRYANT AVENUE-EAST 174TH STREET | BRONX | BUILDING MANAGEMENT ASSOCIATES (PRIVATE - BX 1) | 0 | 0 |  |  | 72 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 7435.6435 | 73653.3945 | 1159792.78 | 1240881.818
86 | BUSHWICK | BROOKLYN | BUSHWICK | Zone 1 | $$ |  |  | 1219 | Yes | 8 | 8 | 8 | 2 | 2 | 0 | 1 | 2095139.1199 | 0 | 589227.156 | 1591050.02 | 4275416.2959
113 | BUTLER | BRONX | BUTLER | Zone 1 | $$ |  |  | 1476 | 0 | 6 | 12 | 12 | 2 | 2 | 0 | 1 | 0 | 0 | 883840.734 | 1591050.02 | 2474890.754
286 | CAMPOS PLAZA II | MANHATTAN | LOWER EAST SIDE CONSOLIDATED | Zone 1 | $$ | 2026 |  | 224 | Yes | 2 | 3 | 3 | 0 | 0 | 0 | 1 | 384996.8522 | 22306.9305 | 220960.1835 | 1159792.78 | 1788056.7462
166 | CAREY GARDENS | BROOKLYN | CAREY GARDENS | 0 | 0 |  |  | 682 | 0 | 3 | 3 | 3 | 2 | 2 | 0 | 1 | 0 | 22306.9305 | 220960.1835 | 1591050.02 | 1834317.134
164 | CARLETON MANOR | QUEENS | HAMMEL | 0 | 0 |  |  | 169 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 7435.6435 | 73653.3945 | 1159792.78 | 1240881.818
58 | CARVER | MANHATTAN | CARVER | Zone 2 | $$ |  |  | 1244 | 0 | 13 | 13 | 13 | 3 | 3 | 0 | 1 | 0 | 96663.3655 | 957494.1285 | 2022307.26 | 3076464.754
206 | CASSIDY-LAFAYETTE | STATEN ISLAND | RICHMOND TERRACE | 0 | 0 |  |  | 378 | 0 | 4 | 4 | 4 | 1 | 1 | 0 | 1 | 0 | 0 | 294613.578 | 1159792.78 | 1454406.358
80 | CASTLE HILL | BRONX | CASTLE HILL | 0 | 0 |  |  | 2022 | 0 | 14 | 14 | 14 | 4 | 4 | 0 | 1 | 0 | 104099.009 | 1031147.523 | 2453564.5 | 3588811.032
134 | CHELSEA | MANHATTAN | CHELSEA | 0 | 0 |  |  | 425 | 0 | 2 | 4 | 4 | 0 | 0 | 0 | 1 | 0 | 29742.574 | 294613.578 | 1159792.78 | 1484148.932
176 | CHELSEA ADDITION | MANHATTAN | CHELSEA | 0 | 0 |  |  | 96 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 7435.6435 | 73653.3945 | 1159792.78 | 1240881.818
334 | CLAREMONT PARKWAY-FRANKLIN AVENUE | BRONX | UNION AVENUE CONSOLIDATED | Zone 3 | $ | 2026 |  | 187 | 0 | 3 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 7435.6435 | 73653.3945 | 1159792.78 | 1240881.818
307 | CLAREMONT REHAB (GROUP 2) | BRONX | CLAREMONT CONSOLIDATED | Zone 1 | $ | 2025 |  | 106 | 0 | 6 | 5 | 5 | 0 | 0 | 0 | 1 | 0 | 37178.2175 | 0 | 0 | 37178.2175
308 | CLAREMONT REHAB (GROUP 3) | BRONX | CLAREMONT CONSOLIDATED | Zone 1 | $ | 2025 |  | 107 | 0 | 5 | 4 | 4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
335 | CLAREMONT REHAB (GROUP 4) | BRONX | CLAREMONT CONSOLIDATED | Zone 1 | $ | 2025 |  | 147 | 0 | 9 | 9 | 9 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
336 | CLAREMONT REHAB (GROUP 5) | BRONX | CLAREMONT CONSOLIDATED | Zone 1 | $ | 2025 |  | 129 | 0 | 3 | 4 | 4 | 0 | 0 | 0 | 1 | 0 | 29742.574 | 0 | 0 | 29742.574
11 | CLASON POINT GARDENS | BRONX | SACK WERN | 0 | 0 | 2024 | Yes | 401 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
123 | CLINTON | MANHATTAN | CLINTON | Zone 2 | $$$$ |  |  | 748 | 0 | 6 | 6 | 6 | 1 | 1 | 0 | 1 | 0 | 44613.861 | 441920.367 | 1159792.78 | 1646327.008
236 | COLLEGE AVENUE-EAST 165TH STREET | BRONX | CLAREMONT CONSOLIDATED | Zone 1 | $ | 2025 |  | 95 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 7435.6435 | 0 | 0 | 7435.6435
94 | CONEY ISLAND | BROOKLYN | SURFSIDE GARDENS | 0 | 0 |  |  | 530 | 0 | 5 | 5 | 5 | 0 | 0 | 0 | 1 | 0 | 37178.2175 | 368266.9725 | 1159792.78 | 1565237.97
239 | CONEY ISLAND I (SITE 1B) | BROOKLYN | CAREY GARDENS | 0 | 0 |  |  | 192 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 7435.6435 | 73653.3945 | 1159792.78 | 1240881.818
238 | CONEY ISLAND I (SITE 8) | BROOKLYN | O'DWYER GARDENS | 0 | 0 |  |  | 124 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 7435.6435 | 73653.3945 | 1159792.78 | 1240881.818
216 | CONEY ISLAND I (SITES 4 & 5) | BROOKLYN | SURFSIDE GARDENS | 0 | 0 |  |  | 376 | 0 | 1 | 3 | 3 | 1 | 1 | 1 | 0 | 0 | 22306.9305 | 220960.1835 | 1159792.78 | 1403059.894
232 | CONLON LIHFE TOWER | QUEENS | BAISLEY PARK | 0 | 0 |  |  | 214 | 0 | 1 | 1 | 1 | 2 | 2 | 0 | 1 | 0 | 0 | 73653.3945 | 1591050.02 | 1664703.4145
69 | COOPER PARK | BROOKLYN | COOPER PARK | 0 | 0 |  |  | 700 | Yes | 11 | 13 | 13 | 2 | 2 | 0 | 1 | 1203115.1632 | 96663.3655 | 957494.1285 | 1591050.02 | 3848322.6772
199 | CORSI HOUSES | MANHATTAN | JEFFERSON | Zone 2 | $ | 2026 |  | 171 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 73653.3945 | 1159792.78 | 1233446.1745
312 | CROWN HEIGHTS | BROOKLYN | PARK ROCK CONSOLIDATED | Zone 4 | 0 | 2025 |  | 121 | Yes | 8 | 8 | 8 | 0 | 0 | 0 | 1 | 207967.0496 | 59485.148 | 0 | 0 | 267452.1976
70 | CYPRESS HILLS | BROOKLYN | CYPRESS HILLS | 0 | 0 | 2023 | Yes | 1439 | 0 | 15 | 29 | 29 | 3 | 0 | 0 | 1 | 0 | 215633.6615 | 0 | 0 | 215633.6615
190 | DAVIDSON | BRONX | UNION AVENUE CONSOLIDATED | Zone 3 | $ | 2026 |  | 175 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 7435.6435 | 73653.3945 | 1159792.78 | 1240881.818
155 | DE HOSTOS APARTMENTS | MANHATTAN | WISE TOWERS | 0 | 0 |  |  | 219 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 14871.287 | 147306.789 | 1159792.78 | 1321970.856
148 | DOUGLASS ADDITION | MANHATTAN | DOUGLASS | Zone 3 | $ |  |  | 135 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 7435.6435 | 73653.3945 | 1159792.78 | 1240881.818
82 | DOUGLASS I | MANHATTAN | DOUGLASS | Zone 3 | $$$ |  |  | 1302 | 0 | 11 | 11 | 11 | 0 | 0 | 0 | 1 | 0 | 81792.0785 | 810187.3395 | 1159792.78 | 2051772.198
582 | DOUGLASS II | MANHATTAN | DOUGLASS | Zone 3 | $$$ |  |  | 752 | 0 | 6 | 6 | 6 | 0 | 0 | 0 | 1 | 0 | 44613.861 | 441920.367 | 1159792.78 | 1646327.008
111 | DREW-HAMILTON | MANHATTAN | DREW-HAMILTON | Zone 2 | $ |  |  | 1211 | 0 | 5 | 5 | 5 | 2 | 2 | 0 | 1 | 0 | 37178.2175 | 368266.9725 | 1591050.02 | 1996495.21
41 | DYCKMAN | MANHATTAN | DYCKMAN | 0 | 0 |  |  | 1167 | 0 | 7 | 14 | 14 | 2 | 0 | 0 | 1 | 0 | 104099.009 | 1031147.523 | 1159792.78 | 2295039.312
224 | EAGLE AVENUE-EAST 163RD STREET | BRONX | FOREST | 0 | 0 |  |  | 65 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 7435.6435 | 73653.3945 | 1159792.78 | 1240881.818
237 | EAST 152ND STREET-COURTLANDT AVENUE | BRONX | MELROSE | 0 | 0 | 2023 | Yes | 221 | 0 | 2 | 2 | 2 | 1 | 1 | 0 | 1 | 0 | 14871.287 | 0 | 0 | 14871.287
304 | EAST 165TH STREET-BRYANT AVENUE | BRONX | BUILDING MANAGEMENT ASSOCIATES (PRIVATE - BX 1) | Zone 4 | 0 |  |  | 111 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1159792.78 | 1159792.78
338 | EAST 173RD STREET-VYSE AVENUE | BRONX | BUILDING MANAGEMENT ASSOCIATES (PRIVATE - BX 1) | Zone 4 | 0 |  |  | 168 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
208 | EAST 180TH STREET-MONTEREY AVENUE | BRONX | TWIN PARKS CONSOLIDATED | Zone 1 | $$ |  |  | 239 | 0 | 1 | 2 | 2 | 1 | 1 | 0 | 1 | 0 | 14871.287 | 147306.789 | 1159792.78 | 1321970.856
263 | EAST NEW YORK CITY LINE | BROOKLYN | CYPRESS HILLS | 0 | 0 | 2023 | Yes | 66 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
9 | EAST RIVER | MANHATTAN | EAST RIVER | Zone 2 | $ | 2024 | Yes | 1156 | 0 | 10 | 29 | 29 | 2 | 2 | 0 | 1 | 0 | 215633.6615 | 0 | 0 | 215633.6615
34 | EASTCHESTER GARDENS | BRONX | EASTCHESTER GARDENS | 0 | 0 | 2026 |  | 877 | 0 | 10 | 15 | 15 | 2 | 2 | 0 | 1 | 0 | 111534.6525 | 1104800.9175 | 1591050.02 | 2807385.59
57 | EDENWALD | BRONX | EDENWALD | 0 | 0 | 2022 | Yes | 2035 | 0 | 40 | 62 | 3 | 5 | 0 | 0 | 1 | 0 | 461009.897 | 0 | 0 | 461009.897
15 | ELLIOTT | MANHATTAN | CHELSEA | 0 | 0 |  |  | 606 | 0 | 4 | 8 | 8 | 2 | 0 | 0 | 1 | 0 | 59485.148 | 589227.156 | 1159792.78 | 1808505.084
29 | FARRAGUT | BROOKLYN | FARRAGUT | 0 | 0 | 2027 |  | 1389 | Yes | 10 | 10 | 10 | 1 | 1 | 0 | 1 | 2387324.2309 | 74356.435 | 736533.945 | 1159792.78 | 4358007.3909
205 | FENIMORE-LEFFERTS | BROOKLYN | REID APARTMENTS | 0 | 0 | 2021 | Yes | 36 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
209 | FHA REPOSSESSED HOUSES (GROUP I) | 0 | BAISLEY PARK | 0 | 0 |  |  | 21 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
212 | FHA REPOSSESSED HOUSES (GROUP II) | 0 | BAISELY PARK | 0 | 0 |  |  | 10 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
213 | FHA REPOSSESSED HOUSES (GROUP III) | 0 | BAISLEY PARK | 0 | 0 |  |  | 11 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
226 | FHA REPOSSESSED HOUSES (GROUP IV) | 0 | BAISLEY PARK | 0 | 0 |  |  | 10 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
283 | FHA REPOSSESSED HOUSES (GROUP IX) | 0 | BAISLEY PARK | Zone 4 | 0 |  |  | 16 | Yes | 16 | 0 | 0 | 0 | 0 | 0 | 1 | 27499.7752 | 0 | 0 | 0 | 27499.7752
260 | FHA REPOSSESSED HOUSES (GROUP V) | 0 | BAISLEY PARK | 0 | 0 |  |  | 29 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
273 | FHA REPOSSESSED HOUSES (GROUP VI) | 0 | BAISLEY PARK | 0 | 0 |  |  | 6 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
274 | FHA REPOSSESSED HOUSES (GROUP VII) | 0 | BAISLEY PARK | 0 | 0 |  |  | 5 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
275 | FHA REPOSSESSED HOUSES (GROUP VIII) | 0 | BAISLEY PARK | 0 | 0 |  |  | 5 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
284 | FHA REPOSSESSED HOUSES (GROUP X) | 0 | BAISLEY PARK | 0 | 0 |  |  | 16 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
207 | FIORENTINO PLAZA | BROOKLYN | UNITY PLAZA | 0 | 0 | 2026 |  | 158 | 0 | 8 | 3 | 3 | 0 | 0 | 0 | 1 | 0 | 22306.9305 | 220960.1835 | 1159792.78 | 1403059.894
1 | FIRST HOUSES | MANHATTAN | LOWER EAST SIDE CONSOLIDATED | Zone 1 | $ | 2026 |  | 126 | Yes | 8 | 8 | 8 | 0 | 0 | 0 | 1 | 216560.7294 | 59485.148 | 589227.156 | 1159792.78 | 2025065.8134
59 | FOREST | BRONX | FOREST | Zone 4 | 0 |  |  | 1348 | 0 | 15 | 15 | 15 | 3 | 3 | 0 | 1 | 0 | 111534.6525 | 1104800.9175 | 2022307.26 | 3238642.83
197 | FORT INDEPENDENCE STREET-HEATH AVENUE | BRONX | FORT INDEPENDENCE | 0 | 0 |  |  | 342 | 0 | 1 | 2 | 2 | 1 | 1 | 0 | 1 | 0 | 14871.287 | 147306.789 | 1159792.78 | 1321970.856
309 | FORT WASHINGTON AVENUE REHAB | MANHATTAN | FORT WASHINGTON | Zone 3 | $ | 2019 | Yes | 226 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
136 | FULTON | MANHATTAN | FULTON | Zone 3 | $ |  |  | 944 | 0 | 11 | 19 | 19 | 2 | 2 | 0 | 1 | 0 | 141277.2265 | 1399414.4955 | 1591050.02 | 3131741.742
252 | GARVEY (GROUP A) | BROOKLYN | GARVEY | 0 | 0 |  |  | 320 | 0 | 3 | 5 | 5 | 0 | 0 | 0 | 1 | 0 | 37178.2175 | 368266.9725 | 1159792.78 | 1565237.97
225 | GLEBE AVENUE-WESTCHESTER AVENUE | BRONX | SOTOMAYOR HOUSES | 0 | 0 | 2021 | Yes | 131 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 14871.287 | 0 | 0 | 14871.287
171 | GLENMORE PLAZA | BROOKLYN | LOW HOUSES | 0 | 0 |  |  | 439 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 1 | 0 | 29742.574 | 294613.578 | 1159792.78 | 1484148.932
44 | GLENWOOD | BROOKLYN | GLENWOOD | 0 | 0 | 2028 |  | 1186 | 0 | 20 | 40 | 40 | 0 | 0 | 0 | 1 | 0 | 297425.74 | 2946135.78 | 1159792.78 | 4403354.3
100 | GOMPERS | MANHATTAN | GOMPERS | Zone 1 | $ |  |  | 472 | Yes | 2 | 4 | 4 | 1 | 1 | 0 | 1 | 811243.3672 | 29742.574 | 294613.578 | 1159792.78 | 2295392.2992
25 | GOWANUS | BROOKLYN | GOWANUS | 0 | 0 |  |  | 1137 | 0 | 15 | 24 | 24 | 3 | 3 | 0 | 1 | 0 | 178455.444 | 1767681.468 | 2022307.26 | 3968444.172
281 | GRAMPION | MANHATTAN | KING TOWERS | Zone 3 | $ | 2019 | Yes | 35 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
87 | GRANT | MANHATTAN | GRANT | Zone 2 | $$$$ |  |  | 1939 | 0 | 9 | 16 | 16 | 2 | 2 | 0 | 1 | 0 | 118970.296 | 1178454.312 | 1591050.02 | 2888474.628
68 | GRAVESEND | BROOKLYN | O'DWYER GARDENS | 0 | 0 |  |  | 627 | 0 | 15 | 15 | 2 | 0 | 0 | 0 | 1 | 0 | 111534.6525 | 147306.789 | 1159792.78 | 1418634.2215
40 | GUN HILL | BRONX | PARKSIDE | 0 | 0 |  |  | 732 | 0 | 6 | 6 | 6 | 2 | 2 | 0 | 1 | 0 | 44613.861 | 441920.367 | 1591050.02 | 2077584.248
142 | HABER | BROOKLYN | CAREY GARDENS | 0 | 0 |  |  | 380 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 220960.1835 | 1159792.78 | 1380752.9635
75 | HAMMEL | QUEENS | HAMMEL | 0 | 0 |  |  | 710 | 0 | 14 | 14 | 14 | 2 | 2 | 0 | 1 | 0 | 104099.009 | 1031147.523 | 1591050.02 | 2726296.552
262 | HARBORVIEW TERRACE | MANHATTAN | AMSTERDAM | 0 | 0 |  |  | 377 | 0 | 2 | 2 | 2 | 1 | 1 | 0 | 1 | 0 | 14871.287 | 147306.789 | 1159792.78 | 1321970.856
3 | HARLEM RIVER | MANHATTAN | HARLEM RIVER | Zone 3 | $ | 2020 | Yes | 574 | 0 | 7 | 43 | 43 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
147 | HARLEM RIVER II | MANHATTAN | HARLEM RIVER | Zone 3 | $$ | 2020 | Yes | 116 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
347 | HARRISON AVENUE REHAB (GROUP A) | BRONX | KRAUS MANAGEMENT (PRIVATE - BX 3) | 0 | 0 |  |  | 34 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 7435.6435 | 73653.3945 | 1159792.78 | 1240881.818
547 | HARRISON AVENUE REHAB (GROUP B) | BRONX | KRAUS MANAGEMENT (PRIVATE - BX 3) | 0 | 0 |  |  | 150 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 1 | 0 | 29742.574 | 294613.578 | 1159792.78 | 1484148.932
184 | HERNANDEZ | MANHATTAN | GOMPERS | Zone 1 | $$ |  |  | 149 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 256091.6562 | 7435.6435 | 73653.3945 | 1159792.78 | 1496973.4742
78 | HIGHBRIDGE GARDENS | BRONX | HIGHBRIDGE GARDENS | Zone 1 | $ |  |  | 700 | 0 | 6 | 6 | 6 | 2 | 2 | 0 | 1 | 0 | 44613.861 | 441920.367 | 1591050.02 | 2077584.248
215 | HOE AVENUE-EAST 173RD STREET | BRONX | BUILDING MANAGEMENT ASSOCIATES (PRIVATE - BX 1) | 0 | 0 |  |  | 65 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 7435.6435 | 73653.3945 | 1159792.78 | 1240881.818
159 | HOLMES TOWERS | MANHATTAN | ISAACS | 0 | 0 |  |  | 536 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 14871.287 | 147306.789 | 1159792.78 | 1321970.856
72 | HOWARD | BROOKLYN | HOWARD | 0 | 0 |  |  | 813 | 0 | 10 | 16 | 16 | 0 | 0 | 0 | 1 | 0 | 118970.296 | 1178454.312 | 1159792.78 | 2457217.388
339 | HOWARD AVENUE | BROOKLYN | PARK ROCK CONSOLIDATED | 0 | 0 | 2025 |  | 148 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
365 | HOWARD AVENUE-PARK PLACE | BROOKLYN | PARK ROCK CONSOLIDATED | Zone 4 | 0 | 2025 |  | 155 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
168 | HUGHES APARTMENTS | BROOKLYN | HUGHES APARTMENTS | 0 | 0 |  |  | 509 | 0 | 3 | 3 | 3 | 1 | 1 | 0 | 1 | 0 | 22306.9305 | 220960.1835 | 1159792.78 | 1403059.894
367 | HUNTS POINT AVENUE REHAB | BRONX | BUILDING MANAGEMENT ASSOCIATES (PRIVATE - BX 1) | 0 | 0 |  |  | 131 | 0 | 13 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 7435.6435 | 73653.3945 | 1159792.78 | 1240881.818
109 | HYLAN | BROOKLYN | BUSHWICK | Zone 1 | $ |  |  | 209 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 359215.813 | 7435.6435 | 73653.3945 | 1159792.78 | 1600097.631
140 | INDEPENDENCE | BROOKLYN | TAYLOR STREET-WYTHE AVENUE | 0 | 0 | 2019 | Yes | 741 | Yes | 6 | 6 | 6 | 2 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0
14 | INGERSOLL | BROOKLYN | INGERSOLL | 0 | 0 |  |  | 1830 | Yes | 20 | 44 | 44 | 2 | 2 | 0 | 1 | 3145286.7837 | 327168.314 | 3240749.358 | 1591050.02 | 8304254.4757
316 | INTERNATIONAL TOWER | QUEENS | BAISLEY PARK | 0 | 0 |  |  | 146 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 147306.789 | 1159792.78 | 1307099.569
139 | ISAACS | MANHATTAN | ISAACS | 0 | 0 |  |  | 634 | 0 | 3 | 6 | 6 | 0 | 0 | 0 | 1 | 0 | 44613.861 | 441920.367 | 1159792.78 | 1646327.008
120 | JACKSON | BRONX | MORRISANIA AIR RIGHTS | Zone 1 | $ |  |  | 868 | 0 | 7 | 7 | 7 | 2 | 2 | 0 | 1 | 0 | 0 | 515573.7615 | 1591050.02 | 2106623.7815
64 | JEFFERSON | MANHATTAN | JEFFERSON | Zone 2 | $$ | 2026 |  | 1486 | 0 | 18 | 34 | 34 | 4 | 4 | 0 | 1 | 0 | 252811.879 | 2504215.413 | 2453564.5 | 5210591.792
17 | JOHNSON | MANHATTAN | JOHNSON | Zone 2 | $$$ | 2028 |  | 1296 | 0 | 10 | 17 | 17 | 2 | 0 | 0 | 1 | 0 | 126405.9395 | 1252107.7065 | 1159792.78 | 2538306.426
30 | KING TOWERS | MANHATTAN | KING TOWERS | Zone 2 | $$$ |  |  | 1377 | 0 | 10 | 10 | 10 | 2 | 0 | 0 | 1 | 0 | 74356.435 | 736533.945 | 1159792.78 | 1970683.16
10 | KINGSBOROUGH | BROOKLYN | KINGSBOROUGH | Zone 3 | $ |  |  | 1154 | Yes | 16 | 35 | 35 | 0 | 0 | 0 | 1 | 1983421.2833 | 260247.5225 | 2577868.8075 | 1159792.78 | 5981330.3933
161 | KINGSBOROUGH EXTENSION | BROOKLYN | KINGSBOROUGH | Zone 4 | 0 |  |  | 182 | Yes | 1 | 2 | 2 | 0 | 0 | 0 | 1 | 312809.9424 | 0 | 147306.789 | 2022307.26 | 2482423.9914
76 | LA GUARDIA | MANHATTAN | LA GUARDIA | Zone 1 | $$ |  |  | 1091 | Yes | 9 | 9 | 9 | 2 | 2 | 0 | 1 | 1875140.9186 | 0 | 662880.5505 | 1591050.02 | 4129071.4891
152 | LA GUARDIA ADDITION | MANHATTAN | LA GUARDIA | Zone 1 | $ |  |  | 149 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 256091.6562 | 0 | 73653.3945 | 1159792.78 | 1489537.8307
122 | LAFAYETTE | BROOKLYN | LAFAYETTE | Zone 1 | $$$ |  |  | 882 | Yes | 7 | 7 | 7 | 2 | 2 | 0 | 1 | 1515925.1056 | 0 | 515573.7615 | 1591050.02 | 3622548.8871
186 | LATIMER GARDENS | QUEENS | LATIMER GARDENS | 0 | 0 |  |  | 423 | 0 | 4 | 4 | 4 | 1 | 1 | 0 | 1 | 0 | 29742.574 | 294613.578 | 1159792.78 | 1484148.932
201 | LEAVITT STREET-34TH AVENUE | QUEENS | LATIMER GARDENS | 0 | 0 |  |  | 83 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 7435.6435 | 73653.3945 | 1159792.78 | 1240881.818
101 | LEHMAN VILLAGE | MANHATTAN | LEHMAN VILLAGE | 0 | 0 |  |  | 617 | 0 | 4 | 4 | 4 | 2 | 2 | 0 | 1 | 0 | 29742.574 | 294613.578 | 1591050.02 | 1915406.172
348 | LENOX ROAD-ROCKAWAY PARKWAY | BROOKLYN | REID APARTMENTS | 0 | 0 | 2021 | Yes | 74 | 0 | 3 | 5 | 5 | 0 | 0 | 0 | 1 | 0 | 37178.2175 | 0 | 0 | 37178.2175
50 | LEXINGTON | MANHATTAN | WASHINGTON | Zone 2 | $ | 2023 | Yes | 448 | 0 | 4 | 4 | 4 | 1 | 1 | 0 | 1 | 0 | 29742.574 | 0 | 0 | 29742.574
20 | LINCOLN | MANHATTAN | LINCOLN | Zone 2 | $$$$ |  |  | 1280 | 0 | 14 | 20 | 20 | 2 | 2 | 0 | 1 | 0 | 148712.87 | 1473067.89 | 1591050.02 | 3212830.78
95 | LINDEN | BROOKLYN | LINDEN | 0 | 0 | 2020 | Yes | 1586 | 0 | 19 | 19 | 19 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
276 | LONG ISLAND BAPTIST HOUSES | BROOKLYN | UNITY PLAZA | 0 | 0 | 2026 |  | 229 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 1 | 0 | 29742.574 | 294613.578 | 1159792.78 | 1484148.932
362 | LONGFELLOW AVENUE REHAB | BRONX | BUILDING MANAGEMENT ASSOCIATES (PRIVATE - BX 1) | 0 | 0 |  |  | 75 | 0 | 2 | 5 | 5 | 0 | 0 | 0 | 1 | 0 | 37178.2175 | 368266.9725 | 1159792.78 | 1565237.97
169 | LOW HOUSES | BROOKLYN | LOW HOUSES | 0 | 0 |  |  | 534 | 0 | 4 | 3 | 3 | 0 | 0 | 0 | 1 | 0 | 22306.9305 | 220960.1835 | 1159792.78 | 1403059.894
326 | LOWER EAST SIDE I INFILL | MANHATTAN | GOMPERS | Zone 1 | $$ |  |  | 189 | Yes | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 324841.0941 | 0 | 0 | 1159792.78 | 1484633.8741
337 | LOWER EAST SIDE II | MANHATTAN | LOWER EAST SIDE CONSOLIDATED | Zone 1 | $ | 2026 |  | 188 | Yes | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 323122.3581 | 0 | 0 | 1159792.78 | 1482915.1381
364 | LOWER EAST SIDE III | MANHATTAN | KRAUS MANAGEMENT (PRIVATE - M/B1) | Zone 1 | $ |  |  | 56 | Yes | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 96249.2131 | 0 | 0 | 1159792.78 | 1256041.9931
292 | LOWER EAST SIDE REHAB (GROUP 5) | MANHATTAN | LOWER EAST SIDE CONSOLIDATED | Zone 1 | $$ | 2026 |  | 55 | Yes | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 94530.4771 | 14871.287 | 147306.789 | 1159792.78 | 1416501.3331
81 | MANHATTANVILLE | MANHATTAN | MANHATTANVILLE | Zone 2 | $ | 2028 |  | 1272 | 0 | 6 | 6 | 6 | 3 | 3 | 0 | 1 | 0 | 44613.861 | 441920.367 | 2022307.26 | 2508841.488
296 | MANHATTANVILLE REHAB (GROUP 2) | MANHATTAN | MANHATTANVILLE | Zone 3 | $ | 2019 | Yes | 46 | 0 | 3 | 3 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
297 | MANHATTANVILLE REHAB (GROUP 3) | MANHATTAN | MANHATTANVILLE | Zone 3 | $ | 2019 | Yes | 51 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
49 | MARBLE HILL | BRONX | MARBLE HILL | 0 | 0 |  |  | 1680 | 0 | 11 | 11 | 11 | 3 | 3 | 0 | 1 | 0 | 81792.0785 | 810187.3395 | 2022307.26 | 2914286.678
21 | MARCY | BROOKLYN | MARCY | Zone 1 | $$ | 2027 |  | 1716 | Yes | 27 | 69 | 69 | 3 | 3 | 0 | 1 | 2949350.8857 | 0 | 5082084.2205 | 2022307.26 | 10053742.3662
363 | MARCY AVENUE-GREENE AVENUE SITE A | BROOKLYN | KRAUS MANAGEMENT (PRIVATE - M/B 1) | Zone 1 | $ | 2019 | Yes | 48 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
358 | MARCY AVENUE-GREENE AVENUE SITE B | BROOKLYN | KRAUS MANAGEMENT (PRIVATE - M/B 1) | 0 | 0 | 2019 | Yes | 30 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
77 | MARINER'S HARBOR | STATEN ISLAND | MARINER'S HARBOR | 0 | 0 | 2028 |  | 606 | 0 | 22 | 27 | 27 | 2 | 0 | 0 | 1 | 0 | 200762.3745 | 1988641.6515 | 1159792.78 | 3349196.806
83 | MARLBORO | BROOKLYN | MARLBORO | 0 | 0 |  |  | 1764 | 0 | 28 | 28 | 28 | 0 | 0 | 0 | 1 | 0 | 208198.018 | 2062295.046 | 1159792.78 | 3430285.844
344 | MARSHALL PLAZA | MANHATTAN | HARLEM RIVER | Zone 3 | $$ | 2020 | Yes | 180 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
103 | MCKINLEY | BRONX | FOREST | Zone 4 | 0 |  |  | 615 | 0 | 5 | 5 | 5 | 2 | 2 | 0 | 1 | 0 | 37178.2175 | 368266.9725 | 1591050.02 | 1996495.21
28 | MELROSE | BRONX | MELROSE | Zone 1 | $ | 2023 | Yes | 1021 | 0 | 8 | 8 | 8 | 2 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0
183 | MELTZER TOWER | MANHATTAN | GOMPERS | Zone 1 | $ |  |  | 229 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 73653.3945 | 1159792.78 | 1233446.1745
181 | METRO NORTH PLAZA | MANHATTAN | WILSON | Zone 2 | $ |  |  | 271 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 1 | 0 | 22306.9305 | 220960.1835 | 1159792.78 | 1403059.894
191 | MIDDLETOWN PLAZA | BRONX | EASTCHESTER GARDENS | 0 | 0 | 2026 |  | 177 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 73653.3945 | 1159792.78 | 1233446.1745
84 | MILL BROOK | BRONX | MILL BROOK | 0 | 0 |  |  | 1251 | 0 | 9 | 9 | 9 | 3 | 3 | 0 | 1 | 0 | 66920.7915 | 662880.5505 | 2022307.26 | 2752108.602
132 | MILL BROOK EXTENSION | BRONX | MILL BROOK | 0 | 0 |  |  | 125 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 7435.6435 | 73653.3945 | 1159792.78 | 1240881.818
145 | MITCHEL | BRONX | MITCHEL | 0 | 0 |  |  | 1732 | 0 | 10 | 20 | 20 | 4 | 4 | 0 | 1 | 0 | 148712.87 | 1473067.89 | 2453564.5 | 4075345.26
88 | MONROE | BRONX | MONROE | Zone 3 | $ |  |  | 1100 | 0 | 12 | 18 | 18 | 2 | 2 | 0 | 1 | 0 | 133841.583 | 1325761.101 | 1591050.02 | 3050652.704
129 | MOORE | BRONX | SAINT MARY'S PARK | Zone 3 | $$ |  |  | 463 | 0 | 2 | 4 | 4 | 1 | 1 | 0 | 1 | 0 | 29742.574 | 294613.578 | 1159792.78 | 1484148.932
102 | MORRIS I | BRONX | MORRIS | Zone 1 | $$ |  |  | 1083 | 0 | 10 | 10 | 10 | 3 | 3 | 0 | 1 | 0 | 0 | 736533.945 | 2022307.26 | 2758841.205
502 | MORRIS II | BRONX | MORRIS | Zone 1 | $$$ |  |  | 802 | 0 | 7 | 7 | 7 | 2 | 2 | 0 | 1 | 0 | 52049.5045 | 515573.7615 | 1591050.02 | 2158673.286
277 | MORRIS PARK SENIOR CITIZENS HOME | MANHATTAN | ROBINSON | Zone 2 | $$$$ |  |  | 97 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 7435.6435 | 73653.3945 | 1159792.78 | 1240881.818
130 | MORRISANIA | BRONX | WEBSTER | Zone 1 | $$$$ |  |  | 206 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 354059.6052 | 14871.287 | 147306.789 | 1159792.78 | 1676030.4612
267 | MORRISANIA AIR RIGHTS | BRONX | MORRISANIA AIR RIGHTS | Zone 1 | $ |  |  | 841 | 0 | 3 | 5 | 5 | 0 | 0 | 0 | 1 | 0 | 0 | 368266.9725 | 1159792.78 | 1528059.7525
121 | MOTT HAVEN | BRONX | MOTT HAVEN | 0 | 0 |  |  | 992 | 0 | 8 | 8 | 8 | 2 | 2 | 0 | 1 | 0 | 59485.148 | 589227.156 | 1591050.02 | 2239762.324
314 | NEW LANE AREA | STATEN ISLAND | SOUTH BEACH | 0 | 0 |  |  | 276 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 147306.789 | 1159792.78 | 1307099.569
43 | NOSTRAND | BROOKLYN | SHEEPSHEAD BAY | 0 | 0 | 2028 |  | 1146 | 0 | 16 | 32 | 32 | 0 | 0 | 0 | 1 | 0 | 237940.592 | 2356908.624 | 1159792.78 | 3754641.996
51 | OCEAN BAY APARTMENTS (OCEANSIDE) | QUEENS | BEACH 41ST STREET-BEACH CHANNEL DRIVE | 0 | 0 |  |  | 417 | 0 | 7 | 13 | 13 | 0 | 0 | 0 | 1 | 0 | 96663.3655 | 957494.1285 | 1159792.78 | 2213950.274
162 | OCEAN HILL APARTMENTS | BROOKLYN | OCEAN HILL APARTMENTS | 0 | 0 |  |  | 238 | Yes | 3 | 3 | 3 | 0 | 0 | 0 | 1 | 409059.1555 | 22306.9305 | 220960.1835 | 1159792.78 | 1812119.0495
313 | OCEAN HILL-BROWNSVILLE | BROOKLYN | PARK ROCK CONSOLIDATED | 0 | 0 | 2025 |  | 125 | Yes | 5 | 6 | 6 | 0 | 0 | 0 | 1 | 214841.9934 | 44613.861 | 0 | 0 | 259455.8544
172 | O'DWYER GARDENS | BROOKLYN | O'DWYER GARDENS | 0 | 0 |  |  | 570 | 0 | 6 | 6 | 6 | 0 | 0 | 0 | 1 | 0 | 44613.861 | 441920.367 | 1159792.78 | 1646327.008
204 | PARK AVENUE-EAST 122ND, 123RD STREETS | MANHATTAN | ROBINSON | Zone 3 | $$ | 2019 | Yes | 90 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
351 | PARK ROCK REHAB | BROOKLYN | PARK ROCK CONSOLIDATED | 0 | 0 | 2025 |  | 134 | Yes | 9 | 6 | 6 | 0 | 0 | 0 | 1 | 230310.617 | 44613.861 | 0 | 0 | 274924.478
47 | PARKSIDE | BRONX | PARKSIDE | 0 | 0 |  |  | 879 | 0 | 14 | 21 | 21 | 2 | 2 | 0 | 1 | 0 | 156148.5135 | 1546721.2845 | 1591050.02 | 3293919.818
24 | PATTERSON | BRONX | PATTERSON | Zone 3 | $$ | 2025 |  | 1789 | 0 | 15 | 25 | 0 | 4 | 0 | 0 | 1 | 0 | 185891.0875 | 0 | 0 | 185891.0875
39 | PELHAM PARKWAY | BRONX | PELHAM PARKWAY | 0 | 0 | 2022 | Yes | 1265 | 0 | 23 | 38 | 38 | 3 | 3 | 0 | 1 | 0 | 282554.453 | 0 | 0 | 282554.453
194 | PENNSYLVANIA AVENUE-WORTMAN AVENUE | BROOKLYN | PENNSYLVANIA-WORTMAN | 0 | 0 |  |  | 336 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 1 | 0 | 22306.9305 | 220960.1835 | 1159792.78 | 1403059.894
89 | PINK | BROOKLYN | PINK | 0 | 0 |  |  | 1500 | 0 | 22 | 22 | 22 | 0 | 0 | 0 | 1 | 0 | 163584.157 | 1620374.679 | 1159792.78 | 2943751.616
149 | POLO GROUNDS TOWERS | MANHATTAN | POLO GROUNDS TOWERS | Zone 2 | $ |  |  | 1614 | 0 | 4 | 9 | 9 | 3 | 3 | 0 | 1 | 0 | 66920.7915 | 662880.5505 | 2022307.26 | 2752108.602
53 | POMONOK | QUEENS | POMONOK | 0 | 0 | 2027 |  | 2069 | 0 | 35 | 121 | 121 | 5 | 5 | 0 | 1 | 0 | 899712.8635 | 8912060.7345 | 2884821.74 | 12696595.338
340 | PUBLIC SCHOOL 139 (CONVERSION) | MANHATTAN | DREW-HAMILTON | Zone 3 | $ | 2019 | Yes | 125 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
505 | QUEENSBRIDGE NORTH | QUEENS | QUEENSBRIDGE NORTH | Zone 3 | $ |  |  | 1542 | 0 | 13 | 47 | 47 | 0 | 0 | 0 | 1 | 0 | 349475.2445 | 3461709.5415 | 1159792.78 | 4970977.566
5 | QUEENSBRIDGE SOUTH | QUEENS | QUEENSBRIDGE SOUTH | Zone 3 | $ |  |  | 1603 | 0 | 13 | 49 | 49 | 12 | 6 | 0 | 1 | 0 | 364346.5315 | 3609016.3305 | 3316078.98 | 7289441.842
352 | RALPH AVENUE REHAB | BROOKLYN | REID APARTMENTS | 0 | 0 | 2021 | Yes | 118 | 0 | 5 | 9 | 9 | 0 | 0 | 0 | 1 | 0 | 66920.7915 | 0 | 0 | 66920.7915
245 | RANDALL AVENUE-BALCOM AVENUE | BRONX | THROGGS NECK | 0 | 0 | 2022 | Yes | 251 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
37 | RANGEL | MANHATTAN | RANGEL | Zone 2 | $ |  |  | 982 | 0 | 8 | 10 | 10 | 3 | 3 | 0 | 1 | 0 | 74356.435 | 736533.945 | 2022307.26 | 2833197.64
48 | RAVENSWOOD | QUEENS | RAVENSWOOD | 0 | 0 |  |  | 2164 | 0 | 31 | 39 | 39 | 0 | 0 | 0 | 1 | 0 | 289990.0965 | 2872482.3855 | 1159792.78 | 4322265.262
4 | RED HOOK EAST | BROOKLYN | RED HOOK EAST | 0 | 0 | 2024 | Yes | 1404 | 0 | 16 | 47 | 47 | 0 | 0 | 0 | 1 | 0 | 349475.2445 | 0 | 0 | 349475.2445
79 | RED HOOK WEST | BROOKLYN | RED HOOK WEST | 0 | 0 | 2025 |  | 1471 | 0 | 14 | 43 | 43 | 2 | 2 | 0 | 1 | 0 | 319732.6705 | 0 | 0 | 319732.6705
55 | REDFERN | QUEENS | REDFERN | 0 | 0 | 2022 | Yes | 599 | 0 | 9 | 16 | 16 | 0 | 0 | 0 | 1 | 0 | 118970.296 | 0 | 0 | 118970.296
143 | REHAB PROGRAM (COLLEGE POINT) | QUEENS | LATIMER GARDENS | 0 | 0 |  |  | 13 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1159792.78 | 1159792.78
515 | REHAB PROGRAM (DOUGLASS REHABS) | MANHATTAN | KRAUS MANAGEMENT (PRIVATE - M/B 1) | 0 | 0 |  |  | 112 | 0 | 4 | 3 | 3 | 0 | 0 | 0 | 1 | 0 | 22306.9305 | 220960.1835 | 1159792.78 | 1403059.894
516 | REHAB PROGRAM (TAFT REHABS) | MANHATTAN | KRAUS MANAGEMENT (PRIVATE - M/B 1) | 0 | 0 |  |  | 156 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 1 | 0 | 29742.574 | 294613.578 | 1159792.78 | 1484148.932
517 | REHAB PROGRAM (WISE REHAB) | MANHATTAN | WISE TOWERS | Zone 4 | 0 |  |  | 40 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 7435.6435 | 73653.3945 | 0 | 81089.038
167 | REID APARTMENTS | BROOKLYN | REID APARTMENTS | 0 | 0 | 2021 | Yes | 227 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
117 | RICHMOND TERRACE | STATEN ISLAND | RICHMOND TERRACE | 0 | 0 |  |  | 488 | 0 | 6 | 6 | 6 | 2 | 0 | 0 | 1 | 0 | 44613.861 | 441920.367 | 1159792.78 | 1646327.008
18 | RIIS | MANHATTAN | RIIS | Zone 1 | $ |  |  | 1191 | Yes | 13 | 15 | 15 | 2 | 2 | 0 | 1 | 2047014.5133 | 111534.6525 | 1104800.9175 | 1591050.02 | 4854400.1033
19 | RIIS II | MANHATTAN | RIIS | Zone 1 | $$ |  |  | 577 | Yes | 6 | 7 | 7 | 1 | 1 | 0 | 1 | 991710.6416 | 52049.5045 | 515573.7615 | 1159792.78 | 2719126.6876
218 | ROBBINS PLAZA | MANHATTAN | ISAACS | 0 | 0 |  |  | 150 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 73653.3945 | 1159792.78 | 1233446.1745
241 | ROBINSON | MANHATTAN | ROBINSON | Zone 2 | $$ |  |  | 188 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 14871.287 | 147306.789 | 1159792.78 | 1321970.856
135 | ROOSEVELT I | BROOKLYN | ROOSEVELT | Zone 1 | $ |  |  | 761 | Yes | 6 | 6 | 6 | 0 | 0 | 0 | 1 | 1307958.056 | 0 | 441920.367 | 1159792.78 | 2909671.203
177 | ROOSEVELT II | BROOKLYN | ROOSEVELT | Zone 1 | $ |  |  | 342 | Yes | 3 | 3 | 3 | 0 | 0 | 0 | 1 | 587807.694 | 22306.9305 | 220960.1835 | 1159792.78 | 1990867.588
99 | RUTGERS | MANHATTAN | RUTGERS | Zone 1 | $ |  |  | 721 | Yes | 5 | 5 | 5 | 1 | 1 | 0 | 1 | 1239208.6181 | 0 | 368266.9725 | 1159792.78 | 2767268.3706
282 | RUTLAND TOWERS | BROOKLYN | REID APARTMENTS | 0 | 0 | 2021 | Yes | 60 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 7435.6435 | 0 | 0 | 7435.6435
280 | SACK WERN | BRONX | SACK WERN | 0 | 0 | 2024 | Yes | 411 | 0 | 7 | 7 | 7 | 0 | 0 | 0 | 1 | 0 | 52049.5045 | 0 | 0 | 52049.5045
93 | SAINT MARY'S PARK | BRONX | SAINT MARY'S PARK | Zone 3 | $ |  |  | 1005 | 0 | 6 | 6 | 6 | 2 | 2 | 0 | 1 | 0 | 44613.861 | 441920.367 | 1591050.02 | 2077584.248
38 | SAINT NICHOLAS | MANHATTAN | SAINT NICHOLAS | Zone 2 | $ |  |  | 1525 | 0 | 13 | 14 | 14 | 3 | 3 | 0 | 1 | 0 | 104099.009 | 1031147.523 | 2022307.26 | 3157553.792
377 | SAMUEL (CITY) | MANHATTAN | SAMUEL | Zone 2 | $$ | 2026 |  | 664 | 0 | 40 | 40 | 40 | 0 | 0 | 0 | 1 | 0 | 297425.74 | 2946135.78 | 1159792.78 | 4403354.3
389 | SAMUEL (MHOP) I | MANHATTAN | KRAUS MANAGEMENT (PRIVATE - M/B 1) | 0 | 0 | 2019 | Yes | 24 | 0 | 5 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
398 | SAMUEL (MHOP) II | MANHATTAN | KRAUS MANAGEMENT (PRIVATE - M/B 1) | 0 | 0 | 2019 | Yes | 4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
399 | SAMUEL (MHOP) III | MANHATTAN | KRAUS MANAGEMENT (PRIVATE - M/B 1) | 0 | 0 | 2019 | Yes | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
158 | SARATOGA VILLAGE | BROOKLYN | OCEAN HILL APARTMENTS | 0 | 0 |  |  | 125 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 214841.9934 | 7435.6435 | 73653.3945 | 1159792.78 | 1455723.8114
45 | SEDGWICK | BRONX | SEDGWICK | 0 | 0 |  |  | 783 | 0 | 7 | 7 | 7 | 2 | 2 | 0 | 1 | 0 | 52049.5045 | 515573.7615 | 1591050.02 | 2158673.286
192 | SEWARD PARK EXTENSION | MANHATTAN | GOMPERS | Zone 1 | $ |  |  | 360 | Yes | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 618744.9411 | 14871.287 | 147306.789 | 1159792.78 | 1940715.7971
36 | SHEEPSHEAD BAY | BROOKLYN | SHEEPSHEAD BAY | 0 | 0 | 2028 |  | 1054 | 0 | 18 | 35 | 35 | 6 | 6 | 0 | 1 | 0 | 260247.5225 | 2577868.8075 | 3316078.98 | 6154195.31
279 | SHELTON HOUSE | QUEENS | BAISLEY PARK | 0 | 0 |  |  | 153 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 73653.3945 | 1159792.78 | 1233446.1745
27 | SMITH | MANHATTAN | SMITH | Zone 1 | $ |  |  | 1934 | Yes | 12 | 13 | 12 | 4 | 4 | 0 | 1 | 3324035.3223 | 0 | 883840.734 | 2453564.5 | 6661440.5563
67 | SOTOMAYOR HOUSES | BRONX | SOTOMAYOR HOUSES | 0 | 0 |  |  | 1495 | 0 | 28 | 28 | 0 | 3 | 3 | 0 | 1 | 0 | 208198.018 | 0 | 2022307.26 | 2230505.278
71 | SOUNDVIEW | BRONX | SOUNDVIEW | 0 | 0 | 2023 | Yes | 1258 | 0 | 13 | 22 | 22 | 4 | 4 | 0 | 1 | 0 | 163584.157 | 0 | 0 | 163584.157
35 | SOUTH BEACH | STATEN ISLAND | SOUTH BEACH | 0 | 0 |  |  | 421 | 0 | 8 | 15 | 15 | 1 | 1 | 0 | 1 | 0 | 111534.6525 | 1104800.9175 | 1159792.78 | 2376128.35
305 | SOUTH BRONX AREA (SITE 402) | BRONX | UNION AVENUE CONSOLIDATED | Zone 3 | $$ | 2026 |  | 112 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1159792.78 | 1159792.78
8 | SOUTH JAMAICA I | QUEENS | SOUTH JAMAICA I | 0 | 0 | 2021 | Yes | 448 | 0 | 11 | 33 | 33 | 0 | 0 | 0 | 1 | 0 | 245376.2355 | 0 | 0 | 245376.2355
66 | SOUTH JAMAICA II | QUEENS | SOUTH JAMAICA I | 0 | 0 | 2021 | Yes | 598 | 0 | 16 | 27 | 27 | 4 | 4 | 0 | 1 | 0 | 200762.3745 | 0 | 0 | 200762.3745
559 | STANTON STREET | MANHATTAN | KRAUS MANAGEMENT (PRIVATE - M/B 1) | 0 | 0 |  |  | 13 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 22343.5673 | 7435.6435 | 73653.3945 | 1159792.78 | 1263225.3853
114 | STAPLETON | STATEN ISLAND | STAPLETON | 0 | 0 |  |  | 693 | 0 | 6 | 12 | 12 | 2 | 2 | 0 | 1 | 0 | 89227.722 | 883840.734 | 1591050.02 | 2564118.476
353 | STEBBINS AVENUE-HEWITT PLACE | BRONX | UNION AVENUE CONSOLIDATED | Zone 3 | $$$ | 2026 |  | 119 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1159792.78 | 1159792.78
366 | STERLING PLACE REHABS (SAINT JOHNS-STERLING) | BROOKLYN | PARK ROCK CONSOLIDATED | 0 | 0 | 2025 |  | 83 | Yes | 5 | 5 | 5 | 0 | 0 | 0 | 1 | 142655.0836 | 37178.2175 | 0 | 0 | 179833.3011
368 | STERLING PLACE REHABS (STERLING-BUFFALO) | BROOKLYN | PARK ROCK CONSOLIDATED | 0 | 0 | 2025 |  | 125 | Yes | 7 | 7 | 7 | 0 | 0 | 0 | 1 | 214841.9934 | 52049.5045 | 0 | 0 | 266891.4979
153 | STRAUS | MANHATTAN | STRAUS | 0 | 0 |  |  | 267 | Yes | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 458902.498 | 14871.287 | 147306.789 | 1159792.78 | 1780873.354
221 | STUYVESANT GARDENS I | BROOKLYN | STUYVESANT GARDENS I | 0 | 0 |  |  | 329 | Yes | 5 | 11 | 11 | 0 | 0 | 0 | 1 | 565464.1267 | 81792.0785 | 810187.3395 | 1159792.78 | 2617236.3247
333 | STUYVESANT GARDENS II | BROOKLYN | STUYVESANT GARDENS I | 0 | 0 |  |  | 150 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 257810.3921 | 0 | 73653.3945 | 1159792.78 | 1491256.5666
73 | SUMNER | BROOKLYN | SUMNER | Zone 1 | $ |  |  | 1098 | Yes | 13 | 24 | 24 | 2 | 2 | 0 | 1 | 1887172.0702 | 0 | 1767681.468 | 1591050.02 | 5245903.5582
170 | SURFSIDE GARDENS | BROOKLYN | SURFSIDE GARDENS | 0 | 0 |  |  | 594 | 0 | 5 | 5 | 5 | 1 | 1 | 0 | 1 | 0 | 37178.2175 | 368266.9725 | 1159792.78 | 1565237.97
369 | SUTTER AVENUE-UNION STREET | BROOKLYN | REID APARTMENTS | 0 | 0 | 2021 | Yes | 100 | 0 | 3 | 5 | 5 | 0 | 0 | 0 | 1 | 0 | 37178.2175 | 0 | 0 | 37178.2175
97 | TAFT | MANHATTAN | TAFT | Zone 2 | $$$ |  |  | 1463 | 0 | 9 | 11 | 11 | 4 | 4 | 0 | 1 | 0 | 81792.0785 | 810187.3395 | 2453564.5 | 3345543.918
354 | TAPSCOTT STREET REHAB | BROOKLYN | REID APARTMENTS | 0 | 0 | 2021 | Yes | 155 | 0 | 8 | 9 | 9 | 0 | 0 | 0 | 1 | 0 | 66920.7915 | 0 | 0 | 66920.7915
234 | TAYLOR STREET-WYTHE AVENUE | BROOKLYN | TAYLOR STREET-WYTHE AVENUE | 0 | 0 |  |  | 525 | Yes | 5 | 6 | 1 | 0 | 0 | 0 | 1 | 902336.3724 | 44613.861 | 73653.3945 | 1159792.78 | 2180396.4079
223 | TELLER AVENUE-EAST 166TH STREET | BRONX | CLAREMONT CONSOLIDATED | Zone 1 | $ | 2025 |  | 90 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 14871.287 | 0 | 0 | 14871.287
268 | THOMAS APARTMENTS | MANHATTAN | WISE TOWERS | Zone 4 | 0 |  |  | 87 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 7435.6435 | 73653.3945 | 0 | 81089.038
63 | THROGGS NECK | BRONX | THROGGS NECK | 0 | 0 | 2022 | Yes | 1182 | 0 | 29 | 60 | 60 | 6 | 6 | 0 | 1 | 0 | 446138.61 | 0 | 0 | 446138.61
193 | THROGGS NECK ADDITION | BRONX | THROGGS NECK | 0 | 0 | 2022 | Yes | 287 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 1 | 0 | 29742.574 | 0 | 0 | 29742.574
96 | TILDEN | BROOKLYN | TILDEN | 0 | 0 |  |  | 998 | 0 | 8 | 8 | 8 | 2 | 2 | 0 | 1 | 0 | 59485.148 | 589227.156 | 1591050.02 | 2239762.324
42 | TODT HILL | STATEN ISLAND | BERRY | 0 | 0 |  |  | 502 | 0 | 7 | 13 | 13 | 0 | 0 | 0 | 1 | 0 | 96663.3655 | 957494.1285 | 1159792.78 | 2213950.274
131 | TOMPKINS | BROOKLYN | TOMPKINS | Zone 1 | $ |  |  | 1045 | Yes | 8 | 12 | 11 | 0 | 0 | 0 | 1 | 1796079.065 | 0 | 810187.3395 | 1159792.78 | 3766059.1845
287 | TWIN PARKS EAST (SITE 9) | BRONX | TWIN PARKS CONSOLIDATED | Zone 1 | $ |  |  | 219 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 73653.3945 | 1159792.78 | 1233446.1745
266 | TWO BRIDGES URA (SITE 7) | MANHATTAN | LA GUARDIA | Zone 1 | $ |  |  | 250 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 7435.6435 | 73653.3945 | 1159792.78 | 1240881.818
342 | UNION AVENUE-EAST 163RD STREET | BRONX | UNION AVENUE CONSOLIDATED | Zone 3 | $ | 2026 |  | 199 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 73653.3945 | 1159792.78 | 1233446.1745
356 | UNION AVENUE-EAST 166TH STREET | BRONX | UNION AVENUE CONSOLIDATED | Zone 3 | $ | 2026 |  | 120 | 0 | 6 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 1159792.78 | 1159792.78
240 | UNITY PLAZA (SITES 17,24,25A) | BROOKLYN | UNITY PLAZA | 0 | 0 | 2026 |  | 167 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 1 | 0 | 22306.9305 | 220960.1835 | 1159792.78 | 1403059.894
261 | UNITY PLAZA (SITES 4-27) | BROOKLYN | UNITY PLAZA | 0 | 0 | 2026 |  | 460 | 0 | 5 | 12 | 12 | 0 | 0 | 0 | 1 | 0 | 89227.722 | 883840.734 | 1159792.78 | 2132861.236
341 | UNIVERSITY AVENUE REHAB | BRONX | KRAUS MANAGEMENT (PRIVATE - BX 3) | 0 | 0 |  |  | 230 | 0 | 4 | 5 | 5 | 0 | 0 | 0 | 1 | 0 | 37178.2175 | 368266.9725 | 1159792.78 | 1565237.97
343 | UPACA (SITE 5) | MANHATTAN | ROBINSON | Zone 2 | $ |  |  | 179 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 73653.3945 | 1159792.78 | 1233446.1745
355 | UPACA (SITE 6) | MANHATTAN | ROBINSON | Zone 2 | $ |  |  | 150 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 7435.6435 | 73653.3945 | 1159792.78 | 1240881.818
61 | VAN DYKE I | BROOKLYN | VAN DYKE I | 0 | 0 | 2024 | Yes | 1603 | 0 | 22 | 31 | 31 | 0 | 0 | 0 | 1 | 0 | 230504.9485 | 0 | 0 | 230504.9485
146 | VAN DYKE II | BROOKLYN | WOODSON | 0 | 0 |  |  | 111 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 7435.6435 | 73653.3945 | 1159792.78 | 1240881.818
315 | VANDALIA AVENUE | BROOKLYN | PENNSYLVANIA-WORTMAN | 0 | 0 |  |  | 288 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 147306.789 | 1159792.78 | 1307099.569
6 | VLADECK | MANHATTAN | VLADECK | Zone 1 | $$ |  |  | 1527 | Yes | 20 | 45 | 2 | 0 | 0 | 0 | 1 | 2624509.7917 | 334603.9575 | 147306.789 | 1159792.78 | 4266213.3182
7 | VLADECK II | MANHATTAN | VLADECK | Zone 1 | $ |  |  | 240 | Yes | 4 | 7 | 7 | 0 | 0 | 0 | 1 | 412496.6274 | 52049.5045 | 515573.7615 | 1159792.78 | 2139912.6734
74 | WAGNER | MANHATTAN | WAGNER | Zone 2 | $ |  |  | 2151 | 0 | 22 | 22 | 22 | 4 | 4 | 0 | 1 | 0 | 163584.157 | 1620374.679 | 2453564.5 | 4237523.336
23 | WALD | MANHATTAN | WALD | Zone 1 | $ |  |  | 1861 | Yes | 16 | 17 | 17 | 3 | 3 | 0 | 1 | 3198567.5981 | 126405.9395 | 1252107.7065 | 2022307.26 | 6599388.5041
62 | WASHINGTON | MANHATTAN | WASHINGTON | Zone 2 | $$$ | 2023 | Yes | 1515 | 0 | 14 | 14 | 14 | 1 | 1 | 1 | 0 | 0 | 104099.009 | 0 | 0 | 104099.009
293 | WASHINGTON HEIGHTS REHAB (GROUPS 1&2) | MANHATTAN | FORT WASHINGTON | 0 | 0 | 2019 | Yes | 215 | 0 | 5 | 6 | 6 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
523 | WASHINGTON HEIGHTS REHAB PHASE III (FORT WASHINGTON) | MANHATTAN | #N/A | 0 | 0 |  |  | 88 | 0 | 7 | 3 | 3 | 0 | 0 | 0 | 1 | 0 | 22306.9305 | 220960.1835 | 1159792.78 | 1403059.894
329 | WASHINGTON HEIGHTS REHAB PHASE III (HARLEM RIVER) | MANHATTAN | #N/A | 0 | 0 |  |  | 14 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 7435.6435 | 73653.3945 | 1159792.78 | 1240881.818
330 | WASHINGTON HEIGHTS REHAB PHASE IV (C) | MANHATTAN | FORT WASHINGTON | 0 | 0 | 2019 | Yes | 32 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
331 | WASHINGTON HEIGHTS REHAB PHASE IV (D) | MANHATTAN | FORT WASHINGTON | 0 | 0 | 2019 | Yes | 32 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
141 | WEBSTER | BRONX | WEBSTER | Zone 1 | $ |  |  | 606 | 0 | 5 | 5 | 5 | 2 | 2 | 0 | 1 | 0 | 0 | 368266.9725 | 1591050.02 | 1959316.9925
229 | WEEKSVILLE GARDENS | BROOKLYN | ALBANY | 0 | 0 | 2019 | Yes | 256 | Yes | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
116 | WEST BRIGHTON I | STATEN ISLAND | WEST BRIGHTON I | 0 | 0 |  |  | 487 | 0 | 8 | 8 | 8 | 2 | 2 | 0 | 1 | 0 | 59485.148 | 589227.156 | 1591050.02 | 2239762.324
175 | WEST BRIGHTON II | STATEN ISLAND | WEST BRIGHTON I | 0 | 0 |  |  | 120 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1159792.78 | 1159792.78
360 | WEST FARMS ROAD REHAB | BRONX | BUILDING MANAGEMENT ASSOCIATES (PRIVATE - BX 1) | 0 | 0 |  |  | 208 | 0 | 4 | 7 | 7 | 0 | 0 | 0 | 1 | 0 | 52049.5045 | 515573.7615 | 1159792.78 | 1727416.046
526 | WEST FARMS SQUARE CONVENTIONAL | BRONX | BUILDING MANAGEMENT ASSOCIATES (PRIVATE - BX 1) | 0 | 0 |  |  | 20 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 7435.6435 | 73653.3945 | 1159792.78 | 1240881.818
246 | WEST TREMONT AVENUE-SEDGWICK AVENUE AREA | BRONX | SEDGWICK | Zone 4 | 0 |  |  | 148 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 7435.6435 | 73653.3945 | 0 | 81089.038
124 | WHITE | MANHATTAN | WILSON | Zone 2 | $ |  |  | 246 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 147306.789 | 1159792.78 | 1307099.569
514 | WHITMAN | BROOKLYN | WHITMAN | 0 | 0 |  |  | 1651 | Yes | 15 | 32 | 32 | 3 | 3 | 0 | 1 | 2837633.0491 | 237940.592 | 2356908.624 | 2022307.26 | 7454789.5251
128 | WILLIAMS PLAZA | BROOKLYN | WILLIAMS PLAZA | 0 | 0 | 2019 | Yes | 577 | Yes | 5 | 5 | 5 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
2 | WILLIAMSBURG | BROOKLYN | WILLIAMSBURG | 0 | 0 | 2020 | Yes | 1627 | Yes | 20 | 134 | 134 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
112 | WILSON | MANHATTAN | WILSON | Zone 2 | $ |  |  | 398 | 0 | 3 | 5 | 5 | 2 | 2 | 0 | 1 | 0 | 37178.2175 | 368266.9725 | 1591050.02 | 1996495.21
127 | WISE TOWERS | MANHATTAN | WISE TOWERS | Zone 4 | 0 | 2019 | Yes | 397 | 0 | 2 | 4 | 4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
33 | WOODSIDE | QUEENS | WOODSIDE | 0 | 0 |  |  | 1355 | 0 | 20 | 56 | 56 | 3 | 3 | 0 | 1 | 0 | 416396.036 | 4124590.092 | 2022307.26 | 6563293.388
182 | WOODSON | BROOKLYN | WOODSON | 0 | 0 |  |  | 407 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 147306.789 | 1159792.78 | 1307099.569
178 | WSUR (BROWNSTONES) | MANHATTAN | WISE TOWERS | Zone 4 | 0 |  |  | 236 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
151 | WSUR (SITE A) 120 WEST 94TH STREET | MANHATTAN | WISE TOWERS | Zone 4 | 0 |  |  | 69 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 7435.6435 | 73653.3945 | 0 | 81089.038
173 | WSUR (SITE B) 74 WEST 92ND STREET | MANHATTAN | WISE TOWERS | Zone 4 | 0 |  |  | 168 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 14871.287 | 147306.789 | 1159792.78 | 1321970.856
174 | WSUR (SITE C) 589 AMSTERDAM AVENUE | MANHATTAN | WISE TOWERS | 0 | 0 |  |  | 158 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 14871.287 | 147306.789 | 1159792.78 | 1321970.856
163 | WYCKOFF GARDENS | BROOKLYN | WYCKOFF GARDENS | 0 | 0 |  |  | 528 | 0 | 3 | 6 | 6 | 0 | 0 | 0 | 1 | 0 | 44613.861 | 441920.367 | 1159792.78 | 1646327.008

## FWD
[11 empty] | 1703503.75 | 60513255.2359 | 62216758.9859
DEVELOPMENT | BOROUGH | WORK TYPE | Dwelling Units | NRR | Priority Level | RAD/PACT | Is RAD/PACT w/in 5yr | CALENDAR YEAR | FISCAL YEAR | STATUS | COST | ESTIMATE | Running Cost/Yr
BARUCH HOUSES ADDITION | MANHATTAN | Food Waste Disposer | 197 | Zone 1 | $ |  |  | 2019 | 2020 | IN PROGRESS | 607266.52 |  | 607266.52
MELTZER TOWER | MANHATTAN | Food Waste Disposer | 229 | Zone 1 | $ |  |  | 2019 | 2020 | IN PROGRESS | 534717.81 |  | 1141984.33
TWO BRIDGES URA (SITE 7) | MANHATTAN | Food Waste Disposer | 250 | Zone 1 | $ |  |  | 2019 | 2020 | IN PROGRESS | 561519.42 |  | 1703503.75
MORRISANIA | BRONX | Food Waste Disposer | 206 | Zone 1 | $$$$ | [6 empty] | 354059.6052 | 354059.6052
303 VERNON AVENUE | BROOKLYN | Food Waste Disposer | 234 | Zone 1 | $ | [6 empty] | 402184.2117 | 756243.8169
344 EAST 28TH STREET | MANHATTAN | Food Waste Disposer | 225 | 0 | 0 | [6 empty] | 386715.5882 | 1142959.405
45 ALLEN STREET | MANHATTAN | Food Waste Disposer | 107 | Zone 1 | $$ | [6 empty] | 183904.7464 | 1326864.1514
ALBANY | BROOKLYN | Food Waste Disposer | 823 | 0 | 0 | 2025 | [5 empty] | 1414519.6847 | 2741383.8361
ALBANY II | BROOKLYN | Food Waste Disposer | 400 | 0 | 0 | 2025 | [5 empty] | 687494.379 | 3428878.2151
ARMSTRONG I | BROOKLYN | Food Waste Disposer | 369 | Zone 1 | $ | [6 empty] | 634213.5646 | 4063091.7796
ARMSTRONG II | BROOKLYN | Food Waste Disposer | 248 | Zone 1 | $ | [6 empty] | 426246.515 | 4489338.2946
BARUCH | MANHATTAN | Food Waste Disposer | 2193 | Zone 1 | $ | [6 empty] | 3769187.9326 | 8258526.2272
BEDFORD-STUYVESANT REHAB | BROOKLYN | Food Waste Disposer | 84 | Zone 1 | $ | [6 empty] | 144373.8196 | 8402900.0468
BERRY STREET-SOUTH 9TH STREET | BROOKLYN | Food Waste Disposer | 150 | 0 | 0 | [6 empty] | 257810.3921 | 8660710.4389
BORINQUEN PLAZA I | BROOKLYN | Food Waste Disposer | 509 | Zone 3 | $$$$ | [6 empty] | 874836.5972 | 9535547.0361
BORINQUEN PLAZA II | BROOKLYN | Food Waste Disposer | 425 | Zone 3 | $$$ | [6 empty] | 730462.7776 | 10266009.8138
BRACETTI PLAZA | MANHATTAN | Food Waste Disposer | 108 | Zone 1 | $ | 2026 | [5 empty] | 185623.4823 | 10451633.2961
BREVOORT | BROOKLYN | Food Waste Disposer | 894 | 0 | 0 | [6 empty] | 1536549.937 | 11988183.2331
BUSHWICK | BROOKLYN | Food Waste Disposer | 1219 | Zone 1 | $$ | [6 empty] | 2095139.1199 | 14083322.3529
BUSHWICK II (GROUPS A & C) | BROOKLYN | Food Waste Disposer | 299 | Zone 1 | 0 | [6 empty] | 513902.0483 | 14597224.4012
BUSHWICK II (GROUPS B & D) | BROOKLYN | Food Waste Disposer | 300 | 0 | 0 | [6 empty] | 515620.7842 | 15112845.1854
BUSHWICK II CDA (GROUP E) | BROOKLYN | Food Waste Disposer | 276 | Zone 1 | 0 | 2019 | Yes |  |  |  |  | 0 | 15112845.1854
CAMPOS PLAZA II | MANHATTAN | Food Waste Disposer | 224 | Zone 1 | $$ | 2026 | [5 empty] | 384996.8522 | 15497842.0377
COOPER PARK | BROOKLYN | Food Waste Disposer | 700 | 0 | 0 | [6 empty] | 1203115.1632 | 16700957.2008
CROWN HEIGHTS | BROOKLYN | Food Waste Disposer | 121 | Zone 4 | 0 | 2025 | [5 empty] | 207967.0496 | 16908924.2505
FARRAGUT | BROOKLYN | Food Waste Disposer | 1389 | 0 | 0 | 2027 | [5 empty] | 2387324.2309 | 19296248.4814
FHA REPOSSESSED HOUSES (GROUP IX) | 0 | Food Waste Disposer | 16 | Zone 4 | 0 | [6 empty] | 27499.7752 | 19323748.2566
FIRST HOUSES | MANHATTAN | Food Waste Disposer | 126 | Zone 1 | $ | 2026 | [5 empty] | 216560.7294 | 19540308.9859
GOMPERS | MANHATTAN | Food Waste Disposer | 472 | Zone 1 | $ | [6 empty] | 811243.3672 | 20351552.3531
HERNANDEZ | MANHATTAN | Food Waste Disposer | 149 | Zone 1 | $$ | [6 empty] | 256091.6562 | 20607644.0093
HOPE GARDENS | BROOKLYN | Food Waste Disposer | 323 | Zone 1 | 0 | 2019 | Yes |  |  |  |  | 0 | 20607644.0093
HYLAN | BROOKLYN | Food Waste Disposer | 209 | Zone 1 | $ | [6 empty] | 359215.813 | 20966859.8223
INDEPENDENCE | BROOKLYN | Food Waste Disposer | 741 | 0 | 0 | 2019 | Yes |  |  |  |  | 0 | 20966859.8223
INGERSOLL | BROOKLYN | Food Waste Disposer | 1830 | 0 | 0 | [6 empty] | 3145286.7837 | 24112146.606
KINGSBOROUGH | BROOKLYN | Food Waste Disposer | 1154 | Zone 3 | $ | [6 empty] | 1983421.2833 | 26095567.8893
KINGSBOROUGH EXTENSION | BROOKLYN | Food Waste Disposer | 182 | Zone 4 | 0 | [6 empty] | 312809.9424 | 26408377.8317
LA GUARDIA | MANHATTAN | Food Waste Disposer | 1091 | Zone 1 | $$ | [6 empty] | 1875140.9186 | 28283518.7503
LA GUARDIA ADDITION | MANHATTAN | Food Waste Disposer | 149 | Zone 1 | $ | [6 empty] | 256091.6562 | 28539610.4065
LAFAYETTE | BROOKLYN | Food Waste Disposer | 882 | Zone 1 | $$$ | [6 empty] | 1515925.1056 | 30055535.5121
LAVANBURG HOMES | MANHATTAN | Food Waste Disposer | 95 | 0 | 0 | [6 empty] | 163279.915 | 30218815.4271
LOWER EAST SIDE I INFILL | MANHATTAN | Food Waste Disposer | 189 | Zone 1 | $$ | [6 empty] | 324841.0941 | 30543656.5211
LOWER EAST SIDE II | MANHATTAN | Food Waste Disposer | 188 | Zone 1 | $ | 2026 | [5 empty] | 323122.3581 | 30866778.8793
LOWER EAST SIDE III | MANHATTAN | Food Waste Disposer | 56 | Zone 1 | $ | [6 empty] | 96249.2131 | 30963028.0923
LOWER EAST SIDE REHAB (GROUP 5) | MANHATTAN | Food Waste Disposer | 55 | Zone 1 | $$ | 2026 | [5 empty] | 94530.4771 | 31057558.5694
MARCY | BROOKLYN | Food Waste Disposer | 1716 | Zone 1 | $$ | 2027 | [5 empty] | 2949350.8857 | 34006909.4551
OCEAN HILL APARTMENTS | BROOKLYN | Food Waste Disposer | 238 | 0 | 0 | [6 empty] | 409059.1555 | 34415968.6106
OCEAN HILL-BROWNSVILLE | BROOKLYN | Food Waste Disposer | 125 | 0 | 0 | 2025 | [5 empty] | 214841.9934 | 34630810.604
PALMETTO GARDENS | BROOKLYN | Food Waste Disposer | 113 | 0 | 0 | 2019 | Yes |  |  |  |  | 0 | 34630810.604
PARK ROCK REHAB | BROOKLYN | Food Waste Disposer | 134 | 0 | 0 | 2025 | [5 empty] | 230310.617 | 34861121.221
RIIS | MANHATTAN | Food Waste Disposer | 1191 | Zone 1 | $ | [6 empty] | 2047014.5133 | 36908135.7343
RIIS II | MANHATTAN | Food Waste Disposer | 577 | Zone 1 | $$ | [6 empty] | 991710.6416 | 37899846.376
ROOSEVELT I | BROOKLYN | Food Waste Disposer | 761 | Zone 1 | $ | [6 empty] | 1307958.056 | 39207804.432
ROOSEVELT II | BROOKLYN | Food Waste Disposer | 342 | Zone 1 | $ | [6 empty] | 587807.694 | 39795612.126
RUTGERS | MANHATTAN | Food Waste Disposer | 721 | Zone 1 | $ | [6 empty] | 1239208.6181 | 41034820.744
SARATOGA VILLAGE | BROOKLYN | Food Waste Disposer | 125 | 0 | 0 | [6 empty] | 214841.9934 | 41249662.7375
SEWARD PARK EXTENSION | MANHATTAN | Food Waste Disposer | 360 | Zone 1 | $ | [6 empty] | 618744.9411 | 41868407.6785
SMITH | MANHATTAN | Food Waste Disposer | 1934 | Zone 1 | $ | [6 empty] | 3324035.3223 | 45192443.0008
STANTON STREET | MANHATTAN | Food Waste Disposer | 13 | 0 | 0 | [6 empty] | 22343.5673 | 45214786.5681
STERLING PLACE REHABS (SAINT JOHNS-STERLING) | BROOKLYN | Food Waste Disposer | 83 | 0 | 0 | 2025 | [5 empty] | 142655.0836 | 45357441.6517
STERLING PLACE REHABS (STERLING-BUFFALO) | BROOKLYN | Food Waste Disposer | 125 | 0 | 0 | 2025 | [5 empty] | 214841.9934 | 45572283.6452
STRAUS | MANHATTAN | Food Waste Disposer | 267 | 0 | 0 | [6 empty] | 458902.498 | 46031186.1431
STUYVESANT GARDENS I | BROOKLYN | Food Waste Disposer | 329 | 0 | 0 | [6 empty] | 565464.1267 | 46596650.2698
STUYVESANT GARDENS II | BROOKLYN | Food Waste Disposer | 150 | 0 | 0 | [6 empty] | 257810.3921 | 46854460.6619
SUMNER | BROOKLYN | Food Waste Disposer | 1098 | Zone 1 | $ | [6 empty] | 1887172.0702 | 48741632.7322
TAYLOR STREET-WYTHE AVENUE | BROOKLYN | Food Waste Disposer | 525 | 0 | 0 | [6 empty] | 902336.3724 | 49643969.1045
TOMPKINS | BROOKLYN | Food Waste Disposer | 1045 | Zone 1 | $ | [6 empty] | 1796079.065 | 51440048.1696
VLADECK | MANHATTAN | Food Waste Disposer | 1527 | Zone 1 | $$ | [6 empty] | 2624509.7917 | 54064557.9612
VLADECK II | MANHATTAN | Food Waste Disposer | 240 | Zone 1 | $ | [6 empty] | 412496.6274 | 54477054.5886
WALD | MANHATTAN | Food Waste Disposer | 1861 | Zone 1 | $ | [6 empty] | 3198567.5981 | 57675622.1867
WEEKSVILLE GARDENS | BROOKLYN | Food Waste Disposer | 256 | 0 | 0 | 2019 | Yes |  |  |  |  | 0 | 57675622.1867
WHITMAN | BROOKLYN | Food Waste Disposer | 1651 | 0 | 0 | [6 empty] | 2837633.0491 | 60513255.2359
WILLIAMS PLAZA | BROOKLYN | Food Waste Disposer | 577 | 0 | 0 | 2019 | Yes |  |  |  |  | 0 | 60513255.2359
WILLIAMSBURG | BROOKLYN | Food Waste Disposer | 1627 | 0 | 0 | 2020 | Yes |  |  |  |  | 0 | 60513255.2359
Formulas:
Is RAD/PACT w/in 5yr = IF(FWD[[#This Row],[RAD/PACT]]="","",IF((FWD[[#This Row],[RAD/PACT]]-YEAR(TODAY()))<=5,"Yes",""))

## EHD
[11 empty] | 1311334.68 | 19035247.36 | 20346582.04
DEVELOPMENT | BOROUGH | WORK TYPE | # Hopper Doors | NRR | Priority Level | RAD/PACT | Is RAD/PACT w/in 5yr | CALENDAR YEAR | FISCAL YEAR | STATUS | COST | ESTIMATE | Running Cost/Yr
BETHUNE GARDENS | MANHATTAN | Enlarge Hopper Door | 1 | Zone 3 | $$ | 2020 | Yes | 2019 | 2019 | COMPLETED |  |  | 0
MARSHALL PLAZA | MANHATTAN | Enlarge Hopper Door | 1 | Zone 3 | $$ | 2020 | Yes | 2019 | 2019 | COMPLETED |  |  | 0
BARUCH HOUSES ADDITION | MANHATTAN | Enlarge Hopper Door | 1 | Zone 1 | $ |  |  | 2019 | 2019 | COMPLETED |  |  | 0
LA GUARDIA ADDITION | MANHATTAN | Enlarge Hopper Door | 1 | Zone 1 | $ |  |  | 2019 | 2019 | COMPLETED |  |  | 0
MELTZER TOWER | MANHATTAN | Enlarge Hopper Door | 1 | Zone 1 | $ |  |  | 2019 | 2019 | COMPLETED |  |  | 0
TWIN PARKS EAST (SITE 9) | BRONX | Enlarge Hopper Door | 1 | Zone 1 | $ |  |  | 2019 | 2019 | COMPLETED |  |  | 0
CORSI HOUSES | MANHATTAN | Enlarge Hopper Door | 1 | Zone 2 | $ | 2026 |  | 2019 | 2019 | COMPLETED |  |  | 0
UPACA (SITE 5) | MANHATTAN | Enlarge Hopper Door | 1 | Zone 2 | $ |  |  | 2019 | 2019 | COMPLETED |  |  | 0
WHITE | MANHATTAN | Enlarge Hopper Door | 2 | Zone 2 | $ |  |  | 2019 | 2019 | COMPLETED |  |  | 0
UNION AVENUE-EAST 163RD STREET | BRONX | Enlarge Hopper Door | 1 | Zone 3 | $ | 2026 |  | 2019 | 2019 | COMPLETED |  |  | 0
BOSTON ROAD PLAZA | BRONX | Enlarge Hopper Door | 1 | 0 | 0 | 2022 | Yes | 2019 | 2019 | COMPLETED |  |  | 0
BRONX RIVER ADDITION | BRONX | Enlarge Hopper Door | 2 | 0 | 0 |  |  | 2019 | 2019 | COMPLETED |  |  | 0
BROWN | BROOKLYN | Enlarge Hopper Door | 2 | 0 | 0 |  |  | 2019 | 2019 | COMPLETED |  |  | 0
CASSIDY-LAFAYETTE | STATEN ISLAND | Enlarge Hopper Door | 4 | 0 | 0 |  |  | 2019 | 2019 | COMPLETED |  |  | 0
CONLON LIHFE TOWER | QUEENS | Enlarge Hopper Door | 1 | 0 | 0 |  |  | 2019 | 2019 | COMPLETED |  |  | 0
HABER | BROOKLYN | Enlarge Hopper Door | 3 | 0 | 0 |  |  | 2019 | 2019 | COMPLETED |  |  | 0
INTERNATIONAL TOWER | QUEENS | Enlarge Hopper Door | 2 | 0 | 0 |  |  | 2019 | 2019 | COMPLETED |  |  | 0
MIDDLETOWN PLAZA | BRONX | Enlarge Hopper Door | 1 | 0 | 0 | 2026 |  | 2019 | 2019 | COMPLETED |  |  | 0
NEW LANE AREA | STATEN ISLAND | Enlarge Hopper Door | 2 | 0 | 0 |  |  | 2019 | 2019 | COMPLETED |  |  | 0
RANDALL AVENUE-BALCOM AVENUE | BRONX | Enlarge Hopper Door | 3 | 0 | 0 | 2022 | Yes | 2019 | 2019 | COMPLETED |  |  | 0
REID APARTMENTS | BROOKLYN | Enlarge Hopper Door | 1 | 0 | 0 | 2021 | Yes | 2019 | 2019 | COMPLETED |  |  | 0
ROBBINS PLAZA | MANHATTAN | Enlarge Hopper Door | 1 | 0 | 0 |  |  | 2019 | 2019 | COMPLETED |  |  | 0
SHELTON HOUSE | QUEENS | Enlarge Hopper Door | 1 | 0 | 0 |  |  | 2019 | 2019 | COMPLETED |  |  | 0
STUYVESANT GARDENS II | BROOKLYN | Enlarge Hopper Door | 1 | 0 | 0 |  |  | 2019 | 2019 | COMPLETED |  |  | 0
VANDALIA AVENUE | BROOKLYN | Enlarge Hopper Door | 2 | 0 | 0 |  |  | 2019 | 2019 | COMPLETED |  |  | 0
WOODSON | BROOKLYN | Enlarge Hopper Door | 2 | 0 | 0 |  |  | 2019 | 2019 | COMPLETED |  |  | 0
KINGSBOROUGH EXTENSION | BROOKLYN | Enlarge Hopper Door | 2 | Zone 4 | 0 |  |  | 2019 | 2019 | COMPLETED |  |  | 0
LAFAYETTE | BROOKLYN | Enlarge Hopper Door | 7 | Zone 1 | $$$ |  |  | 2019 | 2020 | IN PROGRESS | 44983.35 |  | 44983.35
BUSHWICK | BROOKLYN | Enlarge Hopper Door | 8 | Zone 1 | $$ |  |  | 2019 | 2020 | IN PROGRESS | 44243.94 |  | 89227.29
BUTLER | BRONX | Enlarge Hopper Door | 12 | Zone 1 | $$ |  |  | 2019 | 2020 | IN PROGRESS | 38658.23 |  | 127885.52
LA GUARDIA | MANHATTAN | Enlarge Hopper Door | 9 | Zone 1 | $$ |  |  | 2019 | 2020 | IN PROGRESS | 56519.89 |  | 184405.41
MARCY | BROOKLYN | Enlarge Hopper Door | 69 | Zone 1 | $$ | 2027 |  | 2019 | 2020 | IN PROGRESS | 431441.19 |  | 615846.6
MORRIS I | BRONX | Enlarge Hopper Door | 10 | Zone 1 | $$ |  |  | 2019 | 2020 | IN PROGRESS | 57268.37 |  | 673114.97
CLAREMONT REHAB (GROUP 3) | BRONX | Enlarge Hopper Door | 4 | Zone 1 | $ | 2025 |  | 2019 | 2020 | IN PROGRESS | 51048.6 |  | 724163.57
CLAREMONT REHAB (GROUP 4) | BRONX | Enlarge Hopper Door | 9 | Zone 1 | $ | 2025 |  | 2019 | 2020 | IN PROGRESS | 57268.37 |  | 781431.94
JACKSON | BRONX | Enlarge Hopper Door | 7 | Zone 1 | $ |  |  | 2019 | 2020 | IN PROGRESS | 44828.82 |  | 826260.76
MELROSE | BRONX | Enlarge Hopper Door | 8 | Zone 1 | $ | 2023 | Yes | 2019 | 2020 | IN PROGRESS | 51048.6 |  | 877309.36
MORRISANIA AIR RIGHTS | BRONX | Enlarge Hopper Door | 5 | Zone 1 | $ |  |  | 2019 | 2020 | IN PROGRESS | 32430.28 |  | 909739.64
ROOSEVELT I | BROOKLYN | Enlarge Hopper Door | 6 | Zone 1 | $ |  |  | 2019 | 2020 | IN PROGRESS | 38790.68 |  | 948530.32
RUTGERS | MANHATTAN | Enlarge Hopper Door | 5 | Zone 1 | $ |  |  | 2019 | 2020 | IN PROGRESS | 32007.26 |  | 980537.58
SMITH | MANHATTAN | Enlarge Hopper Door | 13 | Zone 1 | $ |  |  | 2019 | 2020 | IN PROGRESS | 74933.74 |  | 1055471.32
SUMNER | BROOKLYN | Enlarge Hopper Door | 24 | Zone 1 | $ |  |  | 2019 | 2020 | IN PROGRESS | 148620.14 |  | 1204091.46
TOMPKINS | BROOKLYN | Enlarge Hopper Door | 12 | Zone 1 | $ |  |  | 2019 | 2020 | IN PROGRESS | 74933.74 |  | 1279025.2
WEBSTER | BRONX | Enlarge Hopper Door | 5 | Zone 1 | $ |  |  | 2019 | 2020 | IN PROGRESS | 32309.48 |  | 1311334.68
MORRISANIA | BRONX | Enlarge Hopper Door | 2 | Zone 1 | $$$$ | [6 empty] | 14871.287 | 14871.287
CLINTON | MANHATTAN | Enlarge Hopper Door | 6 | Zone 2 | $$$$ | [6 empty] | 44613.861 | 59485.148
GRANT | MANHATTAN | Enlarge Hopper Door | 16 | Zone 2 | $$$$ | [6 empty] | 118970.296 | 178455.444
LINCOLN | MANHATTAN | Enlarge Hopper Door | 20 | Zone 2 | $$$$ | [6 empty] | 148712.87 | 327168.314
MORRIS PARK SENIOR CITIZENS HOME | MANHATTAN | Enlarge Hopper Door | 1 | Zone 2 | $$$$ | [6 empty] | 7435.6435 | 334603.9575
AUDUBON | MANHATTAN | Enlarge Hopper Door | 2 | Zone 3 | $$$$ | 2020 | Yes |  |  |  |  | 0 | 334603.9575
BORINQUEN PLAZA I | BROOKLYN | Enlarge Hopper Door | 8 | Zone 3 | $$$$ | [6 empty] | 59485.148 | 394089.1055
MORRIS II | BRONX | Enlarge Hopper Door | 7 | Zone 1 | $$$ | [6 empty] | 52049.5045 | 446138.61
JOHNSON | MANHATTAN | Enlarge Hopper Door | 17 | Zone 2 | $$$ | 2028 | [5 empty] | 126405.9395 | 572544.5495
KING TOWERS | MANHATTAN | Enlarge Hopper Door | 10 | Zone 2 | $$$ | [6 empty] | 74356.435 | 646900.9845
TAFT | MANHATTAN | Enlarge Hopper Door | 11 | Zone 2 | $$$ | [6 empty] | 81792.0785 | 728693.063
WASHINGTON | MANHATTAN | Enlarge Hopper Door | 14 | Zone 2 | $$$ | 2023 | Yes |  |  |  |  | 104099.009 | 832792.072
BORINQUEN PLAZA II | BROOKLYN | Enlarge Hopper Door | 7 | Zone 3 | $$$ | [6 empty] | 52049.5045 | 884841.5765
DOUGLASS I | MANHATTAN | Enlarge Hopper Door | 11 | Zone 3 | $$$ | [6 empty] | 81792.0785 | 966633.655
DOUGLASS II | MANHATTAN | Enlarge Hopper Door | 6 | Zone 3 | $$$ | [6 empty] | 44613.861 | 1011247.516
STEBBINS AVENUE-HEWITT PLACE | BRONX | Enlarge Hopper Door | 0 | Zone 3 | $$$ | 2026 | [5 empty] | 0 | 1011247.516
45 ALLEN STREET | MANHATTAN | Enlarge Hopper Door | 1 | Zone 1 | $$ | [6 empty] | 7435.6435 | 1018683.1595
CAMPOS PLAZA II | MANHATTAN | Enlarge Hopper Door | 3 | Zone 1 | $$ | 2026 | [5 empty] | 22306.9305 | 1040990.09
EAST 180TH STREET-MONTEREY AVENUE | BRONX | Enlarge Hopper Door | 2 | Zone 1 | $$ | [6 empty] | 14871.287 | 1055861.377
HERNANDEZ | MANHATTAN | Enlarge Hopper Door | 1 | Zone 1 | $$ | [6 empty] | 7435.6435 | 1063297.0205
LOWER EAST SIDE I INFILL | MANHATTAN | Enlarge Hopper Door | 0 | Zone 1 | $$ | [6 empty] | 0 | 1063297.0205
LOWER EAST SIDE REHAB (GROUP 5) | MANHATTAN | Enlarge Hopper Door | 2 | Zone 1 | $$ | 2026 | [5 empty] | 14871.287 | 1078168.3075
RIIS II | MANHATTAN | Enlarge Hopper Door | 7 | Zone 1 | $$ | [6 empty] | 52049.5045 | 1130217.812
VLADECK | MANHATTAN | Enlarge Hopper Door | 45 | Zone 1 | $$ | [6 empty] | 334603.9575 | 1464821.7695
CARVER | MANHATTAN | Enlarge Hopper Door | 13 | Zone 2 | $$ | [6 empty] | 96663.3655 | 1561485.135
JEFFERSON | MANHATTAN | Enlarge Hopper Door | 34 | Zone 2 | $$ | 2026 | [5 empty] | 252811.879 | 1814297.014
ROBINSON | MANHATTAN | Enlarge Hopper Door | 2 | Zone 2 | $$ | [6 empty] | 14871.287 | 1829168.301
SAMUEL (CITY) | MANHATTAN | Enlarge Hopper Door | 40 | Zone 2 | $$ | 2026 | [5 empty] | 297425.74 | 2126594.041
HARLEM RIVER II | MANHATTAN | Enlarge Hopper Door | 1 | Zone 3 | $$ | 2020 | Yes |  |  |  |  | 0 | 2126594.041
MOORE | BRONX | Enlarge Hopper Door | 4 | Zone 3 | $$ | [6 empty] | 29742.574 | 2156336.615
PARK AVENUE-EAST 122ND, 123RD STREETS | MANHATTAN | Enlarge Hopper Door | 2 | Zone 3 | $$ | 2019 | Yes |  |  |  |  | 0 | 2156336.615
PATTERSON | BRONX | Enlarge Hopper Door | 25 | Zone 3 | $$ | 2025 | [5 empty] | 185891.0875 | 2342227.7025
SOUTH BRONX AREA (SITE 402) | BRONX | Enlarge Hopper Door | 0 | Zone 3 | $$ | 2026 | [5 empty] | 0 | 2342227.7025
303 VERNON AVENUE | BROOKLYN | Enlarge Hopper Door | 2 | Zone 1 | $ | [6 empty] | 14871.287 | 2357098.9895
ARMSTRONG I | BROOKLYN | Enlarge Hopper Door | 6 | Zone 1 | $ | [6 empty] | 44613.861 | 2401712.8505
ARMSTRONG II | BROOKLYN | Enlarge Hopper Door | 10 | Zone 1 | $ | [6 empty] | 74356.435 | 2476069.2855
BARUCH | MANHATTAN | Enlarge Hopper Door | 17 | Zone 1 | $ | [6 empty] | 126405.9395 | 2602475.225
BEDFORD-STUYVESANT REHAB | BROOKLYN | Enlarge Hopper Door | 5 | Zone 1 | $ | [6 empty] | 37178.2175 | 2639653.4425
BRACETTI PLAZA | MANHATTAN | Enlarge Hopper Door | 2 | Zone 1 | $ | 2026 | [5 empty] | 14871.287 | 2654524.7295
CLAREMONT REHAB (GROUP 2) | BRONX | Enlarge Hopper Door | 5 | Zone 1 | $ | 2025 | [5 empty] | 37178.2175 | 2691702.947
CLAREMONT REHAB (GROUP 5) | BRONX | Enlarge Hopper Door | 4 | Zone 1 | $ | 2025 | [5 empty] | 29742.574 | 2721445.521
COLLEGE AVENUE-EAST 165TH STREET | BRONX | Enlarge Hopper Door | 1 | Zone 1 | $ | 2025 | [5 empty] | 7435.6435 | 2728881.1645
FIRST HOUSES | MANHATTAN | Enlarge Hopper Door | 8 | Zone 1 | $ | 2026 | [5 empty] | 59485.148 | 2788366.3125
GOMPERS | MANHATTAN | Enlarge Hopper Door | 4 | Zone 1 | $ | [6 empty] | 29742.574 | 2818108.8865
HIGHBRIDGE GARDENS | BRONX | Enlarge Hopper Door | 6 | Zone 1 | $ | [6 empty] | 44613.861 | 2862722.7475
HYLAN | BROOKLYN | Enlarge Hopper Door | 1 | Zone 1 | $ | [6 empty] | 7435.6435 | 2870158.391
LOWER EAST SIDE II | MANHATTAN | Enlarge Hopper Door | 0 | Zone 1 | $ | 2026 | [5 empty] | 0 | 2870158.391
LOWER EAST SIDE III | MANHATTAN | Enlarge Hopper Door | 0 | Zone 1 | $ | [6 empty] | 0 | 2870158.391
MARCY AVENUE-GREENE AVENUE SITE A | BROOKLYN | Enlarge Hopper Door | 0 | Zone 1 | $ | 2019 | Yes |  |  |  |  | 0 | 2870158.391
RIIS | MANHATTAN | Enlarge Hopper Door | 15 | Zone 1 | $ | [6 empty] | 111534.6525 | 2981693.0435
ROOSEVELT II | BROOKLYN | Enlarge Hopper Door | 3 | Zone 1 | $ | [6 empty] | 22306.9305 | 3003999.974
SEWARD PARK EXTENSION | MANHATTAN | Enlarge Hopper Door | 2 | Zone 1 | $ | [6 empty] | 14871.287 | 3018871.261
TELLER AVENUE-EAST 166TH STREET | BRONX | Enlarge Hopper Door | 2 | Zone 1 | $ | 2025 | [5 empty] | 14871.287 | 3033742.548
TWO BRIDGES URA (SITE 7) | MANHATTAN | Enlarge Hopper Door | 1 | Zone 1 | $ | [6 empty] | 7435.6435 | 3041178.1915
VLADECK II | MANHATTAN | Enlarge Hopper Door | 7 | Zone 1 | $ | [6 empty] | 52049.5045 | 3093227.696
WALD | MANHATTAN | Enlarge Hopper Door | 17 | Zone 1 | $ | [6 empty] | 126405.9395 | 3219633.6355
131 SAINT NICHOLAS AVENUE | MANHATTAN | Enlarge Hopper Door | 1 | Zone 2 | $ | [6 empty] | 7435.6435 | 3227069.279
DREW-HAMILTON | MANHATTAN | Enlarge Hopper Door | 5 | Zone 2 | $ | [6 empty] | 37178.2175 | 3264247.4965
EAST RIVER | MANHATTAN | Enlarge Hopper Door | 29 | Zone 2 | $ | 2024 | Yes |  |  |  |  | 215633.6615 | 3479881.158
LEXINGTON | MANHATTAN | Enlarge Hopper Door | 4 | Zone 2 | $ | 2023 | Yes |  |  |  |  | 29742.574 | 3509623.732
MANHATTANVILLE | MANHATTAN | Enlarge Hopper Door | 6 | Zone 2 | $ | 2028 | [5 empty] | 44613.861 | 3554237.593
METRO NORTH PLAZA | MANHATTAN | Enlarge Hopper Door | 3 | Zone 2 | $ | [6 empty] | 22306.9305 | 3576544.5235
POLO GROUNDS TOWERS | MANHATTAN | Enlarge Hopper Door | 9 | Zone 2 | $ | [6 empty] | 66920.7915 | 3643465.315
RANGEL | MANHATTAN | Enlarge Hopper Door | 10 | Zone 2 | $ | [6 empty] | 74356.435 | 3717821.75
SAINT NICHOLAS | MANHATTAN | Enlarge Hopper Door | 14 | Zone 2 | $ | [6 empty] | 104099.009 | 3821920.759
UPACA (SITE 6) | MANHATTAN | Enlarge Hopper Door | 1 | Zone 2 | $ | [6 empty] | 7435.6435 | 3829356.4025
WAGNER | MANHATTAN | Enlarge Hopper Door | 22 | Zone 2 | $ | [6 empty] | 163584.157 | 3992940.5595
WILSON | MANHATTAN | Enlarge Hopper Door | 5 | Zone 2 | $ | [6 empty] | 37178.2175 | 4030118.777
335 EAST 111TH STREET | MANHATTAN | Enlarge Hopper Door | 1 | Zone 3 | $ | [6 empty] | 7435.6435 | 4037554.4205
BRONX RIVER | BRONX | Enlarge Hopper Door | 9 | Zone 3 | $ | [6 empty] | 66920.7915 | 4104475.212
CLAREMONT PARKWAY-FRANKLIN AVENUE | BRONX | Enlarge Hopper Door | 1 | Zone 3 | $ | 2026 | [5 empty] | 7435.6435 | 4111910.8555
DAVIDSON | BRONX | Enlarge Hopper Door | 1 | Zone 3 | $ | 2026 | [5 empty] | 7435.6435 | 4119346.499
DOUGLASS ADDITION | MANHATTAN | Enlarge Hopper Door | 1 | Zone 3 | $ | [6 empty] | 7435.6435 | 4126782.1425
FORT WASHINGTON AVENUE REHAB | MANHATTAN | Enlarge Hopper Door | 2 | Zone 3 | $ | 2019 | Yes |  |  |  |  | 0 | 4126782.1425
FULTON | MANHATTAN | Enlarge Hopper Door | 19 | Zone 3 | $ | [6 empty] | 141277.2265 | 4268059.369
GRAMPION | MANHATTAN | Enlarge Hopper Door | 1 | Zone 3 | $ | 2019 | Yes |  |  |  |  | 0 | 4268059.369
HARLEM RIVER | MANHATTAN | Enlarge Hopper Door | 43 | Zone 3 | $ | 2020 | Yes |  |  |  |  | 0 | 4268059.369
KINGSBOROUGH | BROOKLYN | Enlarge Hopper Door | 35 | Zone 3 | $ | [6 empty] | 260247.5225 | 4528306.8915
MANHATTANVILLE REHAB (GROUP 2) | MANHATTAN | Enlarge Hopper Door | 3 | Zone 3 | $ | 2019 | Yes |  |  |  |  | 0 | 4528306.8915
MANHATTANVILLE REHAB (GROUP 3) | MANHATTAN | Enlarge Hopper Door | 2 | Zone 3 | $ | 2019 | Yes |  |  |  |  | 0 | 4528306.8915
MONROE | BRONX | Enlarge Hopper Door | 18 | Zone 3 | $ | [6 empty] | 133841.583 | 4662148.4745
PUBLIC SCHOOL 139 (CONVERSION) | MANHATTAN | Enlarge Hopper Door | 1 | Zone 3 | $ | 2019 | Yes |  |  |  |  | 0 | 4662148.4745
QUEENSBRIDGE NORTH | QUEENS | Enlarge Hopper Door | 47 | Zone 3 | $ | [6 empty] | 349475.2445 | 5011623.719
QUEENSBRIDGE SOUTH | QUEENS | Enlarge Hopper Door | 49 | Zone 3 | $ | [6 empty] | 364346.5315 | 5375970.2505
SAINT MARY'S PARK | BRONX | Enlarge Hopper Door | 6 | Zone 3 | $ | [6 empty] | 44613.861 | 5420584.1115
UNION AVENUE-EAST 166TH STREET | BRONX | Enlarge Hopper Door | 0 | Zone 3 | $ | 2026 | [5 empty] | 0 | 5420584.1115
WASHINGTON HEIGHTS REHAB PHASE III | MANHATTAN | Enlarge Hopper Door | 0 | Zone 3 | $ | 2019 | Yes |  |  |  |  | 0 | 5420584.1115
1010 EAST 178TH STREET | BRONX | Enlarge Hopper Door | 1 | 0 | 0 | [6 empty] | 7435.6435 | 5428019.755
104-14 TAPSCOTT STREET | BROOKLYN | Enlarge Hopper Door | 2 | 0 | 0 | 2021 | Yes |  |  |  |  | 14871.287 | 5442891.042
1162-1176 WASHINGTON AVENUE | BRONX | Enlarge Hopper Door | 1 | 0 | 0 | 2025 | [5 empty] | 7435.6435 | 5450326.6855
1471 WATSON AVENUE | BRONX | Enlarge Hopper Door | 2 | 0 | 0 | 2021 | Yes |  |  |  |  | 14871.287 | 5465197.9725
154 WEST 84TH STREET | MANHATTAN | Enlarge Hopper Door | 1 | 0 | 0 | [6 empty] | 7435.6435 | 5472633.616
344 EAST 28TH STREET | MANHATTAN | Enlarge Hopper Door | 1 | 0 | 0 | [6 empty] | 7435.6435 | 5480069.2595
572 WARREN STREET | BROOKLYN | Enlarge Hopper Door | 2 | 0 | 0 | [6 empty] | 14871.287 | 5494940.5465
830 AMSTERDAM AVENUE | MANHATTAN | Enlarge Hopper Door | 2 | 0 | 0 | [6 empty] | 14871.287 | 5509811.8335
ADAMS | BRONX | Enlarge Hopper Door | 7 | 0 | 0 | [6 empty] | 52049.5045 | 5561861.338
ALBANY | BROOKLYN | Enlarge Hopper Door | 6 | 0 | 0 | 2025 | [5 empty] | 44613.861 | 5606475.199
ALBANY II | BROOKLYN | Enlarge Hopper Door | 3 | 0 | 0 | 2025 | [5 empty] | 22306.9305 | 5628782.1295
AMSTERDAM ADDITION | MANHATTAN | Enlarge Hopper Door | 2 | 0 | 0 | [6 empty] | 14871.287 | 5643653.4165
ASTORIA | QUEENS | Enlarge Hopper Door | 22 | 0 | 0 | 2024 | Yes |  |  |  |  | 163584.157 | 5807237.5735
ATLANTIC TERMINAL SITE 4B | BROOKLYN | Enlarge Hopper Door | 2 | 0 | 0 | [6 empty] | 14871.287 | 5822108.8605
BAILEY AVENUE-WEST 193RD STREET | BRONX | Enlarge Hopper Door | 1 | 0 | 0 | [6 empty] | 7435.6435 | 5829544.504
BAISLEY PARK | QUEENS | Enlarge Hopper Door | 5 | 0 | 0 | [6 empty] | 37178.2175 | 5866722.7215
BAY VIEW | BROOKLYN | Enlarge Hopper Door | 23 | 0 | 0 | [6 empty] | 171019.8005 | 6037742.522
BEACH 41ST STREET-BEACH CHANNEL DRIVE | QUEENS | Enlarge Hopper Door | 6 | 0 | 0 | [6 empty] | 44613.861 | 6082356.383
BELMONT-SUTTER AREA | BROOKLYN | Enlarge Hopper Door | 0 | 0 | 0 | [6 empty] | 0 | 6082356.383
BERRY | STATEN ISLAND | Enlarge Hopper Door | 15 | 0 | 0 | [6 empty] | 111534.6525 | 6193891.0355
BERRY STREET-SOUTH 9TH STREET | BROOKLYN | Enlarge Hopper Door | 1 | 0 | 0 | [6 empty] | 7435.6435 | 6201326.679
BLAND | QUEENS | Enlarge Hopper Door | 5 | 0 | 0 | [6 empty] | 37178.2175 | 6238504.8965
BOSTON SECOR | BRONX | Enlarge Hopper Door | 4 | 0 | 0 | [6 empty] | 29742.574 | 6268247.4705
BOULEVARD | BROOKLYN | Enlarge Hopper Door | 29 | 0 | 0 | 2020 | Yes |  |  |  |  | 0 | 6268247.4705
BOYNTON AVENUE REHAB | BRONX | Enlarge Hopper Door | 3 | 0 | 0 | [6 empty] | 22306.9305 | 6290554.401
BREUKELEN | BROOKLYN | Enlarge Hopper Door | 89 | 0 | 0 | 2021 | Yes |  |  |  |  | 661772.2715 | 6952326.6725
BREVOORT | BROOKLYN | Enlarge Hopper Door | 26 | 0 | 0 | [6 empty] | 193326.731 | 7145653.4035
BROWNSVILLE | BROOKLYN | Enlarge Hopper Door | 46 | 0 | 0 | [6 empty] | 342039.601 | 7487693.0045
BRYANT AVENUE-EAST 174TH STREET | BRONX | Enlarge Hopper Door | 1 | 0 | 0 | [6 empty] | 7435.6435 | 7495128.648
BUSHWICK II (GROUPS B & D) | BROOKLYN | Enlarge Hopper Door | 25 | 0 | 0 | [6 empty] | 185891.0875 | 7681019.7355
CAREY GARDENS | BROOKLYN | Enlarge Hopper Door | 3 | 0 | 0 | [6 empty] | 22306.9305 | 7703326.666
CARLETON MANOR | QUEENS | Enlarge Hopper Door | 1 | 0 | 0 | [6 empty] | 7435.6435 | 7710762.3095
CASTLE HILL | BRONX | Enlarge Hopper Door | 14 | 0 | 0 | [6 empty] | 104099.009 | 7814861.3185
CHELSEA | MANHATTAN | Enlarge Hopper Door | 4 | 0 | 0 | [6 empty] | 29742.574 | 7844603.8925
CHELSEA ADDITION | MANHATTAN | Enlarge Hopper Door | 1 | 0 | 0 | [6 empty] | 7435.6435 | 7852039.536
CLASON POINT GARDENS | BRONX | Enlarge Hopper Door | 0 | 0 | 0 | 2024 | Yes |  |  |  |  | 0 | 7852039.536
CONEY ISLAND | BROOKLYN | Enlarge Hopper Door | 5 | 0 | 0 | [6 empty] | 37178.2175 | 7889217.7535
CONEY ISLAND I (SITE 1B) | BROOKLYN | Enlarge Hopper Door | 1 | 0 | 0 | [6 empty] | 7435.6435 | 7896653.397
CONEY ISLAND I (SITE 8) | BROOKLYN | Enlarge Hopper Door | 1 | 0 | 0 | [6 empty] | 7435.6435 | 7904089.0405
CONEY ISLAND I (SITES 4 & 5) | BROOKLYN | Enlarge Hopper Door | 3 | 0 | 0 | [6 empty] | 22306.9305 | 7926395.971
COOPER PARK | BROOKLYN | Enlarge Hopper Door | 13 | 0 | 0 | [6 empty] | 96663.3655 | 8023059.3365
CYPRESS HILLS | BROOKLYN | Enlarge Hopper Door | 29 | 0 | 0 | 2023 | Yes |  |  |  |  | 215633.6615 | 8238692.998
DE HOSTOS APARTMENTS | MANHATTAN | Enlarge Hopper Door | 2 | 0 | 0 | [6 empty] | 14871.287 | 8253564.285
DOUGLASS | MANHATTAN | Enlarge Hopper Door | 0 | 0 | 0 | [6 empty] | 0 | 8253564.285
DYCKMAN | MANHATTAN | Enlarge Hopper Door | 14 | 0 | 0 | [6 empty] | 104099.009 | 8357663.294
EAGLE AVENUE-EAST 163RD STREET | BRONX | Enlarge Hopper Door | 1 | 0 | 0 | [6 empty] | 7435.6435 | 8365098.9375
EAST 152ND STREET-COURTLANDT AVENUE | BRONX | Enlarge Hopper Door | 2 | 0 | 0 | 2023 | Yes |  |  |  |  | 14871.287 | 8379970.2245
EAST NEW YORK CITY LINE | BROOKLYN | Enlarge Hopper Door | 0 | 0 | 0 | 2023 | Yes |  |  |  |  | 0 | 8379970.2245
EASTCHESTER GARDENS | BRONX | Enlarge Hopper Door | 15 | 0 | 0 | 2026 | [5 empty] | 111534.6525 | 8491504.877
EDENWALD | BRONX | Enlarge Hopper Door | 62 | 0 | 0 | 2022 | Yes |  |  |  |  | 461009.897 | 8952514.774
ELLIOTT | MANHATTAN | Enlarge Hopper Door | 8 | 0 | 0 | [6 empty] | 59485.148 | 9011999.922
FARRAGUT | BROOKLYN | Enlarge Hopper Door | 10 | 0 | 0 | 2027 | [5 empty] | 74356.435 | 9086356.357
FENIMORE-LEFFERTS | BROOKLYN | Enlarge Hopper Door | 0 | 0 | 0 | 2021 | Yes |  |  |  |  | 0 | 9086356.357
FHA REPOSSESSED HOUSES (GROUP I) | 0 | Enlarge Hopper Door | 0 | 0 | 0 | [6 empty] | 0 | 9086356.357
FHA REPOSSESSED HOUSES (GROUP II) | 0 | Enlarge Hopper Door | 0 | 0 | 0 | [6 empty] | 0 | 9086356.357
FHA REPOSSESSED HOUSES (GROUP III) | 0 | Enlarge Hopper Door | 0 | 0 | 0 | [6 empty] | 0 | 9086356.357
FHA REPOSSESSED HOUSES (GROUP IV) | 0 | Enlarge Hopper Door | 0 | 0 | 0 | [6 empty] | 0 | 9086356.357
FHA REPOSSESSED HOUSES (GROUP V) | 0 | Enlarge Hopper Door | 0 | 0 | 0 | [6 empty] | 0 | 9086356.357
FHA REPOSSESSED HOUSES (GROUP VI) | 0 | Enlarge Hopper Door | 0 | 0 | 0 | [6 empty] | 0 | 9086356.357
FHA REPOSSESSED HOUSES (GROUP VII) | 0 | Enlarge Hopper Door | 0 | 0 | 0 | [6 empty] | 0 | 9086356.357
FHA REPOSSESSED HOUSES (GROUP VIII) | 0 | Enlarge Hopper Door | 0 | 0 | 0 | [6 empty] | 0 | 9086356.357
FHA REPOSSESSED HOUSES (GROUP X) | 0 | Enlarge Hopper Door | 0 | 0 | 0 | [6 empty] | 0 | 9086356.357
FIORENTINO PLAZA | BROOKLYN | Enlarge Hopper Door | 3 | 0 | 0 | 2026 | [5 empty] | 22306.9305 | 9108663.2875
FORT INDEPENDENCE STREET-HEATH AVENUE | BRONX | Enlarge Hopper Door | 2 | 0 | 0 | [6 empty] | 14871.287 | 9123534.5745
GARVEY (GROUP A) | BROOKLYN | Enlarge Hopper Door | 5 | 0 | 0 | [6 empty] | 37178.2175 | 9160712.792
GLEBE AVENUE-WESTCHESTER AVENUE | BRONX | Enlarge Hopper Door | 2 | 0 | 0 | 2021 | Yes |  |  |  |  | 14871.287 | 9175584.079
GLENMORE PLAZA | BROOKLYN | Enlarge Hopper Door | 4 | 0 | 0 | [6 empty] | 29742.574 | 9205326.653
GLENWOOD | BROOKLYN | Enlarge Hopper Door | 40 | 0 | 0 | 2028 | [5 empty] | 297425.74 | 9502752.393
GOWANUS | BROOKLYN | Enlarge Hopper Door | 24 | 0 | 0 | [6 empty] | 178455.444 | 9681207.837
GRAVESEND | BROOKLYN | Enlarge Hopper Door | 15 | 0 | 0 | [6 empty] | 111534.6525 | 9792742.4895
GUN HILL | BRONX | Enlarge Hopper Door | 6 | 0 | 0 | [6 empty] | 44613.861 | 9837356.3505
HAMMEL | QUEENS | Enlarge Hopper Door | 14 | 0 | 0 | [6 empty] | 104099.009 | 9941455.3595
HARBORVIEW TERRACE | MANHATTAN | Enlarge Hopper Door | 2 | 0 | 0 | [6 empty] | 14871.287 | 9956326.6465
HARRISON AVENUE REHAB (GROUP A) | BRONX | Enlarge Hopper Door | 1 | 0 | 0 | [6 empty] | 7435.6435 | 9963762.29
HARRISON AVENUE REHAB (GROUP B) | BRONX | Enlarge Hopper Door | 4 | 0 | 0 | [6 empty] | 29742.574 | 9993504.864
HOE AVENUE-EAST 173RD STREET | BRONX | Enlarge Hopper Door | 1 | 0 | 0 | [6 empty] | 7435.6435 | 10000940.5075
HOLMES TOWERS | MANHATTAN | Enlarge Hopper Door | 2 | 0 | 0 | [6 empty] | 14871.287 | 10015811.7945
HOWARD | BROOKLYN | Enlarge Hopper Door | 16 | 0 | 0 | [6 empty] | 118970.296 | 10134782.0905
HOWARD AVENUE | BROOKLYN | Enlarge Hopper Door | 0 | 0 | 0 | 2025 | [5 empty] | 0 | 10134782.0905
HUGHES APARTMENTS | BROOKLYN | Enlarge Hopper Door | 3 | 0 | 0 | [6 empty] | 22306.9305 | 10157089.021
HUNTS POINT AVENUE REHAB | BRONX | Enlarge Hopper Door | 1 | 0 | 0 | [6 empty] | 7435.6435 | 10164524.6645
INDEPENDENCE | BROOKLYN | Enlarge Hopper Door | 6 | 0 | 0 | 2019 | Yes |  |  |  |  | 0 | 10164524.6645
INGERSOLL | BROOKLYN | Enlarge Hopper Door | 44 | 0 | 0 | [6 empty] | 327168.314 | 10491692.9785
ISAACS | MANHATTAN | Enlarge Hopper Door | 6 | 0 | 0 | [6 empty] | 44613.861 | 10536306.8395
LATIMER GARDENS | QUEENS | Enlarge Hopper Door | 4 | 0 | 0 | [6 empty] | 29742.574 | 10566049.4135
LAVANBURG HOMES | MANHATTAN | Enlarge Hopper Door | 0 | 0 | 0 | [6 empty] | 0 | 10566049.4135
LEAVITT STREET-34TH AVENUE | QUEENS | Enlarge Hopper Door | 1 | 0 | 0 | [6 empty] | 7435.6435 | 10573485.057
LEHMAN VILLAGE | MANHATTAN | Enlarge Hopper Door | 4 | 0 | 0 | [6 empty] | 29742.574 | 10603227.631
LENOX ROAD-ROCKAWAY PARKWAY | BROOKLYN | Enlarge Hopper Door | 5 | 0 | 0 | 2021 | Yes |  |  |  |  | 37178.2175 | 10640405.8485
LINDEN | BROOKLYN | Enlarge Hopper Door | 19 | 0 | 0 | 2020 | Yes |  |  |  |  | 0 | 10640405.8485
LONG ISLAND BAPTIST HOUSES | BROOKLYN | Enlarge Hopper Door | 4 | 0 | 0 | 2026 | [5 empty] | 29742.574 | 10670148.4225
LONGFELLOW AVENUE REHAB | BRONX | Enlarge Hopper Door | 5 | 0 | 0 | [6 empty] | 37178.2175 | 10707326.64
LOW HOUSES | BROOKLYN | Enlarge Hopper Door | 3 | 0 | 0 | [6 empty] | 22306.9305 | 10729633.5705
MARBLE HILL | BRONX | Enlarge Hopper Door | 11 | 0 | 0 | [6 empty] | 81792.0785 | 10811425.649
MARCY AVENUE-GREENE AVENUE SITE B | BROOKLYN | Enlarge Hopper Door | 0 | 0 | 0 | 2019 | Yes |  |  |  |  | 0 | 10811425.649
MARINER'S HARBOR | STATEN ISLAND | Enlarge Hopper Door | 27 | 0 | 0 | 2028 | [5 empty] | 200762.3745 | 11012188.0235
MARLBORO | BROOKLYN | Enlarge Hopper Door | 28 | 0 | 0 | [6 empty] | 208198.018 | 11220386.0415
MILL BROOK | BRONX | Enlarge Hopper Door | 9 | 0 | 0 | [6 empty] | 66920.7915 | 11287306.833
MILL BROOK EXTENSION | BRONX | Enlarge Hopper Door | 1 | 0 | 0 | [6 empty] | 7435.6435 | 11294742.4765
MITCHEL | BRONX | Enlarge Hopper Door | 20 | 0 | 0 | [6 empty] | 148712.87 | 11443455.3465
MOTT HAVEN | BRONX | Enlarge Hopper Door | 8 | 0 | 0 | [6 empty] | 59485.148 | 11502940.4945
NOSTRAND | BROOKLYN | Enlarge Hopper Door | 32 | 0 | 0 | 2028 | [5 empty] | 237940.592 | 11740881.0865
OCEAN BAY APARTMENTS (OCEANSIDE) | QUEENS | Enlarge Hopper Door | 13 | 0 | 0 | [6 empty] | 96663.3655 | 11837544.452
OCEAN HILL APARTMENTS | BROOKLYN | Enlarge Hopper Door | 3 | 0 | 0 | [6 empty] | 22306.9305 | 11859851.3825
OCEAN HILL-BROWNSVILLE | BROOKLYN | Enlarge Hopper Door | 6 | 0 | 0 | 2025 | [5 empty] | 44613.861 | 11904465.2435
O'DWYER GARDENS | BROOKLYN | Enlarge Hopper Door | 6 | 0 | 0 | [6 empty] | 44613.861 | 11949079.1045
PALMETTO GARDENS | BROOKLYN | Enlarge Hopper Door | 1 | 0 | 0 | 2019 | Yes |  |  |  |  | 0 | 11949079.1045
PARK ROCK REHAB | BROOKLYN | Enlarge Hopper Door | 6 | 0 | 0 | 2025 | [5 empty] | 44613.861 | 11993692.9655
PARKSIDE | BRONX | Enlarge Hopper Door | 21 | 0 | 0 | [6 empty] | 156148.5135 | 12149841.479
PELHAM PARKWAY | BRONX | Enlarge Hopper Door | 38 | 0 | 0 | 2022 | Yes |  |  |  |  | 282554.453 | 12432395.932
PENNSYLVANIA AVENUE-WORTMAN AVENUE | BROOKLYN | Enlarge Hopper Door | 3 | 0 | 0 | [6 empty] | 22306.9305 | 12454702.8625
PINK | BROOKLYN | Enlarge Hopper Door | 22 | 0 | 0 | [6 empty] | 163584.157 | 12618287.0195
POMONOK | QUEENS | Enlarge Hopper Door | 121 | 0 | 0 | 2027 | [5 empty] | 899712.8635 | 13517999.883
PSS GRANDPARENT FAMILY APARTMENTS | BRONX | Enlarge Hopper Door | 0 | 0 | 0 | [6 empty] | 0 | 13517999.883
RALPH AVENUE REHAB | BROOKLYN | Enlarge Hopper Door | 9 | 0 | 0 | 2021 | Yes |  |  |  |  | 66920.7915 | 13584920.6745
RANDOLPH SOUTH | MANHATTAN | Enlarge Hopper Door | 0 | 0 | 0 | [6 empty] | 0 | 13584920.6745
RAVENSWOOD | QUEENS | Enlarge Hopper Door | 39 | 0 | 0 | [6 empty] | 289990.0965 | 13874910.771
RED HOOK EAST | BROOKLYN | Enlarge Hopper Door | 47 | 0 | 0 | 2024 | Yes |  |  |  |  | 349475.2445 | 14224386.0155
RED HOOK WEST | BROOKLYN | Enlarge Hopper Door | 43 | 0 | 0 | 2025 | [5 empty] | 319732.6705 | 14544118.686
REDFERN | QUEENS | Enlarge Hopper Door | 16 | 0 | 0 | 2022 | Yes |  |  |  |  | 118970.296 | 14663088.982
REHAB PROGRAM (COLLEGE POINT) | QUEENS | Enlarge Hopper Door | 0 | 0 | 0 | [6 empty] | 0 | 14663088.982
REHAB PROGRAM (DOUGLASS REHABS) | MANHATTAN | Enlarge Hopper Door | 3 | 0 | 0 | [6 empty] | 22306.9305 | 14685395.9125
REHAB PROGRAM (TAFT REHABS) | MANHATTAN | Enlarge Hopper Door | 4 | 0 | 0 | [6 empty] | 29742.574 | 14715138.4865
RICHMOND TERRACE | STATEN ISLAND | Enlarge Hopper Door | 6 | 0 | 0 | [6 empty] | 44613.861 | 14759752.3475
RUTLAND TOWERS | BROOKLYN | Enlarge Hopper Door | 1 | 0 | 0 | 2021 | Yes |  |  |  |  | 7435.6435 | 14767187.991
SACK WERN | BRONX | Enlarge Hopper Door | 7 | 0 | 0 | 2024 | Yes |  |  |  |  | 52049.5045 | 14819237.4955
SAMUEL (MHOP) I | MANHATTAN | Enlarge Hopper Door | 1 | 0 | 0 | 2019 | Yes |  |  |  |  | 0 | 14819237.4955
SAMUEL (MHOP) II | MANHATTAN | Enlarge Hopper Door | 0 | 0 | 0 | 2019 | Yes |  |  |  |  | 0 | 14819237.4955
SAMUEL (MHOP) III | MANHATTAN | Enlarge Hopper Door | 1 | 0 | 0 | 2019 | Yes |  |  |  |  | 0 | 14819237.4955
SARATOGA VILLAGE | BROOKLYN | Enlarge Hopper Door | 1 | 0 | 0 | [6 empty] | 7435.6435 | 14826673.139
SEDGWICK | BRONX | Enlarge Hopper Door | 7 | 0 | 0 | [6 empty] | 52049.5045 | 14878722.6435
SHEEPSHEAD BAY | BROOKLYN | Enlarge Hopper Door | 35 | 0 | 0 | 2028 | [5 empty] | 260247.5225 | 15138970.166
SOTOMAYOR HOUSES | BRONX | Enlarge Hopper Door | 28 | 0 | 0 | [6 empty] | 208198.018 | 15347168.184
SOUNDVIEW | BRONX | Enlarge Hopper Door | 22 | 0 | 0 | 2023 | Yes |  |  |  |  | 163584.157 | 15510752.341
SOUTH BEACH | STATEN ISLAND | Enlarge Hopper Door | 15 | 0 | 0 | [6 empty] | 111534.6525 | 15622286.9935
SOUTH JAMAICA I | QUEENS | Enlarge Hopper Door | 33 | 0 | 0 | 2021 | Yes |  |  |  |  | 245376.2355 | 15867663.229
SOUTH JAMAICA II | QUEENS | Enlarge Hopper Door | 27 | 0 | 0 | 2021 | Yes |  |  |  |  | 200762.3745 | 16068425.6035
STANTON STREET | MANHATTAN | Enlarge Hopper Door | 1 | 0 | 0 | [6 empty] | 7435.6435 | 16075861.247
STAPLETON | STATEN ISLAND | Enlarge Hopper Door | 12 | 0 | 0 | [6 empty] | 89227.722 | 16165088.969
STERLING PLACE REHABS (SAINT JOHNS-STERLING) | BROOKLYN | Enlarge Hopper Door | 5 | 0 | 0 | 2025 | [5 empty] | 37178.2175 | 16202267.1865
STERLING PLACE REHABS (STERLING-BUFFALO) | BROOKLYN | Enlarge Hopper Door | 7 | 0 | 0 | 2025 | [5 empty] | 52049.5045 | 16254316.691
STRAUS | MANHATTAN | Enlarge Hopper Door | 2 | 0 | 0 | [6 empty] | 14871.287 | 16269187.978
STUYVESANT GARDENS I | BROOKLYN | Enlarge Hopper Door | 11 | 0 | 0 | [6 empty] | 81792.0785 | 16350980.0565
SURFSIDE GARDENS | BROOKLYN | Enlarge Hopper Door | 5 | 0 | 0 | [6 empty] | 37178.2175 | 16388158.274
SUTTER AVENUE-UNION STREET | BROOKLYN | Enlarge Hopper Door | 5 | 0 | 0 | 2021 | Yes |  |  |  |  | 37178.2175 | 16425336.4915
TAPSCOTT STREET REHAB | BROOKLYN | Enlarge Hopper Door | 9 | 0 | 0 | 2021 | Yes |  |  |  |  | 66920.7915 | 16492257.283
TAYLOR STREET-WYTHE AVENUE | BROOKLYN | Enlarge Hopper Door | 6 | 0 | 0 | [6 empty] | 44613.861 | 16536871.144
THROGGS NECK | BRONX | Enlarge Hopper Door | 60 | 0 | 0 | 2022 | Yes |  |  |  |  | 446138.61 | 16983009.754
THROGGS NECK ADDITION | BRONX | Enlarge Hopper Door | 4 | 0 | 0 | 2022 | Yes |  |  |  |  | 29742.574 | 17012752.328
TILDEN | BROOKLYN | Enlarge Hopper Door | 8 | 0 | 0 | [6 empty] | 59485.148 | 17072237.476
TODT HILL | STATEN ISLAND | Enlarge Hopper Door | 13 | 0 | 0 | [6 empty] | 96663.3655 | 17168900.8415
UNITY PLAZA (SITES 17,24,25A) | BROOKLYN | Enlarge Hopper Door | 3 | 0 | 0 | 2026 | [5 empty] | 22306.9305 | 17191207.772
UNITY PLAZA (SITES 4-27) | BROOKLYN | Enlarge Hopper Door | 12 | 0 | 0 | 2026 | [5 empty] | 89227.722 | 17280435.494
UNIVERSITY AVENUE REHAB | BRONX | Enlarge Hopper Door | 5 | 0 | 0 | [6 empty] | 37178.2175 | 17317613.7115
VAN DYKE I | BROOKLYN | Enlarge Hopper Door | 31 | 0 | 0 | 2024 | Yes |  |  |  |  | 230504.9485 | 17548118.66
VAN DYKE II | BROOKLYN | Enlarge Hopper Door | 1 | 0 | 0 | [6 empty] | 7435.6435 | 17555554.3035
WASHINGTON HEIGHTS REHAB (GROUPS 1&2) | MANHATTAN | Enlarge Hopper Door | 6 | 0 | 0 | 2019 | Yes |  |  |  |  | 0 | 17555554.3035
WASHINGTON HEIGHTS REHAB PHASE III (FORT WASHINGTON) | MANHATTAN | Enlarge Hopper Door | 3 | 0 | 0 | [6 empty] | 22306.9305 | 17577861.234
WASHINGTON HEIGHTS REHAB PHASE III (HARLEM RIVER) | MANHATTAN | Enlarge Hopper Door | 1 | 0 | 0 | [6 empty] | 7435.6435 | 17585296.8775
WASHINGTON HEIGHTS REHAB PHASE IV (C) | MANHATTAN | Enlarge Hopper Door | 2 | 0 | 0 | 2019 | Yes |  |  |  |  | 0 | 17585296.8775
WASHINGTON HEIGHTS REHAB PHASE IV (D) | MANHATTAN | Enlarge Hopper Door | 2 | 0 | 0 | 2019 | Yes |  |  |  |  | 0 | 17585296.8775
WEEKSVILLE GARDENS | BROOKLYN | Enlarge Hopper Door | 0 | 0 | 0 | 2019 | Yes |  |  |  |  | 0 | 17585296.8775
WEST BRIGHTON I | STATEN ISLAND | Enlarge Hopper Door | 8 | 0 | 0 | [6 empty] | 59485.148 | 17644782.0255
WEST BRIGHTON II | STATEN ISLAND | Enlarge Hopper Door | 0 | 0 | 0 | [6 empty] | 0 | 17644782.0255
WEST FARMS ROAD REHAB | BRONX | Enlarge Hopper Door | 7 | 0 | 0 | [6 empty] | 52049.5045 | 17696831.53
WEST FARMS SQUARE CONVENTIONAL | BRONX | Enlarge Hopper Door | 1 | 0 | 0 | [6 empty] | 7435.6435 | 17704267.1735
WHITMAN | BROOKLYN | Enlarge Hopper Door | 32 | 0 | 0 | [6 empty] | 237940.592 | 17942207.7655
WILLIAMS PLAZA | BROOKLYN | Enlarge Hopper Door | 5 | 0 | 0 | 2019 | Yes |  |  |  |  | 0 | 17942207.7655
WILLIAMSBURG | BROOKLYN | Enlarge Hopper Door | 134 | 0 | 0 | 2020 | Yes |  |  |  |  | 0 | 17942207.7655
WOODSIDE | QUEENS | Enlarge Hopper Door | 56 | 0 | 0 | [6 empty] | 416396.036 | 18358603.8015
WSUR (SITE C) 589 AMSTERDAM AVENUE | MANHATTAN | Enlarge Hopper Door | 2 | 0 | 0 | [6 empty] | 14871.287 | 18373475.0885
WYCKOFF GARDENS | BROOKLYN | Enlarge Hopper Door | 6 | 0 | 0 | [6 empty] | 44613.861 | 18418088.9495
BUSHWICK II (GROUPS A & C) | BROOKLYN | Enlarge Hopper Door | 25 | Zone 1 | 0 | [6 empty] | 185891.0875 | 18603980.037
BUSHWICK II CDA (GROUP E) | BROOKLYN | Enlarge Hopper Door | 0 | Zone 1 | 0 | 2019 | Yes |  |  |  |  | 0 | 18603980.037
HOPE GARDENS | BROOKLYN | Enlarge Hopper Door | 4 | Zone 1 | 0 | 2019 | Yes |  |  |  |  | 0 | 18603980.037
AMSTERDAM | MANHATTAN | Enlarge Hopper Door | 24 | Zone 4 | 0 | [6 empty] | 178455.444 | 18782435.481
CROWN HEIGHTS | BROOKLYN | Enlarge Hopper Door | 8 | Zone 4 | 0 | 2025 | [5 empty] | 59485.148 | 18841920.629
EAST 165TH STREET-BRYANT AVENUE | BRONX | Enlarge Hopper Door | 0 | Zone 4 | 0 | [6 empty] | 0 | 18841920.629
EAST 173RD STREET-VYSE AVENUE | BRONX | Enlarge Hopper Door | 0 | Zone 4 | 0 | [6 empty] | 0 | 18841920.629
FHA REPOSSESSED HOUSES (GROUP IX) | 0 | Enlarge Hopper Door | 0 | Zone 4 | 0 | [6 empty] | 0 | 18841920.629
FOREST | BRONX | Enlarge Hopper Door | 15 | Zone 4 | 0 | [6 empty] | 111534.6525 | 18953455.2815
HOWARD AVENUE-PARK PLACE | BROOKLYN | Enlarge Hopper Door | 0 | Zone 4 | 0 | 2025 | [5 empty] | 0 | 18953455.2815
MCKINLEY | BRONX | Enlarge Hopper Door | 5 | Zone 4 | 0 | [6 empty] | 37178.2175 | 18990633.499
REHAB PROGRAM (WISE REHAB) | MANHATTAN | Enlarge Hopper Door | 1 | Zone 4 | 0 | [6 empty] | 7435.6435 | 18998069.1425
THOMAS APARTMENTS | MANHATTAN | Enlarge Hopper Door | 1 | Zone 4 | 0 | [6 empty] | 7435.6435 | 19005504.786
WEST TREMONT AVENUE-SEDGWICK AVENUE AREA | BRONX | Enlarge Hopper Door | 1 | Zone 4 | 0 | [6 empty] | 7435.6435 | 19012940.4295
WISE TOWERS | MANHATTAN | Enlarge Hopper Door | 4 | Zone 4 | 0 | 2019 | Yes |  |  |  |  | 0 | 19012940.4295
WSUR (BROWNSTONES) | MANHATTAN | Enlarge Hopper Door | 0 | Zone 4 | 0 | [6 empty] | 0 | 19012940.4295
WSUR (SITE A) 120 WEST 94TH STREET | MANHATTAN | Enlarge Hopper Door | 1 | Zone 4 | 0 | [6 empty] | 7435.6435 | 19020376.073
WSUR (SITE B) 74 WEST 92ND STREET | MANHATTAN | Enlarge Hopper Door | 2 | Zone 4 | 0 | [6 empty] | 14871.287 | 19035247.36
Formulas:
Is RAD/PACT w/in 5yr = IF(EHD[[#This Row],[RAD/PACT]]="","",IF((EHD[[#This Row],[RAD/PACT]]-YEAR(TODAY()))<=5,"Yes",""))

## NRR Extension (hidden)
[8 empty] | 0 | #N/A | #N/A
BOROUGH | PROGRAM AREA | DEVELOPMENT | NRR | WORK TYPE | CALENDAR YEAR | FISCAL YEAR | STATUS | COST | ESTIMATES | RESOURCE
MANHATTAN |  | 335 EAST 111TH STREET | Pt III | [5 empty] | #N/A
MANHATTAN |  | AUDUBON | Pt III | [5 empty] | #N/A
MANHATTAN |  | BETHUNE GARDENS | Pt III | [5 empty] | #N/A
BROOKLYN |  | BORINQUEN PLAZA I | Pt III | [5 empty] | #N/A
BROOKLYN |  | BORINQUEN PLAZA II | Pt III | [5 empty] | #N/A
BRONX |  | BRONX RIVER | Pt III | [5 empty] | #N/A
BRONX |  | CLAREMONT PARKWAY-FRANKLIN AVENUE | Pt III | [5 empty] | #N/A
BRONX |  | DAVIDSON | Pt III | [5 empty] | #N/A
MANHATTAN |  | DOUGLASS ADDITION | Pt III | [5 empty] | #N/A
MANHATTAN |  | DOUGLASS I | Pt III | [5 empty] | #N/A
MANHATTAN |  | DOUGLASS II | Pt III | [5 empty] | #N/A
MANHATTAN |  | FORT WASHINGTON AVENUE REHAB | Pt III | [5 empty] | #N/A
MANHATTAN |  | FULTON | Pt III | [5 empty] | #N/A
MANHATTAN |  | GRAMPION | Pt III | [5 empty] | #N/A
MANHATTAN |  | HARLEM RIVER | Pt III | [5 empty] | #N/A
MANHATTAN |  | HARLEM RIVER II | Pt III | [5 empty] | #N/A
BROOKLYN |  | KINGSBOROUGH | Pt III | [5 empty] | #N/A
MANHATTAN |  | MANHATTANVILLE REHAB (GROUP 2) | Pt III | [5 empty] | #N/A
MANHATTAN |  | MANHATTANVILLE REHAB (GROUP 3) | Pt III | [5 empty] | #N/A
MANHATTAN |  | MARSHALL PLAZA | Pt III | [5 empty] | #N/A
BRONX |  | MONROE | Pt III | [5 empty] | #N/A
BRONX |  | MOORE | Pt III | [5 empty] | #N/A
MANHATTAN |  | PARK AVENUE-EAST 122ND, 123RD STREETS | Pt III | [5 empty] | #N/A
BRONX |  | PATTERSON | Pt III | [5 empty] | #N/A
MANHATTAN |  | PUBLIC SCHOOL 139 (CONVERSION) | Pt III | [5 empty] | #N/A
QUEENS |  | QUEENSBRIDGE NORTH | Pt III | [5 empty] | #N/A
QUEENS |  | QUEENSBRIDGE SOUTH | Pt III | [5 empty] | #N/A
BRONX |  | SOUTH BRONX AREA (SITE 402) | Pt III | [5 empty] | #N/A
BRONX |  | SAINT MARY'S PARK | Pt III | [5 empty] | #N/A
BRONX |  | STEBBINS AVENUE-HEWITT PLACE | Pt III | [5 empty] | #N/A
BRONX |  | UNION AVENUE-EAST 163RD STREET | Pt III | [5 empty] | #N/A
BRONX |  | UNION AVENUE-EAST 166TH STREET | Pt III | [5 empty] | #N/A
MANHATTAN |  | WASHINGTON HEIGHTS REHAB PHASE III | Pt III | [5 empty] | #N/A
MANHATTAN |  | LEHMAN VILLAGE | Pt II | Enlarge Hopper Door |  |  |  |  | 0
MANHATTAN |  | CLINTON | Pt II | Enlarge Hopper Door |  |  |  |  | 0
MANHATTAN |  | KING TOWERS | Pt II | Enlarge Hopper Door |  |  |  |  | 0
MANHATTAN |  | POLO GROUNDS TOWERS | Pt II | Enlarge Hopper Door |  |  |  |  | 0
MANHATTAN |  | WASHINGTON | Pt II | Enlarge Hopper Door |  |  |  |  | 0
MANHATTAN |  | LEXINGTON | Pt II | Enlarge Hopper Door |  |  |  |  | 0
MANHATTAN |  | UPACA (SITE 5) | Pt II | Enlarge Hopper Door |  |  |  |  | 0
MANHATTAN |  | UPACA (SITE 6) | Pt II | Enlarge Hopper Door |  |  |  |  | 0
MANHATTAN |  | WILSON | Pt II | Enlarge Hopper Door |  |  |  |  | 0
MANHATTAN |  | WAGNER | Pt II | Enlarge Hopper Door |  |  |  |  | 0
MANHATTAN |  | MANHATTANVILLE | Pt II | Enlarge Hopper Door |  |  |  |  | 0
MANHATTAN |  | CARVER | Pt II | Enlarge Hopper Door |  |  |  |  | 0
MANHATTAN |  | LINCOLN | Pt II | Enlarge Hopper Door |  |  |  |  | 0
MANHATTAN |  | RANGEL | Pt II | Enlarge Hopper Door |  |  |  |  | 0
MANHATTAN |  | JEFFERSON | Pt II | Enlarge Hopper Door |  |  |  |  | 0
MANHATTAN |  | DREW-HAMILTON | Pt II | Enlarge Hopper Door |  |  |  |  | 0
MANHATTAN |  | JOHNSON | Pt II | Enlarge Hopper Door |  |  |  |  | 0
MANHATTAN |  | SAINT NICHOLAS | Pt II | Enlarge Hopper Door |  |  |  |  | 0
MANHATTAN |  | EAST RIVER | Pt II | Enlarge Hopper Door |  |  |  |  | 0
MANHATTAN |  | TAFT | Pt II | Enlarge Hopper Door |  |  |  |  | 0
MANHATTAN |  | SAMUEL (CITY) | Pt II | Enlarge Hopper Door |  |  |  |  | 0
MANHATTAN |  | METRO NORTH PLAZA | Pt II | Enlarge Hopper Door |  |  |  |  | 0
MANHATTAN |  | GRANT | Pt II | Enlarge Hopper Door |  |  |  |  | 0
MANHATTAN |  | CORSI HOUSES | Pt II | Enlarge Hopper Door |  |  |  |  | 0
MANHATTAN |  | 131 SAINT NICHOLAS AVENUE | Pt II | Enlarge Hopper Door |  |  |  |  | 0
MANHATTAN |  | WHITE | Pt II | Enlarge Hopper Door |  |  |  |  | 0
MANHATTAN |  | ROBINSON | Pt II | Enlarge Hopper Door |  |  |  |  | 0
MANHATTAN |  | MORRIS PARK SENIOR CITIZENS HOME | Pt II | Enlarge Hopper Door |  |  |  |  | 0
MANHATTAN |  | CLINTON | Pt II | Cardboard Baler |  |  |  |  | 38885.4
MANHATTAN |  | KING TOWERS | Pt II | Cardboard Baler |  |  |  |  | 38885.4
MANHATTAN |  | POLO GROUNDS TOWERS | Pt II | Cardboard Baler |  |  |  |  | 38885.4
MANHATTAN |  | WAGNER | Pt II | Cardboard Baler |  |  |  |  | 38885.4
MANHATTAN |  | MANHATTANVILLE | Pt II | Cardboard Baler |  |  |  |  | 38885.4
MANHATTAN |  | CARVER | Pt II | Cardboard Baler |  |  |  |  | 38885.4
MANHATTAN |  | LINCOLN | Pt II | Cardboard Baler |  |  |  |  | 38885.4
MANHATTAN |  | RANGEL | Pt II | Cardboard Baler |  |  |  |  | 38885.4
MANHATTAN |  | JEFFERSON | Pt II | Cardboard Baler |  |  |  |  | 38885.4
MANHATTAN |  | DREW-HAMILTON | Pt II | Cardboard Baler |  |  |  |  | 38885.4
MANHATTAN |  | JOHNSON | Pt II | Cardboard Baler |  |  |  |  | 38885.4
MANHATTAN |  | SAINT NICHOLAS | Pt II | Cardboard Baler |  |  |  |  | 38885.4
MANHATTAN |  | EAST RIVER | Pt II | Cardboard Baler |  |  |  |  | 38885.4
MANHATTAN |  | TAFT | Pt II | Cardboard Baler |  |  |  |  | 38885.4
MANHATTAN |  | METRO NORTH PLAZA | Pt II | Cardboard Baler |  |  |  |  | 38885.4
MANHATTAN |  | GRANT | Pt II | Cardboard Baler |  |  |  |  | 38885.4
MANHATTAN |  | LEHMAN VILLAGE | Pt II | Interior Compactors |  |  |  |  | #N/A
MANHATTAN |  | CLINTON | Pt II | Interior Compactors |  |  |  |  | #N/A
MANHATTAN |  | KING TOWERS | Pt II | Interior Compactors |  |  |  |  | #N/A
MANHATTAN |  | POLO GROUNDS TOWERS | Pt II | Interior Compactors |  |  |  |  | #N/A
MANHATTAN |  | WASHINGTON | Pt II | Interior Compactors |  |  |  |  | #N/A
MANHATTAN |  | LEXINGTON | Pt II | Interior Compactors |  |  |  |  | #N/A
MANHATTAN |  | UPACA (SITE 5) | Pt II | Interior Compactors |  |  |  |  | #N/A
MANHATTAN |  | UPACA (SITE 6) | Pt II | Interior Compactors |  |  |  |  | #N/A
MANHATTAN |  | WILSON | Pt II | Interior Compactors |  |  |  |  | #N/A
MANHATTAN |  | WAGNER | Pt II | Interior Compactors |  |  |  |  | #N/A
MANHATTAN |  | MANHATTANVILLE | Pt II | Interior Compactors |  |  |  |  | #N/A
MANHATTAN |  | CARVER | Pt II | Interior Compactors |  |  |  |  | #N/A
MANHATTAN |  | LINCOLN | Pt II | Interior Compactors |  |  |  |  | #N/A
MANHATTAN |  | RANGEL | Pt II | Interior Compactors |  |  |  |  | #N/A
MANHATTAN |  | JEFFERSON | Pt II | Interior Compactors |  |  |  |  | #N/A
MANHATTAN |  | DREW-HAMILTON | Pt II | Interior Compactors |  |  |  |  | #N/A
MANHATTAN |  | JOHNSON | Pt II | Interior Compactors |  |  |  |  | #N/A
MANHATTAN |  | SAINT NICHOLAS | Pt II | Interior Compactors |  |  |  |  | #N/A
MANHATTAN |  | EAST RIVER | Pt II | Interior Compactors |  |  |  |  | #N/A
MANHATTAN |  | TAFT | Pt II | Interior Compactors |  |  |  |  | #N/A
MANHATTAN |  | SAMUEL (CITY) | Pt II | Interior Compactors |  |  |  |  | #N/A
MANHATTAN |  | METRO NORTH PLAZA | Pt II | Interior Compactors |  |  |  |  | #N/A
MANHATTAN |  | GRANT | Pt II | Interior Compactors |  |  |  |  | #N/A
MANHATTAN |  | CORSI HOUSES | Pt II | Interior Compactors |  |  |  |  | #N/A
MANHATTAN |  | 131 SAINT NICHOLAS AVENUE | Pt II | Interior Compactors |  |  |  |  | #N/A
MANHATTAN |  | WHITE | Pt II | Interior Compactors |  |  |  |  | #N/A
MANHATTAN |  | ROBINSON | Pt II | Interior Compactors |  |  |  |  | #N/A
MANHATTAN |  | MORRIS PARK SENIOR CITIZENS HOME | Pt II | Interior Compactors |  |  |  |  | #N/A
MANHATTAN |  | REHAB PROGRAM (TAFT REHABS) | Pt II | Interior Compactors |  |  |  |  | #N/A
MANHATTAN |  | LEHMAN VILLAGE | Pt II | Exterior Compactors |  |  |  |  | #N/A
MANHATTAN |  | CLINTON | Pt II | Exterior Compactors |  |  |  |  | #N/A
MANHATTAN |  | KING TOWERS | Pt II | Exterior Compactors |  |  |  |  | #N/A
MANHATTAN |  | POLO GROUNDS TOWERS | Pt II | Exterior Compactors |  |  |  |  | #N/A
MANHATTAN |  | WASHINGTON | Pt II | Exterior Compactors |  |  |  |  | #N/A
MANHATTAN |  | LEXINGTON | Pt II | Exterior Compactors |  |  |  |  | #N/A
MANHATTAN |  | UPACA (SITE 5) | Pt II | Exterior Compactors |  |  |  |  | #N/A
MANHATTAN |  | UPACA (SITE 6) | Pt II | Exterior Compactors |  |  |  |  | #N/A
MANHATTAN |  | WILSON | Pt II | Exterior Compactors |  |  |  |  | #N/A
MANHATTAN |  | WAGNER | Pt II | Exterior Compactors |  |  |  |  | #N/A
MANHATTAN |  | MANHATTANVILLE | Pt II | Exterior Compactors |  |  |  |  | #N/A
MANHATTAN |  | CARVER | Pt II | Exterior Compactors |  |  |  |  | #N/A
MANHATTAN |  | LINCOLN | Pt II | Exterior Compactors |  |  |  |  | #N/A
MANHATTAN |  | RANGEL | Pt II | Exterior Compactors |  |  |  |  | #N/A
MANHATTAN |  | JEFFERSON | Pt II | Exterior Compactors |  |  |  |  | #N/A
MANHATTAN |  | DREW-HAMILTON | Pt II | Exterior Compactors |  |  |  |  | #N/A
MANHATTAN |  | JOHNSON | Pt II | Exterior Compactors |  |  |  |  | #N/A
MANHATTAN |  | SAINT NICHOLAS | Pt II | Exterior Compactors |  |  |  |  | #N/A
MANHATTAN |  | EAST RIVER | Pt II | Exterior Compactors |  |  |  |  | #N/A
MANHATTAN |  | TAFT | Pt II | Exterior Compactors |  |  |  |  | #N/A
MANHATTAN |  | SAMUEL (CITY) | Pt II | Exterior Compactors |  |  |  |  | #N/A
MANHATTAN |  | METRO NORTH PLAZA | Pt II | Exterior Compactors |  |  |  |  | #N/A
MANHATTAN |  | GRANT | Pt II | Exterior Compactors |  |  |  |  | #N/A
MANHATTAN |  | CORSI HOUSES | Pt II | Exterior Compactors |  |  |  |  | #N/A
MANHATTAN |  | 131 SAINT NICHOLAS AVENUE | Pt II | Exterior Compactors |  |  |  |  | #N/A
MANHATTAN |  | WHITE | Pt II | Exterior Compactors |  |  |  |  | #N/A
MANHATTAN |  | ROBINSON | Pt II | Exterior Compactors |  |  |  |  | #N/A
MANHATTAN |  | MORRIS PARK SENIOR CITIZENS HOME | Pt II | Exterior Compactors |  |  |  |  | #N/A
MANHATTAN |  | REHAB PROGRAM (TAFT REHABS) | Pt II | Exterior Compactors |  |  |  |  | #N/A
MANHATTAN |  | CLINTON | Pt II | Bulk Crusher |  |  |  |  | 1307070
MANHATTAN |  | KING TOWERS | Pt II | Bulk Crusher |  |  |  |  | 1307070
MANHATTAN |  | POLO GROUNDS TOWERS | Pt II | Bulk Crusher |  |  |  |  | 1307070
MANHATTAN |  | WAGNER | Pt II | Bulk Crusher |  |  |  |  | 1307070
MANHATTAN |  | MANHATTANVILLE | Pt II | Bulk Crusher |  |  |  |  | 1307070
MANHATTAN |  | CARVER | Pt II | Bulk Crusher |  |  |  |  | 1307070
MANHATTAN |  | LINCOLN | Pt II | Bulk Crusher |  |  |  |  | 1307070
MANHATTAN |  | RANGEL | Pt II | Bulk Crusher |  |  |  |  | 1307070
MANHATTAN |  | JEFFERSON | Pt II | Bulk Crusher |  |  |  |  | 1307070
MANHATTAN |  | DREW-HAMILTON | Pt II | Bulk Crusher |  |  |  |  | 1307070
MANHATTAN |  | JOHNSON | Pt II | Bulk Crusher |  |  |  |  | 1307070
MANHATTAN |  | SAINT NICHOLAS | Pt II | Bulk Crusher |  |  |  |  | 1307070
MANHATTAN |  | EAST RIVER | Pt II | Bulk Crusher |  |  |  |  | 1307070
MANHATTAN |  | TAFT | Pt II | Bulk Crusher |  |  |  |  | 1307070
MANHATTAN |  | METRO NORTH PLAZA | Pt II | Bulk Crusher |  |  |  |  | 1307070
MANHATTAN |  | GRANT | Pt II | Bulk Crusher |  |  |  |  | 1307070
MANHATTAN |  | KING TOWERS | Pt II | Secondary collection areas |  |  |  |  | 133611.6
MANHATTAN |  | WASHINGTON | Pt II | Secondary collection areas |  |  |  |  | 133611.6
MANHATTAN |  | WAGNER | Pt II | Secondary collection areas |  |  |  |  | 133611.6
MANHATTAN |  | CARVER | Pt II | Secondary collection areas |  |  |  |  | 133611.6
MANHATTAN |  | LINCOLN | Pt II | Secondary collection areas |  |  |  |  | 133611.6
MANHATTAN |  | RANGEL | Pt II | Secondary collection areas |  |  |  |  | 133611.6
MANHATTAN |  | JEFFERSON | Pt II | Secondary collection areas |  |  |  |  | 133611.6
MANHATTAN |  | JOHNSON | Pt II | Secondary collection areas |  |  |  |  | 133611.6
MANHATTAN |  | SAINT NICHOLAS | Pt II | Secondary collection areas |  |  |  |  | 133611.6
MANHATTAN |  | EAST RIVER | Pt II | Secondary collection areas |  |  |  |  | 133611.6
MANHATTAN |  | TAFT | Pt II | Secondary collection areas |  |  |  |  | 133611.6
MANHATTAN |  | GRANT | Pt II | Secondary collection areas |  |  |  |  | 133611.6
MANHATTAN |  | CLINTON | Pt II | Mattress Recycling |  |  |  |  | 13656
MANHATTAN |  | KING TOWERS | Pt II | Mattress Recycling |  |  |  |  | 13656
MANHATTAN |  | POLO GROUNDS TOWERS | Pt II | Mattress Recycling |  |  |  |  | 13656
MANHATTAN |  | WAGNER | Pt II | Mattress Recycling |  |  |  |  | 13656
MANHATTAN |  | MANHATTANVILLE | Pt II | Mattress Recycling |  |  |  |  | 13656
MANHATTAN |  | CARVER | Pt II | Mattress Recycling |  |  |  |  | 13656
MANHATTAN |  | LINCOLN | Pt II | Mattress Recycling |  |  |  |  | 13656
MANHATTAN |  | RANGEL | Pt II | Mattress Recycling |  |  |  |  | 13656
MANHATTAN |  | JEFFERSON | Pt II | Mattress Recycling |  |  |  |  | 13656
MANHATTAN |  | DREW-HAMILTON | Pt II | Mattress Recycling |  |  |  |  | 13656
MANHATTAN |  | JOHNSON | Pt II | Mattress Recycling |  |  |  |  | 13656
MANHATTAN |  | SAINT NICHOLAS | Pt II | Mattress Recycling |  |  |  |  | 13656
MANHATTAN |  | EAST RIVER | Pt II | Mattress Recycling |  |  |  |  | 13656
MANHATTAN |  | TAFT | Pt II | Mattress Recycling |  |  |  |  | 13656
MANHATTAN |  | METRO NORTH PLAZA | Pt II | Mattress Recycling |  |  |  |  | 13656
MANHATTAN |  | GRANT | Pt II | Mattress Recycling |  |  |  |  | 13656
MANHATTAN |  | KING TOWERS | Pt II | Electric Tilt Truck |  |  |  |  | 37000
MANHATTAN |  | WAGNER | Pt II | Electric Tilt Truck |  |  |  |  | 37000
MANHATTAN |  | CARVER | Pt II | Electric Tilt Truck |  |  |  |  | 37000
MANHATTAN |  | LINCOLN | Pt II | Electric Tilt Truck |  |  |  |  | 37000
MANHATTAN |  | RANGEL | Pt II | Electric Tilt Truck |  |  |  |  | 37000
MANHATTAN |  | JEFFERSON | Pt II | Electric Tilt Truck |  |  |  |  | 37000
MANHATTAN |  | JOHNSON | Pt II | Electric Tilt Truck |  |  |  |  | 37000
MANHATTAN |  | SAINT NICHOLAS | Pt II | Electric Tilt Truck |  |  |  |  | 37000
MANHATTAN |  | EAST RIVER | Pt II | Electric Tilt Truck |  |  |  |  | 37000
MANHATTAN |  | TAFT | Pt II | Electric Tilt Truck |  |  |  |  | 37000
MANHATTAN |  | GRANT | Pt II | Electric Tilt Truck |  |  |  |  | 37000

## year pivot (hidden)
|  |  | total sum | 27545858.6263
|  |  | 2019 | 3170880.55
Row Labels | Sum of COST | Sum of ESTIMATES | 2020 | 8554799.0213
2019 | 3170880.55 |  | 2021 | 5442349.02
Enlarge Hopper Door | 1467376.8 |  | 2022 | 2712097.635
BUSHWICK | 44243.94 |  | 2023 | 3228462.9
BUTLER | 44405.061 |  | 2024 | 4436776.5
CLAREMONT REHAB (GROUP 3) | 59206.748 |  | 2025 | #REF!
CLAREMONT REHAB (GROUP 4) | 66607.5915 |  | 2026 | #REF!
JACKSON | 51805.9045 |  | 2027 | #REF!
LA GUARDIA | 56519.89 |  | 2028 | #REF!
LAFAYETTE | 51805.9045 |  | 2029 | #REF!
MARCY | 518059.045 |  | 2030 | #REF!
MELROSE | 59206.748
MORRIS I | 66607.5915
MORRISANIA AIR RIGHTS | 37004.2175
ROOSEVELT I | 44405.061
RUTGERS | 32007.26
SMITH | 74933.74
SUMNER | 148620.14
TOMPKINS | 74933.74
WEBSTER | 37004.2175
Food Waste Disposer | 1703503.75
BARUCH HOUSES ADDITION | 607266.52
MELTZER TOWER | 534717.81
TWO BRIDGES URA (SITE 7) | 561519.42
2020 |  | 8554799.0213
Cardboard Baler |  | 111996.72
LA GUARDIA |  | 37332.24
RIIS |  | 37332.24
VLADECK |  | 37332.24
Enlarge Hopper Door |  | 510658.2015
45 ALLEN STREET |  | 7400.8435
BARUCH |  | 125814.3395
BRACETTI PLAZA |  | 14801.687
CAMPOS PLAZA II |  | 22202.5305
GOMPERS |  | 29603.374
LOWER EAST SIDE I INFILL |  | 7400.8435
LOWER EAST SIDE II |  | 7400.8435
LOWER EAST SIDE REHAB (GROUP 5) |  | 22202.5305
RIIS |  | 133215.183
SEWARD PARK EXTENSION |  | 14801.687
TWO BRIDGES URA (SITE 7) |  | 7400.8435
WALD |  | 118413.496
Exterior Compactors |  | 2762129.37
131 SAINT NICHOLAS AVENUE |  | 0
335 EAST 111TH STREET |  | 0
AUDUBON |  | 0
BETHUNE GARDENS |  | 0
BORINQUEN PLAZA II |  | 0
BRONX RIVER |  | 586220.895
CORSI HOUSES |  | 0
DOUGLASS ADDITION |  | 0
DOUGLASS II |  | 0
DREW-HAMILTON |  | 390813.93
EAST RIVER |  | 0
FORT WASHINGTON AVENUE REHAB |  | 0
GRAMPION |  | 0
GRANT |  | 781627.86
HARLEM RIVER II |  | 0
JOHNSON |  | 390813.93
KINGSBOROUGH |  | 0
LA GUARDIA |  | 417245.79
MANHATTANVILLE REHAB (GROUP 2) |  | 0
MANHATTANVILLE REHAB (GROUP 3) |  | 0
MARSHALL PLAZA |  | 0
METRO NORTH PLAZA |  | 0
MOORE |  | 195406.965
MORRIS PARK SENIOR CITIZENS HOME |  | 0
PARK AVENUE-EAST 122ND, 123RD STREETS |  | 0
PUBLIC SCHOOL 139 (CONVERSION) |  | 0
SAMUEL (CITY) |  | 0
SOUTH BRONX AREA (SITE 402) |  | 0
STEBBINS AVENUE-HEWITT PLACE |  | 0
UNION AVENUE-EAST 163RD STREET |  | 0
UNION AVENUE-EAST 166TH STREET |  | 0
UPACA (SITE 6) |  | 0
WASHINGTON HEIGHTS REHAB PHASE III |  | 0
WHITE |  | 0
Food Waste Disposer |  | 5169957.7298
LA GUARDIA |  | 1875140.9186
LA GUARDIA ADDITION |  | 256091.6562
RIIS |  | 2047014.5133
RIIS II |  | 991710.6416
Interior Compactors |  | 57
LOWER EAST SIDE I INFILL |  | 1
SEWARD PARK EXTENSION |  | 2
VLADECK |  | 46
VLADECK II |  | 8
2021 |  | 5442349.02
Bulk Crusher |  | 2614140
LA GUARDIA |  | 1307070
RIIS |  | 1307070
Exterior Compactors |  | 2828209.02
FULTON |  | 404029.86
JEFFERSON |  | 606044.79
LINCOLN |  | 404029.86
MELROSE |  | 0
MONROE |  | 404029.86
RANGEL |  | 606044.79
WILSON |  | 404029.86
2022 |  | 2712097.635
Exterior Compactors |  | 2712097.635
303 VERNON AVENUE |  | 208622.895
BORINQUEN PLAZA I |  | 417245.79
CARVER |  | 625868.685
DAVIDSON |  | 208622.895
EAST 180TH STREET-MONTEREY AVENUE |  | 208622.895
MANHATTANVILLE |  | 625868.685
SAINT MARY'S PARK |  | 417245.79
2023 |  | 3228462.9
Exterior Compactors |  | 3228462.9
CLAREMONT PARKWAY-FRANKLIN AVENUE |  | 215230.86
HARLEM RIVER |  | 0
LEXINGTON |  | 0
QUEENSBRIDGE NORTH |  | 645692.58
ROBINSON |  | 430461.72
UPACA (SITE 5) |  | 430461.72
WAGNER |  | 1076154.3
WEBSTER |  | 430461.72
2024 |  | 4436776.5
Exterior Compactors |  | 4436776.5
CLINTON |  | 443677.65
DOUGLASS I |  | 665516.475
KING TOWERS |  | 443677.65
PATTERSON |  | 0
POLO GROUNDS TOWERS |  | 665516.475
QUEENSBRIDGE SOUTH |  | 665516.475
SAINT NICHOLAS |  | 665516.475
TAFT |  | 887355.3
WASHINGTON |  | 0
113 |  | 1
Interior Compactors |  | 1
DAVIDSON |  | 1
59 |  | 2
Interior Compactors |  | 2
PARK AVENUE-EAST 122ND, 123RD STREETS |  | 0
ROBINSON |  | 2
112 |  | 0
Interior Compactors |  | 0
PUBLIC SCHOOL 139 (CONVERSION) |  | 0
2 |  | 0
Interior Compactors |  | 0
SOUTH BRONX AREA (SITE 402) |  | 0
STEBBINS AVENUE-HEWITT PLACE |  | 0
UNION AVENUE-EAST 166TH STREET |  | 0
WASHINGTON HEIGHTS REHAB PHASE III |  | 0
166 |  | 1
Interior Compactors |  | 1
335 EAST 111TH STREET |  | 1
165 |  | 1
Interior Compactors |  | 1
CORSI HOUSES |  | 1
128 |  | 0
Interior Compactors |  | 0
GRAMPION |  | 0
164 |  | 0
Interior Compactors |  | 0
HARLEM RIVER |  | 0
202 |  | 0
Interior Compactors |  | 0
HARLEM RIVER II |  | 0
207 |  | 1
Interior Compactors |  | 1
131 SAINT NICHOLAS AVENUE |  | 1
206 |  | 3
Interior Compactors |  | 3
CLAREMONT PARKWAY-FRANKLIN AVENUE |  | 3
232 |  | 2
Interior Compactors |  | 2
EAST 180TH STREET-MONTEREY AVENUE |  | 2
277 |  | 35
Interior Compactors |  | 35
KINGSBOROUGH |  | 35
216 |  | 9
Interior Compactors |  | 9
RANGEL |  | 9
203 |  | 1
Interior Compactors |  | 1
WHITE |  | 1
379 |  | 6
Interior Compactors |  | 6
BUTLER |  | 6
373 |  | 17
Interior Compactors |  | 17
JOHNSON |  | 17
356 |  | 18
Interior Compactors |  | 18
TAFT |  | 18
416 |  | 6
Interior Compactors |  | 6
SAINT MARY'S PARK |  | 6
401 |  | 22
Interior Compactors |  | 22
WAGNER |  | 22
580 |  | 6
Interior Compactors |  | 6
CLINTON |  | 6
574 |  | 20
Interior Compactors |  | 20
LINCOLN |  | 20
554 |  | 1
Interior Compactors |  | 1
MORRIS PARK SENIOR CITIZENS HOME |  | 1
672 |  | 8
Interior Compactors |  | 8
BUSHWICK |  | 8
664 |  | 34
Interior Compactors |  | 34
JEFFERSON |  | 34
590 |  | 10
Interior Compactors |  | 10
KING TOWERS |  | 10
630 |  | 40
Interior Compactors |  | 40
SAMUEL (CITY) |  | 40
708 |  | 3
Interior Compactors |  | 3
METRO NORTH PLAZA |  | 3
705 |  | 18
Interior Compactors |  | 18
MONROE |  | 18
687 |  | 14
Interior Compactors |  | 14
SAINT NICHOLAS |  | 14
938 |  | 11
Interior Compactors |  | 11
DOUGLASS I |  | 11
927 |  | 6
Interior Compactors |  | 6
DOUGLASS II |  | 6
1001 |  | 13
Interior Compactors |  | 13
BETHUNE GARDENS |  | 0
CARVER |  | 13
1010 |  | 1
Interior Compactors |  | 1
DOUGLASS ADDITION |  | 1
1053 |  | 5
Interior Compactors |  | 5
DREW-HAMILTON |  | 5
1048 |  | 19
Interior Compactors |  | 19
FULTON |  | 19
988 |  | 4
Interior Compactors |  | 4
MOORE |  | 4
1029 |  | 1
Interior Compactors |  | 1
UNION AVENUE-EAST 163RD STREET |  | 1
1249 |  | 49
Interior Compactors |  | 49
QUEENSBRIDGE SOUTH |  | 49
1305 |  | 9
Interior Compactors |  | 9
BRONX RIVER |  | 9
1296 |  | 47
Interior Compactors |  | 47
QUEENSBRIDGE NORTH |  | 47
1686 |  | 1
Interior Compactors |  | 1
MANHATTANVILLE REHAB (GROUP 2) |  | 0
MANHATTANVILLE REHAB (GROUP 3) |  | 0
TWIN PARKS EAST (SITE 9) |  | 1
1633 |  | 3
Interior Compactors |  | 3
WILSON |  | 3
1759 |  | 8
Interior Compactors |  | 8
POLO GROUNDS TOWERS |  | 8
1751 |  | 1
Interior Compactors |  | 1
UPACA (SITE 5) |  | 1
1750 |  | 1
Interior Compactors |  | 1
UPACA (SITE 6) |  | 1
1901 |  | 8
Interior Compactors |  | 8
AUDUBON |  | 0
BORINQUEN PLAZA I |  | 8
1908 |  | 7
Interior Compactors |  | 7
BORINQUEN PLAZA II |  | 7
FORT WASHINGTON AVENUE REHAB |  | 0
MARSHALL PLAZA |  | 0
1871 |  | 6
Interior Compactors |  | 6
LEXINGTON |  | 0
MANHATTANVILLE |  | 6
1847 |  | 0
Interior Compactors |  | 0
WASHINGTON |  | 0
1942 |  | 9
Interior Compactors |  | 9
EAST RIVER |  | 0
GRANT |  | 9
1933 |  | 5
Interior Compactors |  | 5
PATTERSON |  | 0
WEBSTER |  | 5
Grand Total | 3170880.55 | 24374978.0763

## borough pivot (hidden)
|  |  | total | 60805792.0941
|  |  | Bronx | 5976701.2365
Row Labels | Sum of COST | Sum of ESTIMATES | Brooklyn | 7959173.0748
BRONX | 421848.0795 | 5554853.157 | Manhattan | 45558612.7278
Bulk Crusher |  | 2614140 | Queens | 1311305.055
MORRIS II |  | 1307070 | Staten Island
WEBSTER |  | 1307070
Cardboard Baler |  | 111996.72
MELROSE |  | 0
MORRIS I |  | 37332.24
MORRISANIA AIR RIGHTS |  | 37332.24
WEBSTER |  | 37332.24
Enlarge Hopper Door | 421848.0795 | 162818.557
BUTLER | 44405.061
CLAREMONT REHAB (GROUP 2) |  | 29603.374
CLAREMONT REHAB (GROUP 3) | 59206.748
CLAREMONT REHAB (GROUP 4) | 66607.5915
CLAREMONT REHAB (GROUP 5) |  | 22202.5305
COLLEGE AVENUE-EAST 165TH STREET |  | 7400.8435
EAST 180TH STREET-MONTEREY AVENUE |  | 14801.687
JACKSON | 51805.9045
MELROSE | 59206.748
MORRIS I | 66607.5915
MORRIS II |  | 59206.748
MORRISANIA |  | 14801.687
MORRISANIA AIR RIGHTS | 37004.2175
TELLER AVENUE-EAST 166TH STREET |  | 14801.687
WEBSTER | 37004.2175
Exterior Compactors |  | 2665841.88
EAST 180TH STREET-MONTEREY AVENUE |  | 208622.895
MELROSE |  | 0
WEBSTER |  | 430461.72
BRONX RIVER |  | 586220.895
CLAREMONT PARKWAY-FRANKLIN AVENUE |  | 215230.86
DAVIDSON |  | 208622.895
MONROE |  | 404029.86
MOORE |  | 195406.965
PATTERSON |  | 0
SAINT MARY'S PARK |  | 417245.79
SOUTH BRONX AREA (SITE 402) |  | 0
STEBBINS AVENUE-HEWITT PLACE |  | 0
UNION AVENUE-EAST 163RD STREET |  | 0
UNION AVENUE-EAST 166TH STREET |  | 0
Interior Compactors |  | 56
BUTLER |  | 6
EAST 180TH STREET-MONTEREY AVENUE |  | 2
TWIN PARKS EAST (SITE 9) |  | 1
WEBSTER |  | 5
BRONX RIVER |  | 9
CLAREMONT PARKWAY-FRANKLIN AVENUE |  | 3
DAVIDSON |  | 1
MONROE |  | 18
MOORE |  | 4
PATTERSON |  | 0
SAINT MARY'S PARK |  | 6
SOUTH BRONX AREA (SITE 402) |  | 0
STEBBINS AVENUE-HEWITT PLACE |  | 0
UNION AVENUE-EAST 163RD STREET |  | 1
UNION AVENUE-EAST 166TH STREET |  | 0
BROOKLYN | 882067.8305 | 7077105.2443
Bulk Crusher |  | 1307070
MARCY |  | 1307070
Cardboard Baler |  | 111996.72
MARCY |  | 37332.24
ROOSEVELT I |  | 37332.24
SUMNER |  | 37332.24
Enlarge Hopper Door | 882067.8305 | 74008.435
303 VERNON AVENUE |  | 7400.8435
BEDFORD-STUYVESANT REHAB |  | 37004.2175
BUSHWICK | 44243.94
HYLAN |  | 7400.8435
LAFAYETTE | 51805.9045
MARCY | 518059.045
ROOSEVELT I | 44405.061
ROOSEVELT II |  | 22202.5305
SUMNER | 148620.14
TOMPKINS | 74933.74
Exterior Compactors |  | 625868.685
303 VERNON AVENUE |  | 208622.895
BORINQUEN PLAZA I |  | 417245.79
BORINQUEN PLAZA II |  | 0
KINGSBOROUGH |  | 0
Food Waste Disposer |  | 4824491.8043
HYLAN |  | 359215.813
LAFAYETTE |  | 1515925.1056
MARCY |  | 2949350.8857
Interior Compactors |  | 58
BUSHWICK |  | 8
BORINQUEN PLAZA I |  | 8
BORINQUEN PLAZA II |  | 7
KINGSBOROUGH |  | 35
Secondary collection areas |  | 133611.6
MARCY |  | 133611.6
MANHATTAN | 1866964.64 | 43691648.0878
Bulk Crusher |  | 22220190
LA GUARDIA |  | 1307070
RIIS |  | 1307070
CARVER |  | 1307070
CLINTON |  | 1307070
DREW-HAMILTON |  | 1307070
EAST RIVER |  | 0
GRANT |  | 1307070
JEFFERSON |  | 1307070
JOHNSON |  | 1307070
KING TOWERS |  | 1307070
LINCOLN |  | 1307070
MANHATTANVILLE |  | 1307070
METRO NORTH PLAZA |  | 1307070
POLO GROUNDS TOWERS |  | 1307070
RANGEL |  | 1307070
SAINT NICHOLAS |  | 1307070
TAFT |  | 1307070
WAGNER |  | 1307070
Cardboard Baler |  | 671980.32
LA GUARDIA |  | 37332.24
RIIS |  | 37332.24
VLADECK |  | 37332.24
CARVER |  | 37332.24
CLINTON |  | 37332.24
DREW-HAMILTON |  | 37332.24
EAST RIVER |  | 0
GRANT |  | 37332.24
JEFFERSON |  | 37332.24
JOHNSON |  | 37332.24
KING TOWERS |  | 37332.24
LINCOLN |  | 37332.24
MANHATTANVILLE |  | 37332.24
METRO NORTH PLAZA |  | 37332.24
POLO GROUNDS TOWERS |  | 37332.24
RANGEL |  | 37332.24
SAINT NICHOLAS |  | 37332.24
TAFT |  | 37332.24
WAGNER |  | 37332.24
Enlarge Hopper Door | 163460.89 | 2353468.233
45 ALLEN STREET |  | 7400.8435
BARUCH |  | 125814.3395
BRACETTI PLAZA |  | 14801.687
CAMPOS PLAZA II |  | 22202.5305
GOMPERS |  | 29603.374
LA GUARDIA | 56519.89
LOWER EAST SIDE I INFILL |  | 7400.8435
LOWER EAST SIDE II |  | 7400.8435
LOWER EAST SIDE REHAB (GROUP 5) |  | 22202.5305
RIIS |  | 133215.183
RUTGERS | 32007.26
SEWARD PARK EXTENSION |  | 14801.687
SMITH | 74933.74
TWO BRIDGES URA (SITE 7) |  | 7400.8435
WALD |  | 118413.496
CARVER |  | 96210.9655
CLINTON |  | 44405.061
DREW-HAMILTON |  | 37004.2175
EAST RIVER |  | 0
GRANT |  | 66607.5915
JEFFERSON |  | 251628.679
JOHNSON |  | 125814.3395
KING TOWERS |  | 74008.435
LINCOLN |  | 148016.87
MANHATTANVILLE |  | 44405.061
METRO NORTH PLAZA |  | 22202.5305
POLO GROUNDS TOWERS |  | 59206.748
RANGEL |  | 66607.5915
SAINT NICHOLAS |  | 103611.809
TAFT |  | 133215.183
WAGNER |  | 162818.557
131 SAINT NICHOLAS AVENUE |  | 7400.8435
CORSI HOUSES |  | 7400.8435
LEHMAN VILLAGE |  | 29603.374
LEXINGTON |  | 0
MORRIS PARK SENIOR CITIZENS HOME |  | 7400.8435
ROBINSON |  | 14801.687
SAMUEL (CITY) |  | 296033.74
UPACA (SITE 5) |  | 7400.8435
UPACA (SITE 6) |  | 7400.8435
WASHINGTON |  | 0
WHITE |  | 7400.8435
WILSON |  | 22202.5305
Exterior Compactors |  | 11364755.805
LA GUARDIA |  | 417245.79
CARVER |  | 625868.685
CLINTON |  | 443677.65
DREW-HAMILTON |  | 390813.93
EAST RIVER |  | 0
GRANT |  | 781627.86
JEFFERSON |  | 606044.79
JOHNSON |  | 390813.93
KING TOWERS |  | 443677.65
LINCOLN |  | 404029.86
MANHATTANVILLE |  | 625868.685
METRO NORTH PLAZA |  | 0
POLO GROUNDS TOWERS |  | 665516.475
RANGEL |  | 606044.79
SAINT NICHOLAS |  | 665516.475
TAFT |  | 887355.3
WAGNER |  | 1076154.3
131 SAINT NICHOLAS AVENUE |  | 0
CORSI HOUSES |  | 0
LEXINGTON |  | 0
MORRIS PARK SENIOR CITIZENS HOME |  | 0
ROBINSON |  | 430461.72
SAMUEL (CITY) |  | 0
UPACA (SITE 5) |  | 430461.72
UPACA (SITE 6) |  | 0
WASHINGTON |  | 0
WHITE |  | 0
WILSON |  | 404029.86
335 EAST 111TH STREET |  | 0
AUDUBON |  | 0
BETHUNE GARDENS |  | 0
DOUGLASS ADDITION |  | 0
DOUGLASS I |  | 665516.475
DOUGLASS II |  | 0
FORT WASHINGTON AVENUE REHAB |  | 0
FULTON |  | 404029.86
GRAMPION |  | 0
HARLEM RIVER |  | 0
HARLEM RIVER II |  | 0
MANHATTANVILLE REHAB (GROUP 2) |  | 0
MANHATTANVILLE REHAB (GROUP 3) |  | 0
MARSHALL PLAZA |  | 0
PARK AVENUE-EAST 122ND, 123RD STREETS |  | 0
PUBLIC SCHOOL 139 (CONVERSION) |  | 0
WASHINGTON HEIGHTS REHAB PHASE III |  | 0
Food Waste Disposer | 1703503.75 | 5169957.7298
BARUCH HOUSES ADDITION | 607266.52
LA GUARDIA |  | 1875140.9186
LA GUARDIA ADDITION |  | 256091.6562
MELTZER TOWER | 534717.81
RIIS |  | 2047014.5133
RIIS II |  | 991710.6416
TWO BRIDGES URA (SITE 7) | 561519.42
Interior Compactors |  | 340
LOWER EAST SIDE I INFILL |  | 1
SEWARD PARK EXTENSION |  | 2
VLADECK |  | 46
VLADECK II |  | 8
CARVER |  | 13
CLINTON |  | 6
DREW-HAMILTON |  | 5
EAST RIVER |  | 0
GRANT |  | 9
JEFFERSON |  | 34
JOHNSON |  | 17
KING TOWERS |  | 10
LINCOLN |  | 20
MANHATTANVILLE |  | 6
METRO NORTH PLAZA |  | 3
POLO GROUNDS TOWERS |  | 8
RANGEL |  | 9
SAINT NICHOLAS |  | 14
TAFT |  | 18
WAGNER |  | 22
131 SAINT NICHOLAS AVENUE |  | 1
CORSI HOUSES |  | 1
LEXINGTON |  | 0
MORRIS PARK SENIOR CITIZENS HOME |  | 1
ROBINSON |  | 2
SAMUEL (CITY) |  | 40
UPACA (SITE 5) |  | 1
UPACA (SITE 6) |  | 1
WASHINGTON |  | 0
WHITE |  | 1
WILSON |  | 3
335 EAST 111TH STREET |  | 1
AUDUBON |  | 0
BETHUNE GARDENS |  | 0
DOUGLASS ADDITION |  | 1
DOUGLASS I |  | 11
DOUGLASS II |  | 6
FORT WASHINGTON AVENUE REHAB |  | 0
FULTON |  | 19
GRAMPION |  | 0
HARLEM RIVER |  | 0
HARLEM RIVER II |  | 0
MANHATTANVILLE REHAB (GROUP 2) |  | 0
MANHATTANVILLE REHAB (GROUP 3) |  | 0
MARSHALL PLAZA |  | 0
PARK AVENUE-EAST 122ND, 123RD STREETS |  | 0
PUBLIC SCHOOL 139 (CONVERSION) |  | 0
WASHINGTON HEIGHTS REHAB PHASE III |  | 0
Secondary collection areas |  | 1336116
CARVER |  | 133611.6
EAST RIVER |  | 0
GRANT |  | 133611.6
JEFFERSON |  | 133611.6
JOHNSON |  | 133611.6
KING TOWERS |  | 133611.6
LINCOLN |  | 133611.6
RANGEL |  | 133611.6
SAINT NICHOLAS |  | 133611.6
TAFT |  | 133611.6
WAGNER |  | 133611.6
WASHINGTON |  | 0
Electric Tilt Truck |  | 370000
CARVER |  | 37000
EAST RIVER |  | 0
GRANT |  | 37000
JEFFERSON |  | 37000
JOHNSON |  | 37000
KING TOWERS |  | 37000
LINCOLN |  | 37000
RANGEL |  | 37000
SAINT NICHOLAS |  | 37000
TAFT |  | 37000
WAGNER |  | 37000
Mattress Recycling |  | 204840
CARVER |  | 13656
CLINTON |  | 13656
DREW-HAMILTON |  | 13656
EAST RIVER |  | 0
GRANT |  | 13656
JEFFERSON |  | 13656
JOHNSON |  | 13656
KING TOWERS |  | 13656
LINCOLN |  | 13656
MANHATTANVILLE |  | 13656
METRO NORTH PLAZA |  | 13656
POLO GROUNDS TOWERS |  | 13656
RANGEL |  | 13656
SAINT NICHOLAS |  | 13656
TAFT |  | 13656
WAGNER |  | 13656
QUEENS |  | 1311305.055
Exterior Compactors |  | 1311209.055
QUEENSBRIDGE NORTH |  | 645692.58
QUEENSBRIDGE SOUTH |  | 665516.475
Interior Compactors |  | 96
QUEENSBRIDGE NORTH |  | 47
QUEENSBRIDGE SOUTH |  | 49
Grand Total | 3170880.55 | 57634911.5441

## NRR round pivot (hidden)
|  |  | sum | 60805792.0941
|  |  | NRR Pt I | 22182799.3376
Row Labels | Sum of COST | Sum of ESTIMATES | Harlem Ext. | 33768404.9375
Pt I | 3170880.55 | 19011918.7876 | NRR Ext. | 4824984.445
303 VERNON AVENUE |  | 216023.7385
45 ALLEN STREET |  | 7400.8435
BARUCH |  | 125814.3395
BARUCH HOUSES ADDITION | 607266.52
BEDFORD-STUYVESANT REHAB |  | 37004.2175
BRACETTI PLAZA |  | 14801.687
BUSHWICK | 44243.94 | 8
BUTLER | 44405.061 | 6
CAMPOS PLAZA II |  | 22202.5305
CLAREMONT REHAB (GROUP 2) |  | 29603.374
CLAREMONT REHAB (GROUP 3) | 59206.748
CLAREMONT REHAB (GROUP 4) | 66607.5915
CLAREMONT REHAB (GROUP 5) |  | 22202.5305
COLLEGE AVENUE-EAST 165TH STREET |  | 7400.8435
EAST 180TH STREET-MONTEREY AVENUE |  | 223426.582
GOMPERS |  | 29603.374
HYLAN |  | 366616.6565
JACKSON | 51805.9045
LA GUARDIA | 56519.89 | 3636788.9486
LA GUARDIA ADDITION |  | 256091.6562
LAFAYETTE | 51805.9045 | 1515925.1056
LOWER EAST SIDE I INFILL |  | 7401.8435
LOWER EAST SIDE II |  | 7400.8435
LOWER EAST SIDE REHAB (GROUP 5) |  | 22202.5305
MARCY | 518059.045 | 4427364.7257
MELROSE | 59206.748 | 0
MELTZER TOWER | 534717.81
MORRIS I | 66607.5915 | 37332.24
MORRIS II |  | 1366276.748
MORRISANIA |  | 14801.687
MORRISANIA AIR RIGHTS | 37004.2175 | 37332.24
RIIS |  | 3524631.9363
RIIS II |  | 991710.6416
ROOSEVELT I | 44405.061 | 37332.24
ROOSEVELT II |  | 22202.5305
RUTGERS | 32007.26
SEWARD PARK EXTENSION |  | 14803.687
SMITH | 74933.74
SUMNER | 148620.14 | 37332.24
TELLER AVENUE-EAST 166TH STREET |  | 14801.687
TOMPKINS | 74933.74
TWIN PARKS EAST (SITE 9) |  | 1
TWO BRIDGES URA (SITE 7) | 561519.42 | 7400.8435
VLADECK |  | 37378.24
VLADECK II |  | 8
WALD |  | 118413.496
WEBSTER | 37004.2175 | 1774868.96
Pt II |  | 33768404.9375
CARVER |  | 2250762.4905
CLINTON |  | 1846146.951
DREW-HAMILTON |  | 1785881.3875
EAST RIVER |  | 0
GRANT |  | 2376914.2915
JEFFERSON |  | 2386377.309
JOHNSON |  | 2045315.1095
KING TOWERS |  | 2046365.925
LINCOLN |  | 2080736.57
MANHATTANVILLE |  | 2028337.986
METRO NORTH PLAZA |  | 1380263.7705
POLO GROUNDS TOWERS |  | 2082789.463
RANGEL |  | 2201331.2215
SAINT NICHOLAS |  | 2297812.124
TAFT |  | 2549258.323
WAGNER |  | 2767664.697
131 SAINT NICHOLAS AVENUE |  | 7401.8435
CORSI HOUSES |  | 7401.8435
LEXINGTON |  | 0
MORRIS PARK SENIOR CITIZENS HOME |  | 7401.8435
ROBINSON |  | 445265.407
SAMUEL (CITY) |  | 296073.74
UPACA (SITE 5) |  | 437863.5635
UPACA (SITE 6) |  | 7401.8435
WASHINGTON |  | 0
WHITE |  | 7401.8435
WILSON |  | 426235.3905
Pt III |  | 4824984.445
335 EAST 111TH STREET |  | 1
AUDUBON |  | 0
BETHUNE GARDENS |  | 0
BORINQUEN PLAZA I |  | 417253.79
BORINQUEN PLAZA II |  | 7
BRONX RIVER |  | 586229.895
CLAREMONT PARKWAY-FRANKLIN AVENUE |  | 215233.86
DAVIDSON |  | 208623.895
DOUGLASS ADDITION |  | 1
DOUGLASS I |  | 665527.475
DOUGLASS II |  | 6
FORT WASHINGTON AVENUE REHAB |  | 0
FULTON |  | 404048.86
GRAMPION |  | 0
HARLEM RIVER |  | 0
HARLEM RIVER II |  | 0
KINGSBOROUGH |  | 35
MANHATTANVILLE REHAB (GROUP 2) |  | 0
MANHATTANVILLE REHAB (GROUP 3) |  | 0
MARSHALL PLAZA |  | 0
MONROE |  | 404047.86
MOORE |  | 195410.965
PARK AVENUE-EAST 122ND, 123RD STREETS |  | 0
PATTERSON |  | 0
PUBLIC SCHOOL 139 (CONVERSION) |  | 0
QUEENSBRIDGE NORTH |  | 645739.58
QUEENSBRIDGE SOUTH |  | 665565.475
SAINT MARY'S PARK |  | 417251.79
SOUTH BRONX AREA (SITE 402) |  | 0
STEBBINS AVENUE-HEWITT PLACE |  | 0
UNION AVENUE-EAST 163RD STREET |  | 1
UNION AVENUE-EAST 166TH STREET |  | 0
WASHINGTON HEIGHTS REHAB PHASE III |  | 0
0 |  | 29603.374
LEHMAN VILLAGE |  | 29603.374
Grand Total | 3170880.55 | 57634911.5441

## Int. Compactor Pipeline
[11 empty] | inflation |  | 2020 |  | 146201988.0825
3.5%
DEVELOPMENT | BOROUGH | WORK TYPE | # Int. Compactors to Replace | NRR | Priority Level | E&S Priority | RAD/PACT | RAD/PACT by 2025 | AGE (2019) (Y) | # to Replace | Estimate | Count | est. Year | Running Cost/Yr
DOUGLASS ADDITION | MANHATTAN | Interior Compactors | 1 | Zone 3 | $ | 1 |  |  |  | 0 | 73653.3945 | 0 | 2020 | 73653.3945
POMONOK | QUEENS | Interior Compactors | 121 | 0 | 0 | 1 | 2027 |  |  | 0 | 8912060.7345 | 0 | 2020 | 8985714.129
1010 EAST 178TH STREET | BRONX | Interior Compactors | 1 | 0 | 0 |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 9059367.5235
104-14 TAPSCOTT STREET | BROOKLYN | Interior Compactors | 2 | 0 | 0 |  | 2021 | Yes |  | 0 | 0 | 0 | 2020 | 9059367.5235
1162-1176 WASHINGTON AVENUE | BRONX | Interior Compactors | 1 | 0 | 0 |  | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 9059367.5235
131 SAINT NICHOLAS AVENUE | MANHATTAN | Interior Compactors | 1 | Zone 2 | $ |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 9133020.918
1471 WATSON AVENUE | BRONX | Interior Compactors | 2 | 0 | 0 |  | 2021 | Yes |  | 0 | 0 | 0 | 2020 | 9133020.918
154 WEST 84TH STREET | MANHATTAN | Interior Compactors | 1 | 0 | 0 |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 9206674.3125
303 VERNON AVENUE | BROOKLYN | Interior Compactors | 2 | Zone 1 | $ |  |  |  |  | 0 | 147306.789 | 0 | 2020 | 9353981.1015
335 EAST 111TH STREET | MANHATTAN | Interior Compactors | 1 | Zone 3 | $ |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 9427634.496
344 EAST 28TH STREET | MANHATTAN | Interior Compactors | 1 | 0 | 0 |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 9501287.8905
45 ALLEN STREET | MANHATTAN | Interior Compactors | 1 | Zone 1 | $$ |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 9574941.285
572 WARREN STREET | BROOKLYN | Interior Compactors | 2 | 0 | 0 |  |  |  |  | 0 | 147306.789 | 0 | 2020 | 9722248.074
830 AMSTERDAM AVENUE | MANHATTAN | Interior Compactors | 2 | 0 | 0 |  |  |  |  | 0 | 147306.789 | 0 | 2020 | 9869554.863
ADAMS | BRONX | Interior Compactors | 7 | 0 | 0 |  |  |  |  | 0 | 515573.7615 | 0 | 2020 | 10385128.6245
ALBANY | BROOKLYN | Interior Compactors | 6 | 0 | 0 |  | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 10385128.6245
ALBANY II | BROOKLYN | Interior Compactors | 3 | 0 | 0 |  | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 10385128.6245
AMSTERDAM | MANHATTAN | Interior Compactors | 24 | Zone 4 | 0 |  |  |  |  | 0 | 1767681.468 | 0 | 2020 | 12152810.0925
AMSTERDAM ADDITION | MANHATTAN | Interior Compactors | 2 | 0 | 0 |  |  |  |  | 0 | 147306.789 | 0 | 2020 | 12300116.8815
ARMSTRONG I | BROOKLYN | Interior Compactors | 6 | Zone 1 | $ |  |  |  |  | 0 | 441920.367 | 0 | 2020 | 12742037.2485
ARMSTRONG II | BROOKLYN | Interior Compactors | 10 | Zone 1 | $ |  |  |  |  | 0 | 736533.945 | 0 | 2020 | 13478571.1935
ASTORIA | QUEENS | Interior Compactors | 22 | 0 | 0 |  | 2024 | Yes |  | 0 | 0 | 0 | 2020 | 13478571.1935
ATLANTIC TERMINAL SITE 4B | BROOKLYN | Interior Compactors | 2 | 0 | 0 |  |  |  |  | 0 | 147306.789 | 0 | 2020 | 13625877.9825
AUDUBON | MANHATTAN | Interior Compactors | 2 | Zone 3 | $$$$ |  | 2020 | Yes |  | 0 | 0 | 0 | 2020 | 13625877.9825
BAILEY AVENUE-WEST 193RD STREET | BRONX | Interior Compactors | 1 | 0 | 0 |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 13699531.377
BAISLEY PARK | QUEENS | Interior Compactors | 5 | 0 | 0 |  |  |  |  | 0 | 368266.9725 | 0 | 2020 | 14067798.3495
BARUCH | MANHATTAN | Interior Compactors | 0 | Zone 1 | $ |  |  |  |  | 0 | 0 | 0 | 2020 | 14067798.3495
BARUCH HOUSES ADDITION | MANHATTAN | Interior Compactors | 0 | Zone 1 | $ |  |  |  |  | 0 | 0 | 0 | 2020 | 14067798.3495
BAY VIEW | BROOKLYN | Interior Compactors | 23 | 0 | 0 |  |  |  |  | 0 | 1694028.0735 | 0 | 2020 | 15761826.423
BEACH 41ST STREET-BEACH CHANNEL DRIVE | QUEENS | Interior Compactors | 6 | 0 | 0 |  |  |  |  | 0 | 441920.367 | 0 | 2020 | 16203746.79
BEDFORD-STUYVESANT REHAB | BROOKLYN | Interior Compactors | 5 | Zone 1 | $ |  |  |  |  | 0 | 368266.9725 | 0 | 2020 | 16572013.7625
BELMONT-SUTTER AREA | BROOKLYN | Interior Compactors | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 2020 | 16572013.7625
BERRY | STATEN ISLAND | Interior Compactors | 15 | 0 | 0 |  |  |  |  | 0 | 1104800.9175 | 0 | 2020 | 17676814.68
BERRY STREET-SOUTH 9TH STREET | BROOKLYN | Interior Compactors | 1 | 0 | 0 |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 17750468.0745
BETHUNE GARDENS | MANHATTAN | Interior Compactors | 1 | Zone 3 | $$ |  | 2020 | Yes |  | 0 | 0 | 0 | 2020 | 17750468.0745
BLAND | QUEENS | Interior Compactors | 5 | 0 | 0 |  |  |  |  | 0 | 368266.9725 | 0 | 2020 | 18118735.047
BORINQUEN PLAZA I | BROOKLYN | Interior Compactors | 8 | Zone 3 | $$$$ |  |  |  |  | 0 | 589227.156 | 0 | 2020 | 18707962.203
BORINQUEN PLAZA II | BROOKLYN | Interior Compactors | 7 | Zone 3 | $$$ |  |  |  |  | 0 | 515573.7615 | 0 | 2020 | 19223535.9645
BOSTON ROAD PLAZA | BRONX | Interior Compactors | 1 | 0 | 0 |  | 2022 | Yes |  | 0 | 0 | 0 | 2020 | 19223535.9645
BOSTON SECOR | BRONX | Interior Compactors | 4 | 0 | 0 |  |  |  |  | 0 | 294613.578 | 0 | 2020 | 19518149.5425
BOULEVARD | BROOKLYN | Interior Compactors | 29 | 0 | 0 |  | 2020 | Yes |  | 0 | 0 | 0 | 2020 | 19518149.5425
BOYNTON AVENUE REHAB | BRONX | Interior Compactors | 3 | 0 | 0 |  |  |  |  | 0 | 220960.1835 | 0 | 2020 | 19739109.726
BRACETTI PLAZA | MANHATTAN | Interior Compactors | 2 | Zone 1 | $ |  | 2026 |  |  | 0 | 147306.789 | 0 | 2020 | 19886416.515
BREUKELEN | BROOKLYN | Interior Compactors | 89 | 0 | 0 |  | 2021 | Yes |  | 0 | 0 | 0 | 2020 | 19886416.515
BREVOORT | BROOKLYN | Interior Compactors | 26 | 0 | 0 |  |  |  |  | 0 | 1914988.257 | 0 | 2020 | 21801404.772
BRONX RIVER | BRONX | Interior Compactors | 9 | Zone 3 | $ |  |  |  |  | 0 | 662880.5505 | 0 | 2020 | 22464285.3225
BRONX RIVER ADDITION | BRONX | Interior Compactors | 2 | 0 | 0 |  |  |  |  | 0 | 147306.789 | 0 | 2020 | 22611592.1115
BROWN | BROOKLYN | Interior Compactors | 2 | 0 | 0 |  |  |  |  | 0 | 147306.789 | 0 | 2020 | 22758898.9005
BROWNSVILLE | BROOKLYN | Interior Compactors | 46 | 0 | 0 |  |  |  |  | 0 | 3388056.147 | 0 | 2020 | 26146955.0475
BRYANT AVENUE-EAST 174TH STREET | BRONX | Interior Compactors | 1 | 0 | 0 |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 26220608.442
BUSHWICK | BROOKLYN | Interior Compactors | 8 | Zone 1 | $$ |  |  |  |  | 0 | 589227.156 | 0 | 2020 | 26809835.598
BUSHWICK II (GROUPS A & C) | BROOKLYN | Interior Compactors | 25 | Zone 1 | 0 |  |  |  |  | 0 | 1841334.8625 | 0 | 2020 | 28651170.4605
BUSHWICK II (GROUPS B & D) | BROOKLYN | Interior Compactors | 25 | 0 | 0 |  |  |  |  | 0 | 1841334.8625 | 0 | 2020 | 30492505.323
BUSHWICK II CDA (GROUP E) | BROOKLYN | Interior Compactors | 0 | Zone 1 | 0 |  | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 30492505.323
BUTLER | BRONX | Interior Compactors | 12 | Zone 1 | $$ |  |  |  |  | 0 | 883840.734 | 0 | 2020 | 31376346.057
CAMPOS PLAZA II | MANHATTAN | Interior Compactors | 3 | Zone 1 | $$ |  | 2026 |  |  | 0 | 220960.1835 | 0 | 2020 | 31597306.2405
CAREY GARDENS | BROOKLYN | Interior Compactors | 3 | 0 | 0 |  |  |  |  | 0 | 220960.1835 | 0 | 2020 | 31818266.424
CARLETON MANOR | QUEENS | Interior Compactors | 1 | 0 | 0 |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 31891919.8185
CARVER | MANHATTAN | Interior Compactors | 13 | Zone 2 | $$ |  |  |  |  | 0 | 957494.1285 | 0 | 2020 | 32849413.947
CASSIDY-LAFAYETTE | STATEN ISLAND | Interior Compactors | 4 | 0 | 0 |  |  |  |  | 0 | 294613.578 | 0 | 2020 | 33144027.525
CASTLE HILL | BRONX | Interior Compactors | 14 | 0 | 0 |  |  |  |  | 0 | 1031147.523 | 0 | 2020 | 34175175.048
CHELSEA | MANHATTAN | Interior Compactors | 4 | 0 | 0 |  |  |  |  | 0 | 294613.578 | 0 | 2020 | 34469788.626
CHELSEA ADDITION | MANHATTAN | Interior Compactors | 1 | 0 | 0 |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 34543442.0205
CLAREMONT PARKWAY-FRANKLIN AVENUE | BRONX | Interior Compactors | 1 | Zone 3 | $ |  | 2026 |  |  | 0 | 73653.3945 | 0 | 2020 | 34617095.415
CLAREMONT REHAB (GROUP 2) | BRONX | Interior Compactors | 5 | Zone 1 | $ |  | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 34617095.415
CLAREMONT REHAB (GROUP 3) | BRONX | Interior Compactors | 4 | Zone 1 | $ |  | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 34617095.415
CLAREMONT REHAB (GROUP 4) | BRONX | Interior Compactors | 9 | Zone 1 | $ |  | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 34617095.415
CLAREMONT REHAB (GROUP 5) | BRONX | Interior Compactors | 4 | Zone 1 | $ |  | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 34617095.415
CLASON POINT GARDENS | BRONX | Interior Compactors | 0 | 0 | 0 |  | 2024 | Yes |  | 0 | 0 | 0 | 2020 | 34617095.415
CLINTON | MANHATTAN | Interior Compactors | 6 | Zone 2 | $$$$ |  |  |  |  | 0 | 441920.367 | 0 | 2020 | 35059015.782
COLLEGE AVENUE-EAST 165TH STREET | BRONX | Interior Compactors | 1 | Zone 1 | $ |  | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 35059015.782
CONEY ISLAND | BROOKLYN | Interior Compactors | 5 | 0 | 0 |  |  |  |  | 0 | 368266.9725 | 0 | 2020 | 35427282.7545
CONEY ISLAND I (SITE 1B) | BROOKLYN | Interior Compactors | 1 | 0 | 0 |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 35500936.149
CONEY ISLAND I (SITE 8) | BROOKLYN | Interior Compactors | 1 | 0 | 0 |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 35574589.5435
CONEY ISLAND I (SITES 4 & 5) | BROOKLYN | Interior Compactors | 3 | 0 | 0 |  |  |  |  | 0 | 220960.1835 | 0 | 2020 | 35795549.727
CONLON LIHFE TOWER | QUEENS | Interior Compactors | 1 | 0 | 0 |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 35869203.1215
COOPER PARK | BROOKLYN | Interior Compactors | 13 | 0 | 0 |  |  |  |  | 0 | 957494.1285 | 0 | 2020 | 36826697.25
CORSI HOUSES | MANHATTAN | Interior Compactors | 1 | Zone 2 | $ |  | 2026 |  |  | 0 | 73653.3945 | 0 | 2020 | 36900350.6445
CROWN HEIGHTS | BROOKLYN | Interior Compactors | 8 | Zone 4 | 0 |  | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 36900350.6445
CYPRESS HILLS | BROOKLYN | Interior Compactors | 29 | 0 | 0 |  | 2023 | Yes |  | 0 | 0 | 0 | 2020 | 36900350.6445
DAVIDSON | BRONX | Interior Compactors | 1 | Zone 3 | $ |  | 2026 |  |  | 0 | 73653.3945 | 0 | 2020 | 36974004.039
DE HOSTOS APARTMENTS | MANHATTAN | Interior Compactors | 2 | 0 | 0 |  |  |  |  | 0 | 147306.789 | 0 | 2020 | 37121310.828
DOUGLASS | MANHATTAN | Interior Compactors | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 2020 | 37121310.828
DOUGLASS I | MANHATTAN | Interior Compactors | 11 | Zone 3 | $$$ |  |  |  |  | 0 | 810187.3395 | 0 | 2020 | 37931498.1675
DOUGLASS II | MANHATTAN | Interior Compactors | 6 | Zone 3 | $$$ |  |  |  |  | 0 | 441920.367 | 0 | 2020 | 38373418.5345
DREW-HAMILTON | MANHATTAN | Interior Compactors | 5 | Zone 2 | $ |  |  |  |  | 0 | 368266.9725 | 0 | 2020 | 38741685.507
DYCKMAN | MANHATTAN | Interior Compactors | 14 | 0 | 0 |  |  |  |  | 0 | 1031147.523 | 0 | 2020 | 39772833.03
EAGLE AVENUE-EAST 163RD STREET | BRONX | Interior Compactors | 1 | 0 | 0 |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 39846486.4245
EAST 152ND STREET-COURTLANDT AVENUE | BRONX | Interior Compactors | 2 | 0 | 0 |  | 2023 | Yes |  | 0 | 0 | 0 | 2020 | 39846486.4245
EAST 165TH STREET-BRYANT AVENUE | BRONX | Interior Compactors | 0 | Zone 4 | 0 |  |  |  |  | 0 | 0 | 0 | 2020 | 39846486.4245
EAST 173RD STREET-VYSE AVENUE | BRONX | Interior Compactors | 0 | Zone 4 | 0 |  |  |  |  | 0 | 0 | 0 | 2020 | 39846486.4245
EAST 180TH STREET-MONTEREY AVENUE | BRONX | Interior Compactors | 2 | Zone 1 | $$ |  |  |  |  | 0 | 147306.789 | 0 | 2020 | 39993793.2135
EAST NEW YORK CITY LINE | BROOKLYN | Interior Compactors | 0 | 0 | 0 |  | 2023 | Yes |  | 0 | 0 | 0 | 2020 | 39993793.2135
EAST RIVER | MANHATTAN | Interior Compactors | 29 | Zone 2 | $ |  | 2024 | Yes |  | 0 | 0 | 0 | 2020 | 39993793.2135
EASTCHESTER GARDENS | BRONX | Interior Compactors | 15 | 0 | 0 |  | 2026 |  |  | 0 | 1104800.9175 | 0 | 2020 | 41098594.131
EDENWALD | BRONX | Interior Compactors | 3 | 0 | 0 |  | 2022 | Yes |  | 0 | 0 | 0 | 2020 | 41098594.131
ELLIOTT | MANHATTAN | Interior Compactors | 8 | 0 | 0 |  |  |  |  | 0 | 589227.156 | 0 | 2020 | 41687821.287
FARRAGUT | BROOKLYN | Interior Compactors | 10 | 0 | 0 |  | 2027 |  |  | 0 | 736533.945 | 0 | 2020 | 42424355.232
FENIMORE-LEFFERTS | BROOKLYN | Interior Compactors | 0 | 0 | 0 |  | 2021 | Yes |  | 0 | 0 | 0 | 2020 | 42424355.232
FHA REPOSSESSED HOUSES (GROUP I) | 0 | Interior Compactors | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 2020 | 42424355.232
FHA REPOSSESSED HOUSES (GROUP II) | 0 | Interior Compactors | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 2020 | 42424355.232
FHA REPOSSESSED HOUSES (GROUP III) | 0 | Interior Compactors | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 2020 | 42424355.232
FHA REPOSSESSED HOUSES (GROUP IV) | 0 | Interior Compactors | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 2020 | 42424355.232
FHA REPOSSESSED HOUSES (GROUP IX) | 0 | Interior Compactors | 0 | Zone 4 | 0 |  |  |  |  | 0 | 0 | 0 | 2020 | 42424355.232
FHA REPOSSESSED HOUSES (GROUP V) | 0 | Interior Compactors | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 2020 | 42424355.232
FHA REPOSSESSED HOUSES (GROUP VI) | 0 | Interior Compactors | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 2020 | 42424355.232
FHA REPOSSESSED HOUSES (GROUP VII) | 0 | Interior Compactors | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 2020 | 42424355.232
FHA REPOSSESSED HOUSES (GROUP VIII) | 0 | Interior Compactors | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 2020 | 42424355.232
FHA REPOSSESSED HOUSES (GROUP X) | 0 | Interior Compactors | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 2020 | 42424355.232
FIORENTINO PLAZA | BROOKLYN | Interior Compactors | 3 | 0 | 0 |  | 2026 |  |  | 0 | 220960.1835 | 0 | 2020 | 42645315.4155
FIRST HOUSES | MANHATTAN | Interior Compactors | 8 | Zone 1 | $ |  | 2026 |  |  | 0 | 589227.156 | 0 | 2020 | 43234542.5715
FOREST | BRONX | Interior Compactors | 15 | Zone 4 | 0 |  |  |  |  | 0 | 1104800.9175 | 0 | 2020 | 44339343.489
FORT INDEPENDENCE STREET-HEATH AVENUE | BRONX | Interior Compactors | 2 | 0 | 0 |  |  |  |  | 0 | 147306.789 | 0 | 2020 | 44486650.278
FORT WASHINGTON AVENUE REHAB | MANHATTAN | Interior Compactors | 2 | Zone 3 | $ |  | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 44486650.278
FULTON | MANHATTAN | Interior Compactors | 19 | Zone 3 | $ |  |  |  |  | 0 | 1399414.4955 | 0 | 2020 | 45886064.7735
GARVEY (GROUP A) | BROOKLYN | Interior Compactors | 5 | 0 | 0 |  |  |  |  | 0 | 368266.9725 | 0 | 2020 | 46254331.746
GLEBE AVENUE-WESTCHESTER AVENUE | BRONX | Interior Compactors | 2 | 0 | 0 |  | 2021 | Yes |  | 0 | 0 | 0 | 2020 | 46254331.746
GLENMORE PLAZA | BROOKLYN | Interior Compactors | 4 | 0 | 0 |  |  |  |  | 0 | 294613.578 | 0 | 2020 | 46548945.324
GLENWOOD | BROOKLYN | Interior Compactors | 40 | 0 | 0 |  | 2028 |  |  | 0 | 2946135.78 | 0 | 2020 | 49495081.104
GOMPERS | MANHATTAN | Interior Compactors | 4 | Zone 1 | $ |  |  |  |  | 0 | 294613.578 | 0 | 2020 | 49789694.682
GOWANUS | BROOKLYN | Interior Compactors | 24 | 0 | 0 |  |  |  |  | 0 | 1767681.468 | 0 | 2020 | 51557376.15
GRAMPION | MANHATTAN | Interior Compactors | 1 | Zone 3 | $ |  | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 51557376.15
GRANT | MANHATTAN | Interior Compactors | 16 | Zone 2 | $$$$ |  |  |  |  | 0 | 1178454.312 | 0 | 2020 | 52735830.462
GRAVESEND | BROOKLYN | Interior Compactors | 2 | 0 | 0 |  |  |  |  | 0 | 147306.789 | 0 | 2020 | 52883137.251
GUN HILL | BRONX | Interior Compactors | 6 | 0 | 0 |  |  |  |  | 0 | 441920.367 | 0 | 2020 | 53325057.618
HABER | BROOKLYN | Interior Compactors | 3 | 0 | 0 |  |  |  |  | 0 | 220960.1835 | 0 | 2020 | 53546017.8015
HAMMEL | QUEENS | Interior Compactors | 14 | 0 | 0 |  |  |  |  | 0 | 1031147.523 | 0 | 2020 | 54577165.3245
HARBORVIEW TERRACE | MANHATTAN | Interior Compactors | 2 | 0 | 0 |  |  |  |  | 0 | 147306.789 | 0 | 2020 | 54724472.1135
HARLEM RIVER | MANHATTAN | Interior Compactors | 43 | Zone 3 | $ |  | 2020 | Yes |  | 0 | 0 | 0 | 2020 | 54724472.1135
HARLEM RIVER II | MANHATTAN | Interior Compactors | 1 | Zone 3 | $$ |  | 2020 | Yes |  | 0 | 0 | 0 | 2020 | 54724472.1135
HARRISON AVENUE REHAB (GROUP A) | BRONX | Interior Compactors | 1 | 0 | 0 |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 54798125.508
HARRISON AVENUE REHAB (GROUP B) | BRONX | Interior Compactors | 4 | 0 | 0 |  |  |  |  | 0 | 294613.578 | 0 | 2020 | 55092739.086
HERNANDEZ | MANHATTAN | Interior Compactors | 1 | Zone 1 | $$ |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 55166392.4805
HIGHBRIDGE GARDENS | BRONX | Interior Compactors | 6 | Zone 1 | $ |  |  |  |  | 0 | 441920.367 | 0 | 2020 | 55608312.8475
HOE AVENUE-EAST 173RD STREET | BRONX | Interior Compactors | 1 | 0 | 0 |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 55681966.242
HOLMES TOWERS | MANHATTAN | Interior Compactors | 2 | 0 | 0 |  |  |  |  | 0 | 147306.789 | 0 | 2020 | 55829273.031
HOPE GARDENS | BROOKLYN | Interior Compactors | 4 | Zone 1 | 0 |  | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 55829273.031
HOWARD | BROOKLYN | Interior Compactors | 16 | 0 | 0 |  |  |  |  | 0 | 1178454.312 | 0 | 2020 | 57007727.343
HOWARD AVENUE | BROOKLYN | Interior Compactors | 0 | 0 | 0 |  | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 57007727.343
HOWARD AVENUE-PARK PLACE | BROOKLYN | Interior Compactors | 0 | Zone 4 | 0 |  | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 57007727.343
HUGHES APARTMENTS | BROOKLYN | Interior Compactors | 3 | 0 | 0 |  |  |  |  | 0 | 220960.1835 | 0 | 2020 | 57228687.5265
HUNTS POINT AVENUE REHAB | BRONX | Interior Compactors | 1 | 0 | 0 |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 57302340.921
HYLAN | BROOKLYN | Interior Compactors | 1 | Zone 1 | $ |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 57375994.3155
INDEPENDENCE | BROOKLYN | Interior Compactors | 6 | 0 | 0 |  | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 57375994.3155
INGERSOLL | BROOKLYN | Interior Compactors | 44 | 0 | 0 |  |  |  |  | 0 | 3240749.358 | 0 | 2020 | 60616743.6735
INTERNATIONAL TOWER | QUEENS | Interior Compactors | 2 | 0 | 0 |  |  |  |  | 0 | 147306.789 | 0 | 2020 | 60764050.4625
ISAACS | MANHATTAN | Interior Compactors | 6 | 0 | 0 |  |  |  |  | 0 | 441920.367 | 0 | 2020 | 61205970.8295
JACKSON | BRONX | Interior Compactors | 7 | Zone 1 | $ |  |  |  |  | 0 | 515573.7615 | 0 | 2020 | 61721544.591
JEFFERSON | MANHATTAN | Interior Compactors | 34 | Zone 2 | $$ |  | 2026 |  |  | 0 | 2504215.413 | 0 | 2020 | 64225760.004
JOHNSON | MANHATTAN | Interior Compactors | 17 | Zone 2 | $$$ |  | 2028 |  |  | 0 | 1252107.7065 | 0 | 2020 | 65477867.7105
KING TOWERS | MANHATTAN | Interior Compactors | 10 | Zone 2 | $$$ |  |  |  |  | 0 | 736533.945 | 0 | 2020 | 66214401.6555
KINGSBOROUGH | BROOKLYN | Interior Compactors | 35 | Zone 3 | $ |  |  |  |  | 0 | 2577868.8075 | 0 | 2020 | 68792270.463
KINGSBOROUGH EXTENSION | BROOKLYN | Interior Compactors | 2 | Zone 4 | 0 |  |  |  |  | 0 | 147306.789 | 0 | 2020 | 68939577.252
LA GUARDIA | MANHATTAN | Interior Compactors | 9 | Zone 1 | $$ |  |  |  |  | 0 | 662880.5505 | 0 | 2020 | 69602457.8025
LA GUARDIA ADDITION | MANHATTAN | Interior Compactors | 1 | Zone 1 | $ |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 69676111.197
LAFAYETTE | BROOKLYN | Interior Compactors | 7 | Zone 1 | $$$ |  |  |  |  | 0 | 515573.7615 | 0 | 2020 | 70191684.9585
LATIMER GARDENS | QUEENS | Interior Compactors | 4 | 0 | 0 |  |  |  |  | 0 | 294613.578 | 0 | 2020 | 70486298.5365
LAVANBURG HOMES | MANHATTAN | Interior Compactors | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 2020 | 70486298.5365
LEAVITT STREET-34TH AVENUE | QUEENS | Interior Compactors | 1 | 0 | 0 |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 70559951.931
LEHMAN VILLAGE | MANHATTAN | Interior Compactors | 4 | 0 | 0 |  |  |  |  | 0 | 294613.578 | 0 | 2020 | 70854565.509
LENOX ROAD-ROCKAWAY PARKWAY | BROOKLYN | Interior Compactors | 5 | 0 | 0 |  | 2021 | Yes |  | 0 | 0 | 0 | 2020 | 70854565.509
LEXINGTON | MANHATTAN | Interior Compactors | 4 | Zone 2 | $ |  | 2023 | Yes |  | 0 | 0 | 0 | 2020 | 70854565.509
LINCOLN | MANHATTAN | Interior Compactors | 20 | Zone 2 | $$$$ |  |  |  |  | 0 | 1473067.89 | 0 | 2020 | 72327633.399
LINDEN | BROOKLYN | Interior Compactors | 19 | 0 | 0 |  | 2020 | Yes |  | 0 | 0 | 0 | 2020 | 72327633.399
LONG ISLAND BAPTIST HOUSES | BROOKLYN | Interior Compactors | 4 | 0 | 0 |  | 2026 |  |  | 0 | 294613.578 | 0 | 2020 | 72622246.977
LONGFELLOW AVENUE REHAB | BRONX | Interior Compactors | 5 | 0 | 0 |  |  |  |  | 0 | 368266.9725 | 0 | 2020 | 72990513.9495
LOW HOUSES | BROOKLYN | Interior Compactors | 3 | 0 | 0 |  |  |  |  | 0 | 220960.1835 | 0 | 2020 | 73211474.133
LOWER EAST SIDE I INFILL | MANHATTAN | Interior Compactors | 0 | Zone 1 | $$ |  |  |  |  | 0 | 0 | 0 | 2020 | 73211474.133
LOWER EAST SIDE II | MANHATTAN | Interior Compactors | 0 | Zone 1 | $ |  | 2026 |  |  | 0 | 0 | 0 | 2020 | 73211474.133
LOWER EAST SIDE III | MANHATTAN | Interior Compactors | 0 | Zone 1 | $ |  |  |  |  | 0 | 0 | 0 | 2020 | 73211474.133
LOWER EAST SIDE REHAB (GROUP 5) | MANHATTAN | Interior Compactors | 2 | Zone 1 | $$ |  | 2026 |  |  | 0 | 147306.789 | 0 | 2020 | 73358780.922
MANHATTANVILLE | MANHATTAN | Interior Compactors | 6 | Zone 2 | $ |  | 2028 |  |  | 0 | 441920.367 | 0 | 2020 | 73800701.289
MANHATTANVILLE REHAB (GROUP 2) | MANHATTAN | Interior Compactors | 2 | Zone 3 | $ |  | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 73800701.289
MANHATTANVILLE REHAB (GROUP 3) | MANHATTAN | Interior Compactors | 2 | Zone 3 | $ |  | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 73800701.289
MARBLE HILL | BRONX | Interior Compactors | 11 | 0 | 0 |  |  |  |  | 0 | 810187.3395 | 0 | 2020 | 74610888.6285
MARCY | BROOKLYN | Interior Compactors | 69 | Zone 1 | $$ |  | 2027 |  |  | 0 | 5082084.2205 | 0 | 2020 | 79692972.849
MARCY AVENUE-GREENE AVENUE SITE A | BROOKLYN | Interior Compactors | 0 | Zone 1 | $ |  | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 79692972.849
MARCY AVENUE-GREENE AVENUE SITE B | BROOKLYN | Interior Compactors | 0 | 0 | 0 |  | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 79692972.849
MARINER'S HARBOR | STATEN ISLAND | Interior Compactors | 27 | 0 | 0 |  | 2028 |  |  | 0 | 1988641.6515 | 0 | 2020 | 81681614.5005
MARLBORO | BROOKLYN | Interior Compactors | 28 | 0 | 0 |  |  |  |  | 0 | 2062295.046 | 0 | 2020 | 83743909.5465
MARSHALL PLAZA | MANHATTAN | Interior Compactors | 1 | Zone 3 | $$ |  | 2020 | Yes |  | 0 | 0 | 0 | 2020 | 83743909.5465
MCKINLEY | BRONX | Interior Compactors | 5 | Zone 4 | 0 |  |  |  |  | 0 | 368266.9725 | 0 | 2020 | 84112176.519
MELROSE | BRONX | Interior Compactors | 8 | Zone 1 | $ |  | 2023 | Yes |  | 0 | 0 | 0 | 2020 | 84112176.519
MELTZER TOWER | MANHATTAN | Interior Compactors | 1 | Zone 1 | $ |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 84185829.9135
METRO NORTH PLAZA | MANHATTAN | Interior Compactors | 3 | Zone 2 | $ |  |  |  |  | 0 | 220960.1835 | 0 | 2020 | 84406790.097
MIDDLETOWN PLAZA | BRONX | Interior Compactors | 1 | 0 | 0 |  | 2026 |  |  | 0 | 73653.3945 | 0 | 2020 | 84480443.4915
MILL BROOK | BRONX | Interior Compactors | 9 | 0 | 0 |  |  |  |  | 0 | 662880.5505 | 0 | 2020 | 85143324.042
MILL BROOK EXTENSION | BRONX | Interior Compactors | 1 | 0 | 0 |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 85216977.4365
MITCHEL | BRONX | Interior Compactors | 20 | 0 | 0 |  |  |  |  | 0 | 1473067.89 | 0 | 2020 | 86690045.3265
MONROE | BRONX | Interior Compactors | 18 | Zone 3 | $ |  |  |  |  | 0 | 1325761.101 | 0 | 2020 | 88015806.4275
MOORE | BRONX | Interior Compactors | 4 | Zone 3 | $$ |  |  |  |  | 0 | 294613.578 | 0 | 2020 | 88310420.0055
MORRIS I | BRONX | Interior Compactors | 10 | Zone 1 | $$ |  |  |  |  | 0 | 736533.945 | 0 | 2020 | 89046953.9505
MORRIS II | BRONX | Interior Compactors | 7 | Zone 1 | $$$ |  |  |  |  | 0 | 515573.7615 | 0 | 2020 | 89562527.712
MORRIS PARK SENIOR CITIZENS HOME | MANHATTAN | Interior Compactors | 1 | Zone 2 | $$$$ |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 89636181.1065
MORRISANIA | BRONX | Interior Compactors | 2 | Zone 1 | $$$$ |  |  |  |  | 0 | 147306.789 | 0 | 2020 | 89783487.8955
MORRISANIA AIR RIGHTS | BRONX | Interior Compactors | 5 | Zone 1 | $ |  |  |  |  | 0 | 368266.9725 | 0 | 2020 | 90151754.868
MOTT HAVEN | BRONX | Interior Compactors | 8 | 0 | 0 |  |  |  |  | 0 | 589227.156 | 0 | 2020 | 90740982.024
NEW LANE AREA | STATEN ISLAND | Interior Compactors | 2 | 0 | 0 |  |  |  |  | 0 | 147306.789 | 0 | 2020 | 90888288.813
NOSTRAND | BROOKLYN | Interior Compactors | 32 | 0 | 0 |  | 2028 |  |  | 0 | 2356908.624 | 0 | 2020 | 93245197.437
OCEAN BAY APARTMENTS (OCEANSIDE) | QUEENS | Interior Compactors | 13 | 0 | 0 |  |  |  |  | 0 | 957494.1285 | 0 | 2020 | 94202691.5655
OCEAN HILL APARTMENTS | BROOKLYN | Interior Compactors | 3 | 0 | 0 |  |  |  |  | 0 | 220960.1835 | 0 | 2020 | 94423651.749
OCEAN HILL-BROWNSVILLE | BROOKLYN | Interior Compactors | 6 | 0 | 0 |  | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 94423651.749
O'DWYER GARDENS | BROOKLYN | Interior Compactors | 6 | 0 | 0 |  |  |  |  | 0 | 441920.367 | 0 | 2020 | 94865572.116
PALMETTO GARDENS | BROOKLYN | Interior Compactors | 1 | 0 | 0 |  | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 94865572.116
PARK AVENUE-EAST 122ND, 123RD STREETS | MANHATTAN | Interior Compactors | 2 | Zone 3 | $$ |  | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 94865572.116
PARK ROCK REHAB | BROOKLYN | Interior Compactors | 6 | 0 | 0 |  | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 94865572.116
PARKSIDE | BRONX | Interior Compactors | 21 | 0 | 0 |  |  |  |  | 0 | 1546721.2845 | 0 | 2020 | 96412293.4005
PATTERSON | BRONX | Interior Compactors | 0 | Zone 3 | $$ |  | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 96412293.4005
PELHAM PARKWAY | BRONX | Interior Compactors | 38 | 0 | 0 |  | 2022 | Yes |  | 0 | 0 | 0 | 2020 | 96412293.4005
PENNSYLVANIA AVENUE-WORTMAN AVENUE | BROOKLYN | Interior Compactors | 3 | 0 | 0 |  |  |  |  | 0 | 220960.1835 | 0 | 2020 | 96633253.584
PINK | BROOKLYN | Interior Compactors | 22 | 0 | 0 |  |  |  |  | 0 | 1620374.679 | 0 | 2020 | 98253628.263
POLO GROUNDS TOWERS | MANHATTAN | Interior Compactors | 9 | Zone 2 | $ |  |  |  |  | 0 | 662880.5505 | 0 | 2020 | 98916508.8135
PSS GRANDPARENT FAMILY APARTMENTS | BRONX | Interior Compactors | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 2020 | 98916508.8135
PUBLIC SCHOOL 139 (CONVERSION) | MANHATTAN | Interior Compactors | 1 | Zone 3 | $ |  | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 98916508.8135
QUEENSBRIDGE NORTH | QUEENS | Interior Compactors | 47 | Zone 3 | $ |  |  |  |  | 0 | 3461709.5415 | 0 | 2020 | 102378218.355
QUEENSBRIDGE SOUTH | QUEENS | Interior Compactors | 49 | Zone 3 | $ |  |  |  |  | 0 | 3609016.3305 | 0 | 2020 | 105987234.6855
RALPH AVENUE REHAB | BROOKLYN | Interior Compactors | 9 | 0 | 0 |  | 2021 | Yes |  | 0 | 0 | 0 | 2020 | 105987234.6855
RANDALL AVENUE-BALCOM AVENUE | BRONX | Interior Compactors | 3 | 0 | 0 |  | 2022 | Yes |  | 0 | 0 | 0 | 2020 | 105987234.6855
RANDOLPH SOUTH | MANHATTAN | Interior Compactors | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 2020 | 105987234.6855
RANGEL | MANHATTAN | Interior Compactors | 10 | Zone 2 | $ |  |  |  |  | 0 | 736533.945 | 0 | 2020 | 106723768.6305
RAVENSWOOD | QUEENS | Interior Compactors | 39 | 0 | 0 |  |  |  |  | 0 | 2872482.3855 | 0 | 2020 | 109596251.016
RED HOOK EAST | BROOKLYN | Interior Compactors | 47 | 0 | 0 |  | 2024 | Yes |  | 0 | 0 | 0 | 2020 | 109596251.016
RED HOOK WEST | BROOKLYN | Interior Compactors | 43 | 0 | 0 |  | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 109596251.016
REDFERN | QUEENS | Interior Compactors | 16 | 0 | 0 |  | 2022 | Yes |  | 0 | 0 | 0 | 2020 | 109596251.016
REHAB PROGRAM (COLLEGE POINT) | QUEENS | Interior Compactors | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 2020 | 109596251.016
REHAB PROGRAM (DOUGLASS REHABS) | MANHATTAN | Interior Compactors | 3 | 0 | 0 |  |  |  |  | 0 | 220960.1835 | 0 | 2020 | 109817211.1995
REHAB PROGRAM (TAFT REHABS) | MANHATTAN | Interior Compactors | 4 | 0 | 0 |  |  |  |  | 0 | 294613.578 | 0 | 2020 | 110111824.7775
REHAB PROGRAM (WISE REHAB) | MANHATTAN | Interior Compactors | 1 | Zone 4 | 0 |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 110185478.172
REID APARTMENTS | BROOKLYN | Interior Compactors | 1 | 0 | 0 |  | 2021 | Yes |  | 0 | 0 | 0 | 2020 | 110185478.172
RICHMOND TERRACE | STATEN ISLAND | Interior Compactors | 6 | 0 | 0 |  |  |  |  | 0 | 441920.367 | 0 | 2020 | 110627398.539
RIIS | MANHATTAN | Interior Compactors | 15 | Zone 1 | $ |  |  |  |  | 0 | 1104800.9175 | 0 | 2020 | 111732199.4565
RIIS II | MANHATTAN | Interior Compactors | 7 | Zone 1 | $$ |  |  |  |  | 0 | 515573.7615 | 0 | 2020 | 112247773.218
ROBBINS PLAZA | MANHATTAN | Interior Compactors | 1 | 0 | 0 |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 112321426.6125
ROBINSON | MANHATTAN | Interior Compactors | 2 | Zone 2 | $$ |  |  |  |  | 0 | 147306.789 | 0 | 2020 | 112468733.4015
ROOSEVELT I | BROOKLYN | Interior Compactors | 6 | Zone 1 | $ |  |  |  |  | 0 | 441920.367 | 0 | 2020 | 112910653.7685
ROOSEVELT II | BROOKLYN | Interior Compactors | 3 | Zone 1 | $ |  |  |  |  | 0 | 220960.1835 | 0 | 2020 | 113131613.952
RUTGERS | MANHATTAN | Interior Compactors | 5 | Zone 1 | $ |  |  |  |  | 0 | 368266.9725 | 0 | 2020 | 113499880.9245
RUTLAND TOWERS | BROOKLYN | Interior Compactors | 1 | 0 | 0 |  | 2021 | Yes |  | 0 | 0 | 0 | 2020 | 113499880.9245
SACK WERN | BRONX | Interior Compactors | 7 | 0 | 0 |  | 2024 | Yes |  | 0 | 0 | 0 | 2020 | 113499880.9245
SAINT MARY'S PARK | BRONX | Interior Compactors | 6 | Zone 3 | $ |  |  |  |  | 0 | 441920.367 | 0 | 2020 | 113941801.2915
SAINT NICHOLAS | MANHATTAN | Interior Compactors | 14 | Zone 2 | $ |  |  |  |  | 0 | 1031147.523 | 0 | 2020 | 114972948.8145
SAMUEL (CITY) | MANHATTAN | Interior Compactors | 40 | Zone 2 | $$ |  | 2026 |  |  | 0 | 2946135.78 | 0 | 2020 | 117919084.5945
SAMUEL (MHOP) I | MANHATTAN | Interior Compactors | 1 | 0 | 0 |  | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 117919084.5945
SAMUEL (MHOP) II | MANHATTAN | Interior Compactors | 0 | 0 | 0 |  | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 117919084.5945
SAMUEL (MHOP) III | MANHATTAN | Interior Compactors | 1 | 0 | 0 |  | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 117919084.5945
SARATOGA VILLAGE | BROOKLYN | Interior Compactors | 1 | 0 | 0 |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 117992737.989
SEDGWICK | BRONX | Interior Compactors | 7 | 0 | 0 |  |  |  |  | 0 | 515573.7615 | 0 | 2020 | 118508311.7505
SEWARD PARK EXTENSION | MANHATTAN | Interior Compactors | 2 | Zone 1 | $ |  |  |  |  | 0 | 147306.789 | 0 | 2020 | 118655618.5395
SHEEPSHEAD BAY | BROOKLYN | Interior Compactors | 35 | 0 | 0 |  | 2028 |  |  | 0 | 2577868.8075 | 0 | 2020 | 121233487.347
SHELTON HOUSE | QUEENS | Interior Compactors | 1 | 0 | 0 |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 121307140.7415
SMITH | MANHATTAN | Interior Compactors | 12 | Zone 1 | $ |  |  |  |  | 0 | 883840.734 | 0 | 2020 | 122190981.4755
SOTOMAYOR HOUSES | BRONX | Interior Compactors | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 2020 | 122190981.4755
SOUNDVIEW | BRONX | Interior Compactors | 22 | 0 | 0 |  | 2023 | Yes |  | 0 | 0 | 0 | 2020 | 122190981.4755
SOUTH BEACH | STATEN ISLAND | Interior Compactors | 15 | 0 | 0 |  |  |  |  | 0 | 1104800.9175 | 0 | 2020 | 123295782.393
SOUTH BRONX AREA (SITE 402) | BRONX | Interior Compactors | 0 | Zone 3 | $$ |  | 2026 |  |  | 0 | 0 | 0 | 2020 | 123295782.393
SOUTH JAMAICA I | QUEENS | Interior Compactors | 33 | 0 | 0 |  | 2021 | Yes |  | 0 | 0 | 0 | 2020 | 123295782.393
SOUTH JAMAICA II | QUEENS | Interior Compactors | 27 | 0 | 0 |  | 2021 | Yes |  | 0 | 0 | 0 | 2020 | 123295782.393
STANTON STREET | MANHATTAN | Interior Compactors | 1 | 0 | 0 |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 123369435.7875
STAPLETON | STATEN ISLAND | Interior Compactors | 12 | 0 | 0 |  |  |  |  | 0 | 883840.734 | 0 | 2020 | 124253276.5215
STEBBINS AVENUE-HEWITT PLACE | BRONX | Interior Compactors | 0 | Zone 3 | $$$ |  | 2026 |  |  | 0 | 0 | 0 | 2020 | 124253276.5215
STERLING PLACE REHABS (SAINT JOHNS-STERLING) | BROOKLYN | Interior Compactors | 5 | 0 | 0 |  | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 124253276.5215
STERLING PLACE REHABS (STERLING-BUFFALO) | BROOKLYN | Interior Compactors | 7 | 0 | 0 |  | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 124253276.5215
STRAUS | MANHATTAN | Interior Compactors | 2 | 0 | 0 |  |  |  |  | 0 | 147306.789 | 0 | 2020 | 124400583.3105
STUYVESANT GARDENS I | BROOKLYN | Interior Compactors | 11 | 0 | 0 |  |  |  |  | 0 | 810187.3395 | 0 | 2020 | 125210770.65
STUYVESANT GARDENS II | BROOKLYN | Interior Compactors | 1 | 0 | 0 |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 125284424.0445
SUMNER | BROOKLYN | Interior Compactors | 24 | Zone 1 | $ |  |  |  |  | 0 | 1767681.468 | 0 | 2020 | 127052105.5125
SURFSIDE GARDENS | BROOKLYN | Interior Compactors | 5 | 0 | 0 |  |  |  |  | 0 | 368266.9725 | 0 | 2020 | 127420372.485
SUTTER AVENUE-UNION STREET | BROOKLYN | Interior Compactors | 5 | 0 | 0 |  | 2021 | Yes |  | 0 | 0 | 0 | 2020 | 127420372.485
TAFT | MANHATTAN | Interior Compactors | 11 | Zone 2 | $$$ |  |  |  |  | 0 | 810187.3395 | 0 | 2020 | 128230559.8245
TAPSCOTT STREET REHAB | BROOKLYN | Interior Compactors | 9 | 0 | 0 |  | 2021 | Yes |  | 0 | 0 | 0 | 2020 | 128230559.8245
TAYLOR STREET-WYTHE AVENUE | BROOKLYN | Interior Compactors | 1 | 0 | 0 |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 128304213.219
TELLER AVENUE-EAST 166TH STREET | BRONX | Interior Compactors | 2 | Zone 1 | $ |  | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 128304213.219
THOMAS APARTMENTS | MANHATTAN | Interior Compactors | 1 | Zone 4 | 0 |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 128377866.6135
THROGGS NECK | BRONX | Interior Compactors | 60 | 0 | 0 |  | 2022 | Yes |  | 0 | 0 | 0 | 2020 | 128377866.6135
THROGGS NECK ADDITION | BRONX | Interior Compactors | 4 | 0 | 0 |  | 2022 | Yes |  | 0 | 0 | 0 | 2020 | 128377866.6135
TILDEN | BROOKLYN | Interior Compactors | 8 | 0 | 0 |  |  |  |  | 0 | 589227.156 | 0 | 2020 | 128967093.7695
TODT HILL | STATEN ISLAND | Interior Compactors | 13 | 0 | 0 |  |  |  |  | 0 | 957494.1285 | 0 | 2020 | 129924587.898
TOMPKINS | BROOKLYN | Interior Compactors | 11 | Zone 1 | $ |  |  |  |  | 0 | 810187.3395 | 0 | 2020 | 130734775.2375
TWIN PARKS EAST (SITE 9) | BRONX | Interior Compactors | 1 | Zone 1 | $ |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 130808428.632
TWO BRIDGES URA (SITE 7) | MANHATTAN | Interior Compactors | 1 | Zone 1 | $ |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 130882082.0265
UNION AVENUE-EAST 163RD STREET | BRONX | Interior Compactors | 1 | Zone 3 | $ |  | 2026 |  |  | 0 | 73653.3945 | 0 | 2020 | 130955735.421
UNION AVENUE-EAST 166TH STREET | BRONX | Interior Compactors | 0 | Zone 3 | $ |  | 2026 |  |  | 0 | 0 | 0 | 2020 | 130955735.421
UNITY PLAZA (SITES 17,24,25A) | BROOKLYN | Interior Compactors | 3 | 0 | 0 |  | 2026 |  |  | 0 | 220960.1835 | 0 | 2020 | 131176695.6045
UNITY PLAZA (SITES 4-27) | BROOKLYN | Interior Compactors | 12 | 0 | 0 |  | 2026 |  |  | 0 | 883840.734 | 0 | 2020 | 132060536.3385
UNIVERSITY AVENUE REHAB | BRONX | Interior Compactors | 5 | 0 | 0 |  |  |  |  | 0 | 368266.9725 | 0 | 2020 | 132428803.311
UPACA (SITE 5) | MANHATTAN | Interior Compactors | 1 | Zone 2 | $ |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 132502456.7055
UPACA (SITE 6) | MANHATTAN | Interior Compactors | 1 | Zone 2 | $ |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 132576110.1
VAN DYKE I | BROOKLYN | Interior Compactors | 31 | 0 | 0 |  | 2024 | Yes |  | 0 | 0 | 0 | 2020 | 132576110.1
VAN DYKE II | BROOKLYN | Interior Compactors | 1 | 0 | 0 |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 132649763.4945
VANDALIA AVENUE | BROOKLYN | Interior Compactors | 2 | 0 | 0 |  |  |  |  | 0 | 147306.789 | 0 | 2020 | 132797070.2835
VLADECK | MANHATTAN | Interior Compactors | 2 | Zone 1 | $$ |  |  |  |  | 0 | 147306.789 | 0 | 2020 | 132944377.0725
VLADECK II | MANHATTAN | Interior Compactors | 7 | Zone 1 | $ |  |  |  |  | 0 | 515573.7615 | 0 | 2020 | 133459950.834
WAGNER | MANHATTAN | Interior Compactors | 22 | Zone 2 | $ |  |  |  |  | 0 | 1620374.679 | 0 | 2020 | 135080325.513
WALD | MANHATTAN | Interior Compactors | 17 | Zone 1 | $ |  |  |  |  | 0 | 1252107.7065 | 0 | 2020 | 136332433.2195
WASHINGTON | MANHATTAN | Interior Compactors | 14 | Zone 2 | $$$ |  | 2023 | Yes |  | 0 | 0 | 0 | 2020 | 136332433.2195
WASHINGTON HEIGHTS REHAB (GROUPS 1&2) | MANHATTAN | Interior Compactors | 6 | 0 | 0 |  | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 136332433.2195
WASHINGTON HEIGHTS REHAB PHASE III | MANHATTAN | Interior Compactors | 0 | Zone 3 | $ |  | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 136332433.2195
WASHINGTON HEIGHTS REHAB PHASE III (FORT WASHINGTON) | MANHATTAN | Interior Compactors | 3 | 0 | 0 |  |  |  |  | 0 | 220960.1835 | 0 | 2020 | 136553393.403
WASHINGTON HEIGHTS REHAB PHASE III (HARLEM RIVER) | MANHATTAN | Interior Compactors | 1 | 0 | 0 |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 136627046.7975
WASHINGTON HEIGHTS REHAB PHASE IV (C) | MANHATTAN | Interior Compactors | 2 | 0 | 0 |  | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 136627046.7975
WASHINGTON HEIGHTS REHAB PHASE IV (D) | MANHATTAN | Interior Compactors | 2 | 0 | 0 |  | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 136627046.7975
WEBSTER | BRONX | Interior Compactors | 5 | Zone 1 | $ |  |  |  |  | 0 | 368266.9725 | 0 | 2020 | 136995313.77
WEEKSVILLE GARDENS | BROOKLYN | Interior Compactors | 0 | 0 | 0 |  | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 136995313.77
WEST BRIGHTON I | STATEN ISLAND | Interior Compactors | 8 | 0 | 0 |  |  |  |  | 0 | 589227.156 | 0 | 2020 | 137584540.926
WEST BRIGHTON II | STATEN ISLAND | Interior Compactors | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 2020 | 137584540.926
WEST FARMS ROAD REHAB | BRONX | Interior Compactors | 7 | 0 | 0 |  |  |  |  | 0 | 515573.7615 | 0 | 2020 | 138100114.6875
WEST FARMS SQUARE CONVENTIONAL | BRONX | Interior Compactors | 1 | 0 | 0 |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 138173768.082
WEST TREMONT AVENUE-SEDGWICK AVENUE AREA | BRONX | Interior Compactors | 1 | Zone 4 | 0 |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 138247421.4765
WHITE | MANHATTAN | Interior Compactors | 2 | Zone 2 | $ |  |  |  |  | 0 | 147306.789 | 0 | 2020 | 138394728.2655
WHITMAN | BROOKLYN | Interior Compactors | 32 | 0 | 0 |  |  |  |  | 0 | 2356908.624 | 0 | 2020 | 140751636.8895
WILLIAMS PLAZA | BROOKLYN | Interior Compactors | 5 | 0 | 0 |  | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 140751636.8895
WILLIAMSBURG | BROOKLYN | Interior Compactors | 134 | 0 | 0 |  | 2020 | Yes |  | 0 | 0 | 0 | 2020 | 140751636.8895
WILSON | MANHATTAN | Interior Compactors | 5 | Zone 2 | $ |  |  |  |  | 0 | 368266.9725 | 0 | 2020 | 141119903.862
WISE TOWERS | MANHATTAN | Interior Compactors | 4 | Zone 4 | 0 |  | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 141119903.862
WOODSIDE | QUEENS | Interior Compactors | 56 | 0 | 0 |  |  |  |  | 0 | 4124590.092 | 0 | 2020 | 145244493.954
WOODSON | BROOKLYN | Interior Compactors | 2 | 0 | 0 |  |  |  |  | 0 | 147306.789 | 0 | 2020 | 145391800.743
WSUR (BROWNSTONES) | MANHATTAN | Interior Compactors | 0 | Zone 4 | 0 |  |  |  |  | 0 | 0 | 0 | 2020 | 145391800.743
WSUR (SITE A) 120 WEST 94TH STREET | MANHATTAN | Interior Compactors | 1 | Zone 4 | 0 |  |  |  |  | 0 | 73653.3945 | 0 | 2020 | 145465454.1375
WSUR (SITE B) 74 WEST 92ND STREET | MANHATTAN | Interior Compactors | 2 | Zone 4 | 0 |  |  |  |  | 0 | 147306.789 | 0 | 2020 | 145612760.9265
WSUR (SITE C) 589 AMSTERDAM AVENUE | MANHATTAN | Interior Compactors | 2 | 0 | 0 |  |  |  |  | 0 | 147306.789 | 0 | 2020 | 145760067.7155
WYCKOFF GARDENS | BROOKLYN | Interior Compactors | 6 | 0 | 0 |  |  |  |  | 0 | 441920.367 | 0 | 2020 | 146201988.0825
Formulas:
AGE (2019) (Y) = IF(VLOOKUP(IntComp[[#This Row],[DEVELOPMENT]],Data[],10,FALSE)=0,"",DATEDIF(VLOOKUP(IntComp[[#This Row],[DEVELOPMENT]],Data[],12,FALSE),TODAY(),"Y"))
Estimate = IF(IntComp[[#This Row],[RAD/PACT by 2025]]="Yes",0,(IntComp[[#This Row],['# Int. Compactors to Replace]]*'Unit Costs'!$B8)*(1+((IntComp[[#This Row],[est. Year]]-YEAR(TODAY()))*L2)))

## Waste Yards
306800621.88
DEVELOPMENT | BOROUGH | WORK TYPE | # Ext. Compactors to Replace | # Bulk Crushers | NRR | Priority Level | E&S Priority | RAD/PACT | RAD/PACT by 2025 | ext comp age? | Estimate | Count | est. Year | Running Cost/Yr | Notes
AMSTERDAM | MANHATTAN | New Waste Yard v4 | 3 | 0 | Zone 4 | 0 |  |  |  | old | 2022307.26
CROWN HEIGHTS | BROOKLYN | New Waste Yard v1 | 0 | 0 | Zone 4 | 0 |  | 2025 | Yes | old | 0
EAST 165TH STREET-BRYANT AVENUE | BRONX | New Waste Yard v1 | 0 | 0 | Zone 4 | 0 |  |  |  | old | 1159792.78
EAST 173RD STREET-VYSE AVENUE | BRONX | New Waste Yard v1 | 0 | 0 | Zone 4 | 0 |  |  |  | old
FHA REPOSSESSED HOUSES (GROUP IX) | 0 | New Waste Yard v1 | 0 | 0 | Zone 4 | 0 |  |  |  | old |  |  |  |  | FHA handles their own waste
FOREST | BRONX | New Waste Yard v4 | 3 | 0 | Zone 4 | 0 |  |  |  | old | 2022307.26
HOWARD AVENUE-PARK PLACE | BROOKLYN | New Waste Yard v1 | 0 | 0 | Zone 4 | 0 |  | 2025 | Yes | old | 0
KINGSBOROUGH EXTENSION | BROOKLYN | New Waste Yard v4 | 0 | 0 | Zone 4 | 0 |  |  |  | old | 2022307.26
MCKINLEY | BRONX | New Waste Yard v3 | 2 | 0 | Zone 4 | 0 |  |  |  | old | 1591050.02
REHAB PROGRAM (WISE REHAB) | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 4 | 0 |  |  |  | old
THOMAS APARTMENTS | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 4 | 0 |  |  |  | old
WEST TREMONT AVENUE-SEDGWICK AVENUE AREA | BRONX | New Waste Yard v1 | 0 | 0 | Zone 4 | 0 |  |  |  | old
WISE TOWERS | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 4 | 0 |  | 2019 | Yes | old | 0
WSUR (BROWNSTONES) | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 4 | 0 |  |  |  | old
WSUR (SITE A) 120 WEST 94TH STREET | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 4 | 0 |  |  |  | old
WSUR (SITE B) 74 WEST 92ND STREET | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 4 | 0 |  |  |  | old | 1159792.78
335 EAST 111TH STREET | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 3 | $ |  |  |  | old | 1159792.78
AUDUBON | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 3 | $$$$ |  | 2020 | Yes | old | 0
BETHUNE GARDENS | MANHATTAN | New Waste Yard v1 | 1 | 0 | Zone 3 | $$ |  | 2020 | Yes | old | 0
BORINQUEN PLAZA I | BROOKLYN | New Waste Yard v3 | 2 | 0 | Zone 3 | $$$$ |  |  |  | old | 1591050.02
BORINQUEN PLAZA II | BROOKLYN | New Waste Yard v1 | 0 | 0 | Zone 3 | $$$ |  |  |  | old | 1159792.78
BRONX RIVER | BRONX | New Waste Yard v4 | 3 | 0 | Zone 3 | $ |  |  |  | old | 2022307.26
CLAREMONT PARKWAY-FRANKLIN AVENUE | BRONX | New Waste Yard v1 | 1 | 0 | Zone 3 | $ |  | 2026 |  | old | 1159792.78
DAVIDSON | BRONX | New Waste Yard v1 | 0 | 0 | Zone 3 | $ |  | 2026 |  | old | 1159792.78
DOUGLASS ADDITION | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 3 | $ | 1 |  |  | old | 1159792.78
DOUGLASS I | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 3 | $$$ |  |  |  | old | 1159792.78
DOUGLASS II | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 3 | $$$ |  |  |  | old | 1159792.78
FORT WASHINGTON AVENUE REHAB | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 3 | $ |  | 2019 | Yes | old | 0
FULTON | MANHATTAN | New Waste Yard v3 | 2 | 0 | Zone 3 | $ |  |  |  | old | 1591050.02
GRAMPION | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 3 | $ |  | 2019 | Yes | old | 0
HARLEM RIVER | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 3 | $ |  | 2020 | Yes | old | 0
HARLEM RIVER II | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 3 | $$ |  | 2020 | Yes | old | 0
KINGSBOROUGH | BROOKLYN | New Waste Yard v1 | 0 | 0 | Zone 3 | $ |  |  |  | old | 1159792.78
MANHATTANVILLE REHAB (GROUP 2) | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 3 | $ |  | 2019 | Yes | old | 0
MANHATTANVILLE REHAB (GROUP 3) | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 3 | $ |  | 2019 | Yes | old | 0
MARSHALL PLAZA | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 3 | $$ |  | 2020 | Yes | old | 0
MONROE | BRONX | New Waste Yard v3 | 2 | 0 | Zone 3 | $ |  |  |  | old | 1591050.02
MOORE | BRONX | New Waste Yard v1 | 1 | 0 | Zone 3 | $$ |  |  |  | old | 1159792.78
PARK AVENUE-EAST 122ND, 123RD STREETS | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 3 | $$ |  | 2019 | Yes | old | 0
PATTERSON | BRONX | New Waste Yard v1 | 0 | 0 | Zone 3 | $$ |  | 2025 | Yes | old | 0
PUBLIC SCHOOL 139 (CONVERSION) | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 3 | $ |  | 2019 | Yes | old | 0
QUEENSBRIDGE NORTH | QUEENS | New Waste Yard v1 | 0 | 0 | Zone 3 | $ |  |  |  | old | 1159792.78
QUEENSBRIDGE SOUTH | QUEENS | New Waste Yard v7 | 6 | 0 | Zone 3 | $ |  |  |  | old | 3316078.98
SAINT MARY'S PARK | BRONX | New Waste Yard v3 | 2 | 0 | Zone 3 | $ |  |  |  | old | 1591050.02
SOUTH BRONX AREA (SITE 402) | BRONX | New Waste Yard v1 | 0 | 0 | Zone 3 | $$ |  | 2026 |  | old | 1159792.78
STEBBINS AVENUE-HEWITT PLACE | BRONX | New Waste Yard v1 | 0 | 0 | Zone 3 | $$$ |  | 2026 |  | old | 1159792.78
UNION AVENUE-EAST 163RD STREET | BRONX | New Waste Yard v1 | 0 | 0 | Zone 3 | $ |  | 2026 |  | old | 1159792.78
UNION AVENUE-EAST 166TH STREET | BRONX | New Waste Yard v1 | 1 | 0 | Zone 3 | $ |  | 2026 |  | old | 1159792.78
WASHINGTON HEIGHTS REHAB PHASE III | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 3 | $ |  | 2019 | Yes | old | 0
131 SAINT NICHOLAS AVENUE | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 2 | $ |  |  |  | old | 1159792.78
CARVER | MANHATTAN | New Waste Yard v4 | 3 | 0 | Zone 2 | $$ |  |  |  | old | 2022307.26
CLINTON | MANHATTAN | New Waste Yard v1 | 1 | 0 | Zone 2 | $$$$ |  |  |  | old | 1159792.78
CORSI HOUSES | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 2 | $ |  | 2026 |  | old | 1159792.78
DREW-HAMILTON | MANHATTAN | New Waste Yard v3 | 2 | 0 | Zone 2 | $ | 1 |  |  | old | 1591050.02 |  |  |  | HUD Waste Management Action Plan pilot
EAST RIVER | MANHATTAN | New Waste Yard v3 | 2 | 0 | Zone 2 | $ |  | 2024 | Yes | old | 0
GRANT | MANHATTAN | New Waste Yard v3 | 2 | 0 | Zone 2 | $$$$ |  |  |  | old | 1591050.02
JEFFERSON | MANHATTAN | New Waste Yard v5 | 4 | 0 | Zone 2 | $$ |  | 2026 |  | old | 2453564.5
JOHNSON | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 2 | $$$ |  | 2028 |  | old | 1159792.78
KING TOWERS | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 2 | $$$ |  |  |  | old | 1159792.78
LEXINGTON | MANHATTAN | New Waste Yard v1 | 1 | 0 | Zone 2 | $ |  | 2023 | Yes | old | 0
LINCOLN | MANHATTAN | New Waste Yard v3 | 2 | 0 | Zone 2 | $$$$ |  |  |  | old | 1591050.02
MANHATTANVILLE | MANHATTAN | New Waste Yard v4 | 3 | 0 | Zone 2 | $ |  | 2028 |  | old | 2022307.26
METRO NORTH PLAZA | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 2 | $ |  |  |  | old | 1159792.78
MORRIS PARK SENIOR CITIZENS HOME | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 2 | $$$$ |  |  |  | old | 1159792.78
POLO GROUNDS TOWERS | MANHATTAN | New Waste Yard v4 | 3 | 0 | Zone 2 | $ |  |  |  | old | 2022307.26
RANGEL | MANHATTAN | New Waste Yard v4 | 3 | 0 | Zone 2 | $ |  |  |  | old | 2022307.26
ROBINSON | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 2 | $$ |  |  |  | old | 1159792.78
SAINT NICHOLAS | MANHATTAN | New Waste Yard v4 | 3 | 0 | Zone 2 | $ |  |  |  | old | 2022307.26
SAMUEL (CITY) | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 2 | $$ |  | 2026 |  | old | 1159792.78
TAFT | MANHATTAN | New Waste Yard v5 | 4 | 0 | Zone 2 | $$$ | 1 |  |  | old | 2453564.5
UPACA (SITE 5) | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 2 | $ |  |  |  | old | 1159792.78
UPACA (SITE 6) | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 2 | $ |  |  |  | old | 1159792.78
WAGNER | MANHATTAN | New Waste Yard v5 | 4 | 0 | Zone 2 | $ |  |  |  | old | 2453564.5
WASHINGTON | MANHATTAN | New Waste Yard v1 | 1 | 1 | Zone 2 | $$$ |  | 2023 | Yes | old | 0
WHITE | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 2 | $ |  |  |  | old | 1159792.78
WILSON | MANHATTAN | New Waste Yard v3 | 2 | 0 | Zone 2 | $ |  |  |  | old | 1591050.02
303 VERNON AVENUE | BROOKLYN | New Waste Yard v1 | 0 | 0 | Zone 1 | $ |  |  |  | old | 1159792.78
45 ALLEN STREET | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 1 | $$ |  |  |  | old | 1159792.78
ARMSTRONG I | BROOKLYN | New Waste Yard v1 | 0 | 0 | Zone 1 | $ |  |  |  | old | 1159792.78
ARMSTRONG II | BROOKLYN | New Waste Yard v1 | 0 | 0 | Zone 1 | $ |  |  |  | old | 1159792.78
BARUCH | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 1 | $ |  |  |  | old | 1159792.78
BARUCH HOUSES ADDITION | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 1 | $ |  |  |  | old | 1159792.78
BEDFORD-STUYVESANT REHAB | BROOKLYN | New Waste Yard v1 | 0 | 0 | Zone 1 | $ |  |  |  | old | 1159792.78
BRACETTI PLAZA | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 1 | $ |  | 2026 |  | old | 1159792.78
BUSHWICK | BROOKLYN | New Waste Yard v3 | 2 | 0 | Zone 1 | $$ |  |  |  | old | 1591050.02
BUSHWICK II (GROUPS A & C) | BROOKLYN | New Waste Yard v1 | 0 | 0 | Zone 1 | 0 |  |  |  | old | 1159792.78
BUSHWICK II CDA (GROUP E) | BROOKLYN | New Waste Yard v1 | 0 | 0 | Zone 1 | 0 |  | 2019 | Yes | old | 0
BUTLER | BRONX | New Waste Yard v3 | 2 | 0 | Zone 1 | $$ |  |  |  | old | 1591050.02
CAMPOS PLAZA II | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 1 | $$ |  | 2026 |  | old | 1159792.78
CLAREMONT REHAB (GROUP 2) | BRONX | New Waste Yard v1 | 0 | 0 | Zone 1 | $ |  | 2025 | Yes | old | 0
CLAREMONT REHAB (GROUP 3) | BRONX | New Waste Yard v1 | 0 | 0 | Zone 1 | $ |  | 2025 | Yes | old | 0
CLAREMONT REHAB (GROUP 4) | BRONX | New Waste Yard v1 | 0 | 0 | Zone 1 | $ |  | 2025 | Yes | old | 0
CLAREMONT REHAB (GROUP 5) | BRONX | New Waste Yard v1 | 0 | 0 | Zone 1 | $ |  | 2025 | Yes | old | 0
COLLEGE AVENUE-EAST 165TH STREET | BRONX | New Waste Yard v1 | 0 | 0 | Zone 1 | $ |  | 2025 | Yes | old | 0
EAST 180TH STREET-MONTEREY AVENUE | BRONX | New Waste Yard v1 | 1 | 0 | Zone 1 | $$ |  |  |  | old | 1159792.78
FIRST HOUSES | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 1 | $ |  | 2026 |  | old | 1159792.78
GOMPERS | MANHATTAN | New Waste Yard v1 | 1 | 0 | Zone 1 | $ |  |  |  | old | 1159792.78
HERNANDEZ | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 1 | $$ |  |  |  | old | 1159792.78
HIGHBRIDGE GARDENS | BRONX | New Waste Yard v3 | 2 | 0 | Zone 1 | $ |  |  |  | old | 1591050.02
HOPE GARDENS | BROOKLYN | New Waste Yard v1 | 0 | 0 | Zone 1 | 0 |  | 2019 | Yes | old | 0
HYLAN | BROOKLYN | New Waste Yard v1 | 0 | 0 | Zone 1 | $ |  |  |  | old | 1159792.78
JACKSON | BRONX | New Waste Yard v3 | 2 | 0 | Zone 1 | $ |  |  |  | old | 1591050.02
LA GUARDIA | MANHATTAN | New Waste Yard v3 | 2 | 0 | Zone 1 | $$ |  |  |  | old | 1591050.02 |  |  |  | Need to ask Real Estate about yard location
LA GUARDIA ADDITION | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 1 | $ |  |  |  | old | 1159792.78
LAFAYETTE | BROOKLYN | New Waste Yard v3 | 2 | 0 | Zone 1 | $$$ |  |  |  | old | 1591050.02
LOWER EAST SIDE I INFILL | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 1 | $$ |  |  |  | old | 1159792.78
LOWER EAST SIDE II | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 1 | $ |  | 2026 |  | old | 1159792.78
LOWER EAST SIDE III | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 1 | $ |  |  |  | old | 1159792.78
LOWER EAST SIDE REHAB (GROUP 5) | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 1 | $$ |  | 2026 |  | old | 1159792.78
MARCY | BROOKLYN | New Waste Yard v4 | 3 | 0 | Zone 1 | $$ |  | 2027 |  | old | 2022307.26
MARCY AVENUE-GREENE AVENUE SITE A | BROOKLYN | New Waste Yard v1 | 0 | 0 | Zone 1 | $ |  | 2019 | Yes | old | 0
MELROSE | BRONX | New Waste Yard v3 | 2 | 0 | Zone 1 | $ | 1 | 2023 | Yes | old | 0
MELTZER TOWER | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 1 | $ |  |  |  | old | 1159792.78
MORRIS I | BRONX | New Waste Yard v4 | 3 | 0 | Zone 1 | $$ |  |  |  | old | 2022307.26
MORRIS II | BRONX | New Waste Yard v3 | 2 | 0 | Zone 1 | $$$ |  |  |  | old | 1591050.02
MORRISANIA | BRONX | New Waste Yard v1 | 0 | 0 | Zone 1 | $$$$ | 1 |  |  | old | 1159792.78
MORRISANIA AIR RIGHTS | BRONX | New Waste Yard v1 | 0 | 0 | Zone 1 | $ |  |  |  | old | 1159792.78
RIIS | MANHATTAN | New Waste Yard v3 | 2 | 0 | Zone 1 | $ | 1 |  |  | old | 1591050.02
RIIS II | MANHATTAN | New Waste Yard v1 | 1 | 0 | Zone 1 | $$ |  |  |  | old | 1159792.78
ROOSEVELT I | BROOKLYN | New Waste Yard v1 | 0 | 0 | Zone 1 | $ |  |  |  | old | 1159792.78
ROOSEVELT II | BROOKLYN | New Waste Yard v1 | 0 | 0 | Zone 1 | $ |  |  |  | old | 1159792.78
RUTGERS | MANHATTAN | New Waste Yard v1 | 1 | 0 | Zone 1 | $ |  |  |  | old | 1159792.78
SEWARD PARK EXTENSION | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 1 | $ |  |  |  | old | 1159792.78
SMITH | MANHATTAN | New Waste Yard v5 | 4 | 0 | Zone 1 | $ |  |  |  | old | 2453564.5
SUMNER | BROOKLYN | New Waste Yard v3 | 2 | 0 | Zone 1 | $ |  |  |  | old | 1591050.02
TELLER AVENUE-EAST 166TH STREET | BRONX | New Waste Yard v1 | 0 | 0 | Zone 1 | $ |  | 2025 | Yes | old | 0
TOMPKINS | BROOKLYN | New Waste Yard v1 | 0 | 0 | Zone 1 | $ |  |  |  | old | 1159792.78
TWIN PARKS EAST (SITE 9) | BRONX | New Waste Yard v1 | 0 | 0 | Zone 1 | $ |  |  |  | old | 1159792.78
TWO BRIDGES URA (SITE 7) | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 1 | $ |  |  |  | old | 1159792.78
VLADECK | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 1 | $$ |  |  |  | old | 1159792.78
VLADECK II | MANHATTAN | New Waste Yard v1 | 0 | 0 | Zone 1 | $ |  |  |  | old | 1159792.78
WALD | MANHATTAN | New Waste Yard v4 | 3 | 0 | Zone 1 | $ |  |  |  | old | 2022307.26
WEBSTER | BRONX | New Waste Yard v3 | 2 | 0 | Zone 1 | $ |  |  |  | old | 1591050.02
1010 EAST 178TH STREET | BRONX | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
104-14 TAPSCOTT STREET | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2021 | Yes | old | 0
1162-1176 WASHINGTON AVENUE | BRONX | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2025 | Yes | old | 0
1471 WATSON AVENUE | BRONX | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2021 | Yes | old | 0
154 WEST 84TH STREET | MANHATTAN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
344 EAST 28TH STREET | MANHATTAN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
572 WARREN STREET | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
830 AMSTERDAM AVENUE | MANHATTAN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
ADAMS | BRONX | New Waste Yard v3 | 2 | 0 | 0 | 0 |  |  |  | old | 1591050.02
ALBANY | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2025 | Yes | old | 0
ALBANY II | BROOKLYN | New Waste Yard v4 | 3 | 0 | 0 | 0 |  | 2025 | Yes | old | 0
AMSTERDAM ADDITION | MANHATTAN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
ASTORIA | QUEENS | New Waste Yard v4 | 3 | 0 | 0 | 0 |  | 2024 | Yes | old | 0
ATLANTIC TERMINAL SITE 4B | BROOKLYN | New Waste Yard v1 | 1 | 0 | 0 | 0 |  |  |  | old | 1159792.78
BAILEY AVENUE-WEST 193RD STREET | BRONX | New Waste Yard v1 | 1 | 0 | 0 | 0 |  |  |  | old | 1159792.78
BAISLEY PARK | QUEENS | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
BAY VIEW | BROOKLYN | New Waste Yard v5 | 4 | 0 | 0 | 0 |  |  |  | old | 2453564.5
BEACH 41ST STREET-BEACH CHANNEL DRIVE | QUEENS | New Waste Yard v1 | 1 | 0 | 0 | 0 |  |  |  | old | 1159792.78
BELMONT-SUTTER AREA | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
BERRY | STATEN ISLAND | New Waste Yard v1 | 1 | 0 | 0 | 0 |  |  |  | old | 1159792.78
BERRY STREET-SOUTH 9TH STREET | BROOKLYN | New Waste Yard v1 | 1 | 0 | 0 | 0 |  |  |  | old | 1159792.78
BLAND | QUEENS | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
BOSTON ROAD PLAZA | BRONX | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2022 | Yes | old | 0
BOSTON SECOR | BRONX | New Waste Yard v3 | 2 | 0 | 0 | 0 |  |  |  | old | 1591050.02
BOULEVARD | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2020 | Yes | old | 0
BOYNTON AVENUE REHAB | BRONX | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
BREUKELEN | BROOKLYN | New Waste Yard v5 | 4 | 0 | 0 | 0 |  | 2021 | Yes | old | 0
BREVOORT | BROOKLYN | New Waste Yard v3 | 2 | 0 | 0 | 0 |  |  |  | old | 1591050.02
BRONX RIVER ADDITION | BRONX | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
BROWN | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
BROWNSVILLE | BROOKLYN | New Waste Yard v4 | 3 | 0 | 0 | 0 |  |  |  | old | 2022307.26
BRYANT AVENUE-EAST 174TH STREET | BRONX | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
BUSHWICK II (GROUPS B & D) | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
CAREY GARDENS | BROOKLYN | New Waste Yard v3 | 2 | 0 | 0 | 0 |  |  |  | old | 1591050.02
CARLETON MANOR | QUEENS | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
CASSIDY-LAFAYETTE | STATEN ISLAND | New Waste Yard v1 | 1 | 0 | 0 | 0 |  |  |  | old | 1159792.78
CASTLE HILL | BRONX | New Waste Yard v5 | 4 | 0 | 0 | 0 |  |  |  | old | 2453564.5
CHELSEA | MANHATTAN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
CHELSEA ADDITION | MANHATTAN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
CLASON POINT GARDENS | BRONX | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2024 | Yes | old | 0
CONEY ISLAND | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 | 1 |  |  | old | 1159792.78
CONEY ISLAND I (SITE 1B) | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
CONEY ISLAND I (SITE 8) | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
CONEY ISLAND I (SITES 4 & 5) | BROOKLYN | New Waste Yard v1 | 1 | 1 | 0 | 0 |  |  |  | old | 1159792.78
CONLON LIHFE TOWER | QUEENS | New Waste Yard v3 | 2 | 0 | 0 | 0 |  |  |  | old | 1591050.02
COOPER PARK | BROOKLYN | New Waste Yard v3 | 2 | 0 | 0 | 0 |  |  |  | old | 1591050.02
CYPRESS HILLS | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2023 | Yes | old | 0
DE HOSTOS APARTMENTS | MANHATTAN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
DOUGLASS | MANHATTAN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
DYCKMAN | MANHATTAN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
EAGLE AVENUE-EAST 163RD STREET | BRONX | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
EAST 152ND STREET-COURTLANDT AVENUE | BRONX | New Waste Yard v1 | 1 | 0 | 0 | 0 |  | 2023 | Yes | old | 0
EAST NEW YORK CITY LINE | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2023 | Yes | old | 0
EASTCHESTER GARDENS | BRONX | New Waste Yard v3 | 2 | 0 | 0 | 0 |  | 2026 |  | old | 1591050.02
EDENWALD | BRONX | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2022 | Yes | old | 0
ELLIOTT | MANHATTAN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
FARRAGUT | BROOKLYN | New Waste Yard v1 | 1 | 0 | 0 | 0 |  | 2027 |  | old | 1159792.78
FENIMORE-LEFFERTS | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2021 | Yes | old | 0
FHA REPOSSESSED HOUSES (GROUP I) | 0 | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old |  |  |  |  | FHA handles their own waste
FHA REPOSSESSED HOUSES (GROUP II) | 0 | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old |  |  |  |  | FHA handles their own waste
FHA REPOSSESSED HOUSES (GROUP III) | 0 | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old |  |  |  |  | FHA handles their own waste
FHA REPOSSESSED HOUSES (GROUP IV) | 0 | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old |  |  |  |  | FHA handles their own waste
FHA REPOSSESSED HOUSES (GROUP V) | 0 | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old |  |  |  |  | FHA handles their own waste
FHA REPOSSESSED HOUSES (GROUP VI) | 0 | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old |  |  |  |  | FHA handles their own waste
FHA REPOSSESSED HOUSES (GROUP VII) | 0 | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old |  |  |  |  | FHA handles their own waste
FHA REPOSSESSED HOUSES (GROUP VIII) | 0 | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old |  |  |  |  | FHA handles their own waste
FHA REPOSSESSED HOUSES (GROUP X) | 0 | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old |  |  |  |  | FHA handles their own waste
FIORENTINO PLAZA | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2026 |  | old | 1159792.78
FORT INDEPENDENCE STREET-HEATH AVENUE | BRONX | New Waste Yard v1 | 1 | 0 | 0 | 0 |  |  |  | old | 1159792.78
GARVEY (GROUP A) | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
GLEBE AVENUE-WESTCHESTER AVENUE | BRONX | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2021 | Yes | old | 0
GLENMORE PLAZA | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
GLENWOOD | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2028 |  | old | 1159792.78
GOWANUS | BROOKLYN | New Waste Yard v4 | 3 | 0 | 0 | 0 |  |  |  | old | 2022307.26
GRAVESEND | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
GUN HILL | BRONX | New Waste Yard v3 | 2 | 0 | 0 | 0 |  |  |  | old | 1591050.02
HABER | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
HAMMEL | QUEENS | New Waste Yard v3 | 2 | 0 | 0 | 0 |  |  |  | old | 1591050.02
HARBORVIEW TERRACE | MANHATTAN | New Waste Yard v1 | 1 | 0 | 0 | 0 |  |  |  | old | 1159792.78
HARRISON AVENUE REHAB (GROUP A) | BRONX | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
HARRISON AVENUE REHAB (GROUP B) | BRONX | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
HOE AVENUE-EAST 173RD STREET | BRONX | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
HOLMES TOWERS | MANHATTAN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
HOWARD | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
HOWARD AVENUE | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2025 | Yes | old | 0
HUGHES APARTMENTS | BROOKLYN | New Waste Yard v1 | 1 | 0 | 0 | 0 |  |  |  | old | 1159792.78
HUNTS POINT AVENUE REHAB | BRONX | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
INDEPENDENCE | BROOKLYN | New Waste Yard v3 | 2 | 0 | 0 | 0 |  | 2019 | Yes | old | 0
INGERSOLL | BROOKLYN | New Waste Yard v3 | 2 | 0 | 0 | 0 |  |  |  | old | 1591050.02
INTERNATIONAL TOWER | QUEENS | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
ISAACS | MANHATTAN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
LATIMER GARDENS | QUEENS | New Waste Yard v1 | 1 | 0 | 0 | 0 |  |  |  | old | 1159792.78
LAVANBURG HOMES | MANHATTAN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
LEAVITT STREET-34TH AVENUE | QUEENS | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
LEHMAN VILLAGE | MANHATTAN | New Waste Yard v3 | 2 | 0 | 0 | 0 |  |  |  | old | 1591050.02
LENOX ROAD-ROCKAWAY PARKWAY | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2021 | Yes | old | 0
LINDEN | BROOKLYN | New Waste Yard v1 | 0 | 1 | 0 | 0 |  | 2020 | Yes | old | 0
LONG ISLAND BAPTIST HOUSES | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2026 |  | old | 1159792.78
LONGFELLOW AVENUE REHAB | BRONX | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
LOW HOUSES | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 | 1 |  |  | old | 1159792.78
MARBLE HILL | BRONX | New Waste Yard v4 | 3 | 0 | 0 | 0 |  |  |  | old | 2022307.26
MARCY AVENUE-GREENE AVENUE SITE B | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2019 | Yes | old | 0
MARINER'S HARBOR | STATEN ISLAND | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2028 |  | old | 1159792.78
MARLBORO | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
MIDDLETOWN PLAZA | BRONX | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2026 |  | old | 1159792.78
MILL BROOK | BRONX | New Waste Yard v4 | 3 | 0 | 0 | 0 |  |  |  | old | 2022307.26
MILL BROOK EXTENSION | BRONX | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
MITCHEL | BRONX | New Waste Yard v5 | 4 | 0 | 0 | 0 |  |  |  | old | 2453564.5
MOTT HAVEN | BRONX | New Waste Yard v3 | 2 | 0 | 0 | 0 |  |  |  | old | 1591050.02
NEW LANE AREA | STATEN ISLAND | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
NOSTRAND | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2028 |  | old | 1159792.78
OCEAN BAY APARTMENTS (OCEANSIDE) | QUEENS | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
OCEAN HILL APARTMENTS | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
OCEAN HILL-BROWNSVILLE | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2025 | Yes | old | 0
O'DWYER GARDENS | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
PALMETTO GARDENS | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2019 | Yes | old | 0
PARK ROCK REHAB | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2025 | Yes | old | 0
PARKSIDE | BRONX | New Waste Yard v3 | 2 | 0 | 0 | 0 |  |  |  | old | 1591050.02
PELHAM PARKWAY | BRONX | New Waste Yard v4 | 3 | 0 | 0 | 0 |  | 2022 | Yes | old | 0
PENNSYLVANIA AVENUE-WORTMAN AVENUE | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
PINK | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
POMONOK | QUEENS | New Waste Yard v6 | 5 | 0 | 0 | 0 |  | 2027 |  | old | 2884821.74
PSS GRANDPARENT FAMILY APARTMENTS | BRONX | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
RALPH AVENUE REHAB | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2021 | Yes | old | 0
RANDALL AVENUE-BALCOM AVENUE | BRONX | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2022 | Yes | old | 0
RANDOLPH SOUTH | MANHATTAN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
RAVENSWOOD | QUEENS | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
RED HOOK EAST | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2024 | Yes | old | 0
RED HOOK WEST | BROOKLYN | New Waste Yard v3 | 2 | 0 | 0 | 0 |  | 2025 | Yes | old | 0
REDFERN | QUEENS | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2022 | Yes | old | 0
REHAB PROGRAM (COLLEGE POINT) | QUEENS | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
REHAB PROGRAM (DOUGLASS REHABS) | MANHATTAN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
REHAB PROGRAM (TAFT REHABS) | MANHATTAN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
REID APARTMENTS | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2021 | Yes | old | 0
RICHMOND TERRACE | STATEN ISLAND | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
ROBBINS PLAZA | MANHATTAN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
RUTLAND TOWERS | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2021 | Yes | old | 0
SACK WERN | BRONX | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2024 | Yes | old | 0
SAMUEL (MHOP) I | MANHATTAN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2019 | Yes | old | 0
SAMUEL (MHOP) II | MANHATTAN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2019 | Yes | old | 0
SAMUEL (MHOP) III | MANHATTAN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2019 | Yes | old | 0
SARATOGA VILLAGE | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
SEDGWICK | BRONX | New Waste Yard v3 | 2 | 0 | 0 | 0 |  |  |  | old | 1591050.02
SHEEPSHEAD BAY | BROOKLYN | New Waste Yard v7 | 6 | 0 | 0 | 0 |  | 2028 |  | old | 3316078.98
SHELTON HOUSE | QUEENS | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
SOTOMAYOR HOUSES | BRONX | New Waste Yard v4 | 3 | 0 | 0 | 0 |  |  |  | old | 2022307.26
SOUNDVIEW | BRONX | New Waste Yard v5 | 4 | 0 | 0 | 0 |  | 2023 | Yes | old | 0
SOUTH BEACH | STATEN ISLAND | New Waste Yard v1 | 1 | 0 | 0 | 0 |  |  |  | old | 1159792.78
SOUTH JAMAICA I | QUEENS | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2021 | Yes | old | 0
SOUTH JAMAICA II | QUEENS | New Waste Yard v5 | 4 | 0 | 0 | 0 |  | 2021 | Yes | old | 0
STANTON STREET | MANHATTAN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
STAPLETON | STATEN ISLAND | New Waste Yard v3 | 2 | 0 | 0 | 0 |  |  |  | old | 1591050.02
STERLING PLACE REHABS (SAINT JOHNS-STERLING) | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2025 | Yes | old | 0
STERLING PLACE REHABS (STERLING-BUFFALO) | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2025 | Yes | old | 0
STRAUS | MANHATTAN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
STUYVESANT GARDENS I | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
STUYVESANT GARDENS II | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
SURFSIDE GARDENS | BROOKLYN | New Waste Yard v1 | 1 | 0 | 0 | 0 |  |  |  | old | 1159792.78
SUTTER AVENUE-UNION STREET | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2021 | Yes | old | 0
TAPSCOTT STREET REHAB | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2021 | Yes | old | 0
TAYLOR STREET-WYTHE AVENUE | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
THROGGS NECK | BRONX | New Waste Yard v7 | 6 | 0 | 0 | 0 |  | 2022 | Yes | old | 0
THROGGS NECK ADDITION | BRONX | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2022 | Yes | old | 0
TILDEN | BROOKLYN | New Waste Yard v3 | 2 | 0 | 0 | 0 | 1 |  |  | old | 1591050.02
TODT HILL | STATEN ISLAND | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
UNITY PLAZA (SITES 17,24,25A) | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2026 |  | old | 1159792.78
UNITY PLAZA (SITES 4-27) | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2026 |  | old | 1159792.78
UNIVERSITY AVENUE REHAB | BRONX | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
VAN DYKE I | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2024 | Yes | old | 0
VAN DYKE II | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
VANDALIA AVENUE | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
WASHINGTON HEIGHTS REHAB (GROUPS 1&2) | MANHATTAN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2019 | Yes | old | 0
WASHINGTON HEIGHTS REHAB PHASE III (FORT WASHINGTON) | MANHATTAN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
WASHINGTON HEIGHTS REHAB PHASE III (HARLEM RIVER) | MANHATTAN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
WASHINGTON HEIGHTS REHAB PHASE IV (C) | MANHATTAN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2019 | Yes | old | 0
WASHINGTON HEIGHTS REHAB PHASE IV (D) | MANHATTAN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2019 | Yes | old | 0
WEEKSVILLE GARDENS | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2019 | Yes | old | 0
WEST BRIGHTON I | STATEN ISLAND | New Waste Yard v3 | 2 | 0 | 0 | 0 |  |  |  | old | 1591050.02
WEST BRIGHTON II | STATEN ISLAND | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
WEST FARMS ROAD REHAB | BRONX | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
WEST FARMS SQUARE CONVENTIONAL | BRONX | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
WHITMAN | BROOKLYN | New Waste Yard v4 | 3 | 0 | 0 | 0 |  |  |  | old | 2022307.26
WILLIAMS PLAZA | BROOKLYN | New Waste Yard v1 | 0 | 1 | 0 | 0 |  | 2019 | Yes | old | 0
WILLIAMSBURG | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  | 2020 | Yes | old | 0
WOODSIDE | QUEENS | New Waste Yard v4 | 3 | 0 | 0 | 0 |  |  |  | old | 2022307.26
WOODSON | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
WSUR (SITE C) 589 AMSTERDAM AVENUE | MANHATTAN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78
WYCKOFF GARDENS | BROOKLYN | New Waste Yard v1 | 0 | 0 | 0 | 0 |  |  |  | old | 1159792.78

## Ext. Compactor Pipeline (hidden)
[9 empty] | inflation |  | 2020
3.5%
DEVELOPMENT | BOROUGH | WORK TYPE | NRR | Priority Level | RAD/PACT | RAD/PACT by 2025 | AGE (2019) (Y) | # to Replace | Cost per Development | Count | est. Year | Running Cost/Yr | DSNY Priority | DSNY Comments
WYCKOFF GARDENS | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
WSUR (SITE C) 589 AMSTERDAM AVENUE | MANHATTAN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
WSUR (SITE B) 74 WEST 92ND STREET | MANHATTAN | Exterior Compactors | Zone 4 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
WSUR (SITE A) 120 WEST 94TH STREET | MANHATTAN | Exterior Compactors | Zone 4 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
WSUR (BROWNSTONES) | MANHATTAN | Exterior Compactors | Zone 4 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
WOODSON | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
WOODSIDE | QUEENS | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
WISE TOWERS | MANHATTAN |  | Zone 4 | 0 | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 0
WILSON | MANHATTAN | Exterior Compactors | Zone 2 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
WILLIAMSBURG | BROOKLYN |  | 0 | 0 | 2020 | Yes |  | 0 | 0 | 0 | 2020 | 0
WILLIAMS PLAZA | BROOKLYN |  | 0 | 0 | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 0
WHITMAN | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
WHITE | MANHATTAN | Exterior Compactors | Zone 2 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
WEST TREMONT AVENUE-SEDGWICK AVENUE AREA | BRONX | Exterior Compactors | Zone 4 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
WEST FARMS SQUARE CONVENTIONAL | BRONX | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
WEST FARMS ROAD REHAB | BRONX | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
WEST BRIGHTON II | STATEN ISLAND | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
WEST BRIGHTON I | STATEN ISLAND | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
WEEKSVILLE GARDENS | BROOKLYN |  | 0 | 0 | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 0
WEBSTER | BRONX | Exterior Compactors | Zone 1 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
WASHINGTON HEIGHTS REHAB PHASE IV (D) | MANHATTAN |  | 0 | 0 | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 0
WASHINGTON HEIGHTS REHAB PHASE IV (C) | MANHATTAN |  | 0 | 0 | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 0
WASHINGTON HEIGHTS REHAB PHASE III (HARLEM RIVER) | MANHATTAN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
WASHINGTON HEIGHTS REHAB PHASE III (FORT WASHINGTON) | MANHATTAN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
WASHINGTON HEIGHTS REHAB PHASE III | MANHATTAN | Exterior Compactors | Zone 3 | $ | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 0
WASHINGTON HEIGHTS REHAB (GROUPS 1&2) | MANHATTAN |  | 0 | 0 | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 0
WASHINGTON | MANHATTAN | Exterior Compactors | Zone 2 | $$$ | 2023 | Yes |  | 0 | 0 | 0 | 2020 | 0
WALD | MANHATTAN | Exterior Compactors | Zone 1 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
WAGNER | MANHATTAN | Exterior Compactors | Zone 2 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
VLADECK II | MANHATTAN | Exterior Compactors | Zone 1 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
VLADECK | MANHATTAN | Exterior Compactors | Zone 1 | $$ |  |  |  | 0 | 0 | 0 | 2020 | 0
VANDALIA AVENUE | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
VAN DYKE II | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
VAN DYKE I | BROOKLYN |  | 0 | 0 | 2024 | Yes |  | 0 | 0 | 0 | 2020 | 0
UPACA (SITE 6) | MANHATTAN | Exterior Compactors | Zone 2 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
UPACA (SITE 5) | MANHATTAN | Exterior Compactors | Zone 2 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
UNIVERSITY AVENUE REHAB | BRONX | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
UNITY PLAZA (SITES 4-27) | BROOKLYN | Exterior Compactors | 0 | 0 | 2026 |  |  | 0 | 0 | 0 | 2020 | 0
UNITY PLAZA (SITES 17,24,25A) | BROOKLYN | Exterior Compactors | 0 | 0 | 2026 |  |  | 0 | 0 | 0 | 2020 | 0
UNION AVENUE-EAST 166TH STREET | BRONX | Exterior Compactors | Zone 3 | $ | 2026 |  |  | 0 | 0 | 0 | 2020 | 0
UNION AVENUE-EAST 163RD STREET | BRONX | Exterior Compactors | Zone 3 | $ | 2026 |  |  | 0 | 0 | 0 | 2020 | 0
TWO BRIDGES URA (SITE 7) | MANHATTAN | Exterior Compactors | Zone 1 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
TWIN PARKS EAST (SITE 9) | BRONX | Exterior Compactors | Zone 1 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
TOMPKINS | BROOKLYN | Exterior Compactors | Zone 1 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
TODT HILL | STATEN ISLAND | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
TILDEN | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
THROGGS NECK ADDITION | BRONX |  | 0 | 0 | 2022 | Yes |  | 0 | 0 | 0 | 2020 | 0
THROGGS NECK | BRONX |  | 0 | 0 | 2022 | Yes |  | 0 | 0 | 0 | 2020 | 0
THOMAS APARTMENTS | MANHATTAN | Exterior Compactors | Zone 4 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
TELLER AVENUE-EAST 166TH STREET | BRONX | Exterior Compactors | Zone 1 | $ | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 0
TAYLOR STREET-WYTHE AVENUE | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
TAPSCOTT STREET REHAB | BROOKLYN |  | 0 | 0 | 2021 | Yes |  | 0 | 0 | 0 | 2020 | 0
TAFT | MANHATTAN | Exterior Compactors | Zone 2 | $$$ |  |  |  | 0 | 0 | 0 | 2020 | 0
SUTTER AVENUE-UNION STREET | BROOKLYN |  | 0 | 0 | 2021 | Yes |  | 0 | 0 | 0 | 2020 | 0
SURFSIDE GARDENS | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
SUMNER | BROOKLYN | Exterior Compactors | Zone 1 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
STUYVESANT GARDENS II | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
STUYVESANT GARDENS I | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
STRAUS | MANHATTAN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
STERLING PLACE REHABS (STERLING-BUFFALO) | BROOKLYN | Exterior Compactors | 0 | 0 | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 0
STERLING PLACE REHABS (SAINT JOHNS-STERLING) | BROOKLYN | Exterior Compactors | 0 | 0 | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 0
STEBBINS AVENUE-HEWITT PLACE | BRONX | Exterior Compactors | Zone 3 | $$$ | 2026 |  |  | 0 | 0 | 0 | 2020 | 0
STAPLETON | STATEN ISLAND | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
STANTON STREET | MANHATTAN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
SOUTH JAMAICA II | QUEENS |  | 0 | 0 | 2021 | Yes |  | 0 | 0 | 0 | 2020 | 0
SOUTH JAMAICA I | QUEENS |  | 0 | 0 | 2021 | Yes |  | 0 | 0 | 0 | 2020 | 0
SOUTH BRONX AREA (SITE 402) | BRONX | Exterior Compactors | Zone 3 | $$ | 2026 |  |  | 0 | 0 | 0 | 2020 | 0
SOUTH BEACH | STATEN ISLAND | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
SOUNDVIEW | BRONX |  | 0 | 0 | 2023 | Yes |  | 0 | 0 | 0 | 2020 | 0
SOTOMAYOR HOUSES | BRONX | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
SMITH | MANHATTAN | Exterior Compactors | Zone 1 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
SHELTON HOUSE | QUEENS | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
SHEEPSHEAD BAY | BROOKLYN | Exterior Compactors | 0 | 0 | 2028 |  |  | 0 | 0 | 0 | 2020 | 0
SEWARD PARK EXTENSION | MANHATTAN | Exterior Compactors | Zone 1 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
SEDGWICK | BRONX | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
SARATOGA VILLAGE | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
SAMUEL (MHOP) III | MANHATTAN |  | 0 | 0 | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 0
SAMUEL (MHOP) II | MANHATTAN |  | 0 | 0 | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 0
SAMUEL (MHOP) I | MANHATTAN |  | 0 | 0 | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 0
SAMUEL (CITY) | MANHATTAN | Exterior Compactors | Zone 2 | $$ | 2026 |  |  | 0 | 0 | 0 | 2020 | 0
SAINT NICHOLAS | MANHATTAN | Exterior Compactors | Zone 2 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
SAINT MARY'S PARK | BRONX | Exterior Compactors | Zone 3 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
SACK WERN | BRONX |  | 0 | 0 | 2024 | Yes |  | 0 | 0 | 0 | 2020 | 0
RUTLAND TOWERS | BROOKLYN |  | 0 | 0 | 2021 | Yes |  | 0 | 0 | 0 | 2020 | 0
RUTGERS | MANHATTAN | Exterior Compactors | Zone 1 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
ROOSEVELT II | BROOKLYN | Exterior Compactors | Zone 1 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
ROOSEVELT I | BROOKLYN | Exterior Compactors | Zone 1 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
ROBINSON | MANHATTAN | Exterior Compactors | Zone 2 | $$ |  |  |  | 0 | 0 | 0 | 2020 | 0
ROBBINS PLAZA | MANHATTAN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
RIIS II | MANHATTAN | Exterior Compactors | Zone 1 | $$ |  |  |  | 0 | 0 | 0 | 2020 | 0
RIIS | MANHATTAN | Exterior Compactors | Zone 1 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
RICHMOND TERRACE | STATEN ISLAND | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
REID APARTMENTS | BROOKLYN |  | 0 | 0 | 2021 | Yes |  | 0 | 0 | 0 | 2020 | 0
REHAB PROGRAM (WISE REHAB) | MANHATTAN | Exterior Compactors | Zone 4 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
REHAB PROGRAM (TAFT REHABS) | MANHATTAN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
REHAB PROGRAM (DOUGLASS REHABS) | MANHATTAN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
REHAB PROGRAM (COLLEGE POINT) | QUEENS | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
REDFERN | QUEENS |  | 0 | 0 | 2022 | Yes |  | 0 | 0 | 0 | 2020 | 0
RED HOOK WEST | BROOKLYN | Exterior Compactors | 0 | 0 | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 0
RED HOOK EAST | BROOKLYN |  | 0 | 0 | 2024 | Yes |  | 0 | 0 | 0 | 2020 | 0
RAVENSWOOD | QUEENS | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
RANGEL | MANHATTAN | Exterior Compactors | Zone 2 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
RANDOLPH SOUTH | MANHATTAN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
RANDALL AVENUE-BALCOM AVENUE | BRONX |  | 0 | 0 | 2022 | Yes |  | 0 | 0 | 0 | 2020 | 0
RALPH AVENUE REHAB | BROOKLYN |  | 0 | 0 | 2021 | Yes |  | 0 | 0 | 0 | 2020 | 0
QUEENSBRIDGE SOUTH | QUEENS | Exterior Compactors | Zone 3 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
QUEENSBRIDGE NORTH | QUEENS | Exterior Compactors | Zone 3 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
PUBLIC SCHOOL 139 (CONVERSION) | MANHATTAN | Exterior Compactors | Zone 3 | $ | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 0
PSS GRANDPARENT FAMILY APARTMENTS | BRONX | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
POMONOK | QUEENS | Exterior Compactors | 0 | 0 | 2027 |  |  | 0 | 0 | 0 | 2020 | 0
POLO GROUNDS TOWERS | MANHATTAN | Exterior Compactors | Zone 2 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
PINK | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
PENNSYLVANIA AVENUE-WORTMAN AVENUE | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
PELHAM PARKWAY | BRONX |  | 0 | 0 | 2022 | Yes |  | 0 | 0 | 0 | 2020 | 0
PATTERSON | BRONX | Exterior Compactors | Zone 3 | $$ | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 0
PARKSIDE | BRONX | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
PARK ROCK REHAB | BROOKLYN | Exterior Compactors | 0 | 0 | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 0
PARK AVENUE-EAST 122ND, 123RD STREETS | MANHATTAN | Exterior Compactors | Zone 3 | $$ | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 0
PALMETTO GARDENS | BROOKLYN |  | 0 | 0 | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 0
O'DWYER GARDENS | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
OCEAN HILL-BROWNSVILLE | BROOKLYN | Exterior Compactors | 0 | 0 | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 0
OCEAN HILL APARTMENTS | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
OCEAN BAY APARTMENTS (OCEANSIDE) | QUEENS | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
NOSTRAND | BROOKLYN | Exterior Compactors | 0 | 0 | 2028 |  |  | 0 | 0 | 0 | 2020 | 0
NEW LANE AREA | STATEN ISLAND | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
MOTT HAVEN | BRONX | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
MORRISANIA AIR RIGHTS | BRONX | Exterior Compactors | Zone 1 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
MORRISANIA | BRONX | Exterior Compactors | Zone 1 | $$$$ |  |  |  | 0 | 0 | 0 | 2020 | 0
MORRIS PARK SENIOR CITIZENS HOME | MANHATTAN | Exterior Compactors | Zone 2 | $$$$ |  |  |  | 0 | 0 | 0 | 2020 | 0
MORRIS II | BRONX | Exterior Compactors | Zone 1 | $$$ |  |  |  | 0 | 0 | 0 | 2020 | 0
MORRIS I | BRONX | Exterior Compactors | Zone 1 | $$ |  |  |  | 0 | 0 | 0 | 2020 | 0
MOORE | BRONX | Exterior Compactors | Zone 3 | $$ |  |  |  | 0 | 0 | 0 | 2020 | 0
MONROE | BRONX | Exterior Compactors | Zone 3 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
MITCHEL | BRONX | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
MILL BROOK EXTENSION | BRONX | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
MILL BROOK | BRONX | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
MIDDLETOWN PLAZA | BRONX | Exterior Compactors | 0 | 0 | 2026 |  |  | 0 | 0 | 0 | 2020 | 0
METRO NORTH PLAZA | MANHATTAN | Exterior Compactors | Zone 2 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
MELTZER TOWER | MANHATTAN | Exterior Compactors | Zone 1 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
MELROSE | BRONX | Exterior Compactors | Zone 1 | $ | 2023 | Yes |  | 0 | 0 | 0 | 2020 | 0
MCKINLEY | BRONX | Exterior Compactors | Zone 4 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
MARSHALL PLAZA | MANHATTAN | Exterior Compactors | Zone 3 | $$ | 2020 | Yes |  | 0 | 0 | 0 | 2020 | 0
MARLBORO | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
MARINER'S HARBOR | STATEN ISLAND | Exterior Compactors | 0 | 0 | 2028 |  |  | 0 | 0 | 0 | 2020 | 0
MARCY AVENUE-GREENE AVENUE SITE B | BROOKLYN |  | 0 | 0 | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 0
MARCY AVENUE-GREENE AVENUE SITE A | BROOKLYN | Exterior Compactors | Zone 1 | $ | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 0
MARCY | BROOKLYN | Exterior Compactors | Zone 1 | $$ | 2027 |  |  | 0 | 0 | 0 | 2020 | 0
MARBLE HILL | BRONX | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
MANHATTANVILLE REHAB (GROUP 3) | MANHATTAN | Exterior Compactors | Zone 3 | $ | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 0
MANHATTANVILLE REHAB (GROUP 2) | MANHATTAN | Exterior Compactors | Zone 3 | $ | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 0
MANHATTANVILLE | MANHATTAN | Exterior Compactors | Zone 2 | $ | 2028 |  |  | 0 | 0 | 0 | 2020 | 0
LOWER EAST SIDE REHAB (GROUP 5) | MANHATTAN | Exterior Compactors | Zone 1 | $$ | 2026 |  |  | 0 | 0 | 0 | 2020 | 0
LOWER EAST SIDE III | MANHATTAN | Exterior Compactors | Zone 1 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
LOWER EAST SIDE II | MANHATTAN | Exterior Compactors | Zone 1 | $ | 2026 |  |  | 0 | 0 | 0 | 2020 | 0
LOWER EAST SIDE I INFILL | MANHATTAN | Exterior Compactors | Zone 1 | $$ |  |  |  | 0 | 0 | 0 | 2020 | 0
LOW HOUSES | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
LONGFELLOW AVENUE REHAB | BRONX | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
LONG ISLAND BAPTIST HOUSES | BROOKLYN | Exterior Compactors | 0 | 0 | 2026 |  |  | 0 | 0 | 0 | 2020 | 0
LINDEN | BROOKLYN |  | 0 | 0 | 2020 | Yes |  | 0 | 0 | 0 | 2020 | 0
LINCOLN | MANHATTAN | Exterior Compactors | Zone 2 | $$$$ |  |  |  | 0 | 0 | 0 | 2020 | 0
LEXINGTON | MANHATTAN | Exterior Compactors | Zone 2 | $ | 2023 | Yes |  | 0 | 0 | 0 | 2020 | 0
LENOX ROAD-ROCKAWAY PARKWAY | BROOKLYN |  | 0 | 0 | 2021 | Yes |  | 0 | 0 | 0 | 2020 | 0
LEHMAN VILLAGE | MANHATTAN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
LEAVITT STREET-34TH AVENUE | QUEENS | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
LAVANBURG HOMES | MANHATTAN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
LATIMER GARDENS | QUEENS | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
LAFAYETTE | BROOKLYN | Exterior Compactors | Zone 1 | $$$ |  |  |  | 0 | 0 | 0 | 2020 | 0
LA GUARDIA ADDITION | MANHATTAN | Exterior Compactors | Zone 1 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
LA GUARDIA | MANHATTAN | Exterior Compactors | Zone 1 | $$ |  |  |  | 0 | 0 | 0 | 2020 | 0
KINGSBOROUGH EXTENSION | BROOKLYN | Exterior Compactors | Zone 4 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
KINGSBOROUGH | BROOKLYN | Exterior Compactors | Zone 3 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
KING TOWERS | MANHATTAN | Exterior Compactors | Zone 2 | $$$ |  |  |  | 0 | 0 | 0 | 2020 | 0
JOHNSON | MANHATTAN | Exterior Compactors | Zone 2 | $$$ | 2028 |  |  | 0 | 0 | 0 | 2020 | 0
JEFFERSON | MANHATTAN | Exterior Compactors | Zone 2 | $$ | 2026 |  |  | 0 | 0 | 0 | 2020 | 0
JACKSON | BRONX | Exterior Compactors | Zone 1 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
ISAACS | MANHATTAN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
INTERNATIONAL TOWER | QUEENS | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
INGERSOLL | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
INDEPENDENCE | BROOKLYN |  | 0 | 0 | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 0
HYLAN | BROOKLYN | Exterior Compactors | Zone 1 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
HUNTS POINT AVENUE REHAB | BRONX | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
HUGHES APARTMENTS | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
HOWARD AVENUE-PARK PLACE | BROOKLYN | Exterior Compactors | Zone 4 | 0 | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 0
HOWARD AVENUE | BROOKLYN | Exterior Compactors | 0 | 0 | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 0
HOWARD | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
HOPE GARDENS | BROOKLYN | Exterior Compactors | Zone 1 | 0 | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 0
HOLMES TOWERS | MANHATTAN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
HOE AVENUE-EAST 173RD STREET | BRONX | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
HIGHBRIDGE GARDENS | BRONX | Exterior Compactors | Zone 1 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
HERNANDEZ | MANHATTAN | Exterior Compactors | Zone 1 | $$ |  |  |  | 0 | 0 | 0 | 2020 | 0
HARRISON AVENUE REHAB (GROUP B) | BRONX | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
HARRISON AVENUE REHAB (GROUP A) | BRONX | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
HARLEM RIVER II | MANHATTAN | Exterior Compactors | Zone 3 | $$ | 2020 | Yes |  | 0 | 0 | 0 | 2020 | 0
HARLEM RIVER | MANHATTAN | Exterior Compactors | Zone 3 | $ | 2020 | Yes |  | 0 | 0 | 0 | 2020 | 0
HARBORVIEW TERRACE | MANHATTAN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
HAMMEL | QUEENS | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
HABER | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
GUN HILL | BRONX | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
GRAVESEND | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
GRANT | MANHATTAN | Exterior Compactors | Zone 2 | $$$$ |  |  |  | 0 | 0 | 0 | 2020 | 0
GRAMPION | MANHATTAN | Exterior Compactors | Zone 3 | $ | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 0
GOWANUS | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
GOMPERS | MANHATTAN | Exterior Compactors | Zone 1 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
GLENWOOD | BROOKLYN | Exterior Compactors | 0 | 0 | 2028 |  |  | 0 | 0 | 0 | 2020 | 0
GLENMORE PLAZA | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
GLEBE AVENUE-WESTCHESTER AVENUE | BRONX |  | 0 | 0 | 2021 | Yes |  | 0 | 0 | 0 | 2020 | 0
GARVEY (GROUP A) | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
FULTON | MANHATTAN | Exterior Compactors | Zone 3 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
FORT WASHINGTON AVENUE REHAB | MANHATTAN | Exterior Compactors | Zone 3 | $ | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 0
FORT INDEPENDENCE STREET-HEATH AVENUE | BRONX | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
FOREST | BRONX | Exterior Compactors | Zone 4 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
FIRST HOUSES | MANHATTAN | Exterior Compactors | Zone 1 | $ | 2026 |  |  | 0 | 0 | 0 | 2020 | 0
FIORENTINO PLAZA | BROOKLYN | Exterior Compactors | 0 | 0 | 2026 |  |  | 0 | 0 | 0 | 2020 | 0
FHA REPOSSESSED HOUSES (GROUP X) | 0 | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
FHA REPOSSESSED HOUSES (GROUP VIII) | 0 | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
FHA REPOSSESSED HOUSES (GROUP VII) | 0 | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
FHA REPOSSESSED HOUSES (GROUP VI) | 0 | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
FHA REPOSSESSED HOUSES (GROUP V) | 0 | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
FHA REPOSSESSED HOUSES (GROUP IX) | 0 | Exterior Compactors | Zone 4 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
FHA REPOSSESSED HOUSES (GROUP IV) | 0 | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
FHA REPOSSESSED HOUSES (GROUP III) | 0 | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
FHA REPOSSESSED HOUSES (GROUP II) | 0 | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
FHA REPOSSESSED HOUSES (GROUP I) | 0 | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
FENIMORE-LEFFERTS | BROOKLYN |  | 0 | 0 | 2021 | Yes |  | 0 | 0 | 0 | 2020 | 0
FARRAGUT | BROOKLYN | Exterior Compactors | 0 | 0 | 2027 |  |  | 0 | 0 | 0 | 2020 | 0
ELLIOTT | MANHATTAN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
EDENWALD | BRONX |  | 0 | 0 | 2022 | Yes |  | 0 | 0 | 0 | 2020 | 0
EASTCHESTER GARDENS | BRONX | Exterior Compactors | 0 | 0 | 2026 |  |  | 0 | 0 | 0 | 2020 | 0
EAST RIVER | MANHATTAN | Exterior Compactors | Zone 2 | $ | 2024 | Yes |  | 0 | 0 | 0 | 2020 | 0
EAST NEW YORK CITY LINE | BROOKLYN |  | 0 | 0 | 2023 | Yes |  | 0 | 0 | 0 | 2020 | 0
EAST 180TH STREET-MONTEREY AVENUE | BRONX | Exterior Compactors | Zone 1 | $$ |  |  |  | 0 | 0 | 0 | 2020 | 0
EAST 173RD STREET-VYSE AVENUE | BRONX | Exterior Compactors | Zone 4 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
EAST 165TH STREET-BRYANT AVENUE | BRONX | Exterior Compactors | Zone 4 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
EAST 152ND STREET-COURTLANDT AVENUE | BRONX |  | 0 | 0 | 2023 | Yes |  | 0 | 0 | 0 | 2020 | 0
EAGLE AVENUE-EAST 163RD STREET | BRONX | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
DYCKMAN | MANHATTAN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
DREW-HAMILTON | MANHATTAN | Exterior Compactors | Zone 2 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
DOUGLASS II | MANHATTAN | Exterior Compactors | Zone 3 | $$$ |  |  |  | 0 | 0 | 0 | 2020 | 0
DOUGLASS I | MANHATTAN | Exterior Compactors | Zone 3 | $$$ |  |  |  | 0 | 0 | 0 | 2020 | 0
DOUGLASS ADDITION | MANHATTAN | Exterior Compactors | Zone 3 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
DOUGLASS | MANHATTAN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
DE HOSTOS APARTMENTS | MANHATTAN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
DAVIDSON | BRONX | Exterior Compactors | Zone 3 | $ | 2026 |  |  | 0 | 0 | 0 | 2020 | 0
CYPRESS HILLS | BROOKLYN |  | 0 | 0 | 2023 | Yes |  | 0 | 0 | 0 | 2020 | 0
CROWN HEIGHTS | BROOKLYN | Exterior Compactors | Zone 4 | 0 | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 0
CORSI HOUSES | MANHATTAN | Exterior Compactors | Zone 2 | $ | 2026 |  |  | 0 | 0 | 0 | 2020 | 0
COOPER PARK | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
CONLON LIHFE TOWER | QUEENS | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
CONEY ISLAND I (SITES 4 & 5) | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
CONEY ISLAND I (SITE 8) | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
CONEY ISLAND I (SITE 1B) | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
CONEY ISLAND | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
COLLEGE AVENUE-EAST 165TH STREET | BRONX | Exterior Compactors | Zone 1 | $ | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 0
CLINTON | MANHATTAN | Exterior Compactors | Zone 2 | $$$$ |  |  |  | 0 | 0 | 0 | 2020 | 0
CLASON POINT GARDENS | BRONX |  | 0 | 0 | 2024 | Yes |  | 0 | 0 | 0 | 2020 | 0
CLAREMONT REHAB (GROUP 5) | BRONX | Exterior Compactors | Zone 1 | $ | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 0
CLAREMONT REHAB (GROUP 4) | BRONX | Exterior Compactors | Zone 1 | $ | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 0
CLAREMONT REHAB (GROUP 3) | BRONX | Exterior Compactors | Zone 1 | $ | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 0
CLAREMONT REHAB (GROUP 2) | BRONX | Exterior Compactors | Zone 1 | $ | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 0
CLAREMONT PARKWAY-FRANKLIN AVENUE | BRONX | Exterior Compactors | Zone 3 | $ | 2026 |  |  | 0 | 0 | 0 | 2020 | 0
CHELSEA ADDITION | MANHATTAN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
CHELSEA | MANHATTAN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
CASTLE HILL | BRONX | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
CASSIDY-LAFAYETTE | STATEN ISLAND | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
CARVER | MANHATTAN | Exterior Compactors | Zone 2 | $$ |  |  |  | 0 | 0 | 0 | 2020 | 0
CARLETON MANOR | QUEENS | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
CAREY GARDENS | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
CAMPOS PLAZA II | MANHATTAN | Exterior Compactors | Zone 1 | $$ | 2026 |  |  | 0 | 0 | 0 | 2020 | 0
BUTLER | BRONX | Exterior Compactors | Zone 1 | $$ |  |  |  | 0 | 0 | 0 | 2020 | 0
BUSHWICK II CDA (GROUP E) | BROOKLYN | Exterior Compactors | Zone 1 | 0 | 2019 | Yes |  | 0 | 0 | 0 | 2020 | 0
BUSHWICK II (GROUPS B & D) | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
BUSHWICK II (GROUPS A & C) | BROOKLYN | Exterior Compactors | Zone 1 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
BUSHWICK | BROOKLYN | Exterior Compactors | Zone 1 | $$ |  |  |  | 0 | 0 | 0 | 2020 | 0
BRYANT AVENUE-EAST 174TH STREET | BRONX | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
BROWNSVILLE | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
BROWN | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
BRONX RIVER ADDITION | BRONX | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
BRONX RIVER | BRONX | Exterior Compactors | Zone 3 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
BREVOORT | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
BREUKELEN | BROOKLYN |  | 0 | 0 | 2021 | Yes |  | 0 | 0 | 0 | 2020 | 0
BRACETTI PLAZA | MANHATTAN | Exterior Compactors | Zone 1 | $ | 2026 |  |  | 0 | 0 | 0 | 2020 | 0
BOYNTON AVENUE REHAB | BRONX | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
BOULEVARD | BROOKLYN |  | 0 | 0 | 2020 | Yes |  | 0 | 0 | 0 | 2020 | 0
BOSTON SECOR | BRONX | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
BOSTON ROAD PLAZA | BRONX |  | 0 | 0 | 2022 | Yes |  | 0 | 0 | 0 | 2020 | 0
BORINQUEN PLAZA II | BROOKLYN | Exterior Compactors | Zone 3 | $$$ |  |  |  | 0 | 0 | 0 | 2020 | 0
BORINQUEN PLAZA I | BROOKLYN | Exterior Compactors | Zone 3 | $$$$ |  |  |  | 0 | 0 | 0 | 2020 | 0
BLAND | QUEENS | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
BETHUNE GARDENS | MANHATTAN | Exterior Compactors | Zone 3 | $$ | 2020 | Yes |  | 0 | 0 | 0 | 2020 | 0
BERRY STREET-SOUTH 9TH STREET | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
BERRY | STATEN ISLAND | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
BELMONT-SUTTER AREA | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
BEDFORD-STUYVESANT REHAB | BROOKLYN | Exterior Compactors | Zone 1 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
BEACH 41ST STREET-BEACH CHANNEL DRIVE | QUEENS | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
BAY VIEW | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
BARUCH HOUSES ADDITION | MANHATTAN | Exterior Compactors | Zone 1 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
BARUCH | MANHATTAN | Exterior Compactors | Zone 1 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
BAISLEY PARK | QUEENS | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
BAILEY AVENUE-WEST 193RD STREET | BRONX | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
AUDUBON | MANHATTAN | Exterior Compactors | Zone 3 | $$$$ | 2020 | Yes |  | 0 | 0 | 0 | 2020 | 0
ATLANTIC TERMINAL SITE 4B | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
ASTORIA | QUEENS |  | 0 | 0 | 2024 | Yes |  | 0 | 0 | 0 | 2020 | 0
ARMSTRONG II | BROOKLYN | Exterior Compactors | Zone 1 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
ARMSTRONG I | BROOKLYN | Exterior Compactors | Zone 1 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
AMSTERDAM ADDITION | MANHATTAN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
AMSTERDAM | MANHATTAN | Exterior Compactors | Zone 4 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
ALBANY II | BROOKLYN | Exterior Compactors | 0 | 0 | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 0
ALBANY | BROOKLYN | Exterior Compactors | 0 | 0 | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 0
ADAMS | BRONX | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
830 AMSTERDAM AVENUE | MANHATTAN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
572 WARREN STREET | BROOKLYN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
45 ALLEN STREET | MANHATTAN | Exterior Compactors | Zone 1 | $$ |  |  |  | 0 | 0 | 0 | 2020 | 0
344 EAST 28TH STREET | MANHATTAN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
335 EAST 111TH STREET | MANHATTAN | Exterior Compactors | Zone 3 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
303 VERNON AVENUE | BROOKLYN | Exterior Compactors | Zone 1 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
154 WEST 84TH STREET | MANHATTAN | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
1471 WATSON AVENUE | BRONX |  | 0 | 0 | 2021 | Yes |  | 0 | 0 | 0 | 2020 | 0
131 SAINT NICHOLAS AVENUE | MANHATTAN | Exterior Compactors | Zone 2 | $ |  |  |  | 0 | 0 | 0 | 2020 | 0
1162-1176 WASHINGTON AVENUE | BRONX | Exterior Compactors | 0 | 0 | 2025 | Yes |  | 0 | 0 | 0 | 2020 | 0
104-14 TAPSCOTT STREET | BROOKLYN |  | 0 | 0 | 2021 | Yes |  | 0 | 0 | 0 | 2020 | 0
1010 EAST 178TH STREET | BRONX | Exterior Compactors | 0 | 0 |  |  |  | 0 | 0 | 0 | 2020 | 0
Formulas:
AGE (2019) (Y) = IF(VLOOKUP(ExtComp[[#This Row],[DEVELOPMENT]],Data[],11,FALSE)=0,"",DATEDIF(VLOOKUP(ExtComp[[#This Row],[DEVELOPMENT]],Data[],13,FALSE),TODAY(),"Y"))
Cost per Development = (ExtComp[[#This Row],['# to Replace]]*'Unit Costs'!$B6)*(1+((ExtComp[[#This Row],[est. Year]]-YEAR(TODAY()))*J2))

## CPD Information (hidden)
BOROUGH | PROGRAM AREA | DEVELOPMENT | WORK TYPE | CALENDAR YEAR | FISCAL YEAR | STATUS | COST | ESTIMATES | RESOURCE
Manhattan | Waste Management | SEWARD PARK EXTENSION | Interior Compactors | 2017 | 2018 | COMPLETED | 120000 |  | CPD PROJECT MANAGEMENT
Manhattan | Waste Management | BARUCH | Bulk Crushers | 2019 | 2020 | UP-COMING |  | 750000 | CPD PROJECT MANAGEMENT
Manhattan | Waste Management | SMITH | Bulk Crushers | 2019 | 2020 | UP-COMING |  | 750000 | CPD PROJECT MANAGEMENT
Manhattan | Waste Management | WALD | Bulk Crushers | 2019 | 2020 | UP-COMING |  | 750000 | CPD PROJECT MANAGEMENT
Manhattan | Waste Management | VLADECK | Exterior Compactors (New) | 2019 | 2020 | UP-COMING |  | 868792.39 | CPD PROJECT MANAGEMENT
Manhattan | Waste Management | BARUCH | Exterior Compactors (Replacement) | 2019 | 2020 | UP-COMING |  | 1297554 | CPD PROJECT MANAGEMENT
Manhattan | Waste Management | RIIS | Exterior Compactors (Replacement) | 2019 | 2019 | IN-CONSTRUCTION | 456600 |  | CPD PROJECT MANAGEMENT
Manhattan | Waste Management | RUTGERS | Exterior Compactors (Replacement) | 2019 | 2020 | UP-COMING |  | 152200 | CPD PROJECT MANAGEMENT
Manhattan | Waste Management | SMITH | Exterior Compactors (Replacement) | 2019 | 2020 | UP-COMING |  | 1297554 | CPD PROJECT MANAGEMENT
Manhattan | Waste Management | WALD | Exterior Compactors (Replacement) | 2019 | 2020 | UP-COMING |  | 1297554 | CPD PROJECT MANAGEMENT
Manhattan | Waste Management | FIRST HOUSES | Interior Compactors | 2019 | 2020 | UP-COMING | 405596.06 |  | CPD PROJECT MANAGEMENT
Manhattan | Waste Management | GOMPERS | Interior Compactors | 2019 | 2020 | UP-COMING | 188531.9 |  | CPD PROJECT MANAGEMENT
Manhattan | Waste Management | HERNANDEZ | Interior Compactors | 2019 | 2020 | UP-COMING | 58806.74 |  | CPD PROJECT MANAGEMENT
Manhattan | Waste Management | LA GUARDIA | Interior Compactors | 2019 | 2020 | UP-COMING | 472885.23 |  | CPD PROJECT MANAGEMENT
Manhattan | Waste Management | LA GUARDIA ADDITION | Interior Compactors | 2019 | 2020 | UP-COMING | 45923.96 |  | CPD PROJECT MANAGEMENT
Manhattan | Waste Management | RUTGERS | Interior Compactors | 2019 | 2020 | UP-COMING | 260485.58 |  | CPD PROJECT MANAGEMENT
Manhattan | Waste Management | SMITH | Interior Compactors | 2019 | 2019 | IN-CONSTRUCTION | 568561.86 |  | CPD PROJECT MANAGEMENT
Manhattan | Waste Management | TWO BRIDGES URA (SITE 7) | Interior Compactors | 2019 | 2020 | UP-COMING | 84803.79 |  | CPD PROJECT MANAGEMENT
Manhattan | Waste Management | WALD | Interior Compactors | 2019 | 2019 | IN-CONSTRUCTION | 763941.26 |  | CPD PROJECT MANAGEMENT
Manhattan | Waste Management | GOMPERS | Exterior Compactors (Replacement) | 2020 | 2020 | UP-COMING |  | 152200 | CPD PROJECT MANAGEMENT
Manhattan | Waste Management | 45 ALLEN STREET | Interior Compactors | 2020 | 2020 | UP-COMING | 52249.29 |  | CPD PROJECT MANAGEMENT
Manhattan | Waste Management | BRACETTI PLAZA | Interior Compactors | 2020 | 2020 | UP-COMING | 93596.23 |  | CPD PROJECT MANAGEMENT
Manhattan | Waste Management | LES II | Interior Compactors | 2020 | 2020 | UP-COMING | 48867.93 |  | CPD PROJECT MANAGEMENT
Manhattan | Waste Management | LOWER EAST SIDE I INFILL | Interior Compactors | 2020 | 2020 | UP-COMING |  | 74191 | CPD PROJECT MANAGEMENT
Manhattan | Waste Management | MELTZER TOWER | Interior Compactors | 2020 | 2020 | UP-COMING | 55348.64 |  | CPD PROJECT MANAGEMENT
Manhattan | Waste Management | VLADECK | Interior Compactors | 2020 | 2020 | UP-COMING |  | 3412786 | CPD PROJECT MANAGEMENT
Manhattan | Waste Management | VLADECK II | Interior Compactors | 2020 | 2020 | UP-COMING |  | 593528 | CPD PROJECT MANAGEMENT
[7 empty] | 3676198.47 | 11396359.39
15072557.86

## Unit Costs
Work Type | Unit Cost | Funding
Bulk Crusher | 1307070 | capital
Cardboard Baler | 38885.4 | capital
Electric Tilt Truck | 37000 | capital
Enlarge Hopper Door | 7435.6435 | expense
Exterior Compactors | 188799 | capital
Food Waste Disposer | 1718.7359 | expense
Interior Compactors | 71162.7 | capital
Mattress Recycling | 13656 | expense | per year
Secondary collection areas | 133611.6 | expense
Tilt Trucks | 1000 | expense
Trash Cans | 300 | expense
New Waste Yard v1 | 1159792.78 | capital | 2 auger compactors
New Waste Yard v2 | 728535.54 | capital | 1 bulk auger compactor
New Waste Yard v3 | 1591050.02 | capital | 3 auger compactors
New Waste Yard v4 | 2022307.26 | capital | 4 auger compactors
New Waste Yard v5 | 2453564.5 | capital | 5 auger compactors
New Waste Yard v6 | 2884821.74 | capital | 6 auger compactors
New Waste Yard v7 | 3316078.98 | capital | 7 auger compactors

## Development Data
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
DEVELOPMENT | BOROUGH | Managed By | RAD/PACT | # Buildings | # Stairhalls | DUs | NRR | Priority Level | # Interior Compactors | # Exterior Compactors | Int. Compactor Install | Ext. Compactor Install | Enlarge Hopper Door | Bulk Crusher | Cardboard Baler | Mattress Recycling | Electric Tilt Truck | Secondary Collection Areas | Food Waste Disposer | DSNY - # ext affected | DSNY - replacement/new | DSNY - notes | TDS | Newtown Creek | PNA Ext. | PNA Int. | # Bulk Crushers | Bulk Install Date | # Ext RUL <=5 | # Int RUL <=5 | 311 Developments
1010 EAST 178TH STREET | BRONX | MURPHY |  | 1 | 1 | 218 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 218 |  |  |  | 180 |  | 0 | 1 |  |  | 0 | 1 | 1010 EAST 178TH STREET
104-14 TAPSCOTT STREET | BROOKLYN | REID APARTMENTS | 2021 | 1 | 1 | 30 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 30 |  |  |  | 242 |  | 0 | 2 |  |  | 0 | 2 | 104-14 TAPSCOTT STREET
1162-1176 WASHINGTON AVENUE | BRONX | CLAREMONT CONSOLIDATED | 2025 | 1 | 1 | 65 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 65 |  |  |  | 233 |  | 0 | 1 |  |  | 0 | 1 | 1162-1176 WASHINGTON AVENUE
131 SAINT NICHOLAS AVENUE | MANHATTAN | TAFT |  | 1 | 1 | 98 | Zone 2 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 98 |  |  |  | 154 |  | 0 | 1 |  |  | 0 | 1 | 131 SAINT NICHOLAS AVENUE
1471 WATSON AVENUE | BRONX | SOTOMAYOR HOUSES | 2021 | 1 | 1 | 96 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 96 |  |  |  | 214 |  | 0 | 2 |  |  | 0 | 2 | 1471 WATSON AVENUE
154 WEST 84TH STREET | MANHATTAN | KRAUS MANAGEMENT (PRIVATE - M/B 1) |  | 1 | 1 | 35 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 35 |  |  |  | 359 |  | 0 | 1 |  |  | 0 | 1 | 154 WEST 84TH STREET
303 VERNON AVENUE | BROOKLYN | SUMNER |  | 1 | 1 | 234 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 234 |  |  |  | 156 | Yes | 0 | 2 |  |  | 0 | 2 | 303 VERNON AVENUE
335 EAST 111TH STREET | MANHATTAN | JEFFERSON |  | 1 | 1 | 66 | Zone 3 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 66 |  |  |  | 203 |  | 0 | 1 |  |  | 0 | 1 | 335 EAST 111TH STREET
344 EAST 28TH STREET | MANHATTAN | STRAUS |  | 1 | 1 | 225 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 225 |  |  |  | 185 | Yes | 0 | 1 |  |  | 0 | 1 | 344 EAST 28TH STREET
45 ALLEN STREET | MANHATTAN | GOMPERS |  | 1 | 2 | 107 | Zone 1 | $$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 107 |  |  |  | 265 | Yes | 0 | 1 |  |  | 0 | 1 | 45 ALLEN STREET
572 WARREN STREET | BROOKLYN | WYCKOFF GARDENS |  | 1 | 2 | 200 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 200 |  |  |  | 196 |  | 0 | 2 |  |  | 0 | 2 | 572 WARREN STREET
830 AMSTERDAM AVENUE | MANHATTAN | DOUGLASS |  | 1 | 1 | 158 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 158 |  |  |  | 150 |  | 0 | 2 |  |  | 0 | 2 | 830 AMSTERDAM AVENUE
ADAMS | BRONX | ADAMS |  | 7 | 7 | 924 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 924 |  |  |  | 118 |  | 2 | 7 |  |  | 2 | 7 | ADAMS
ALBANY | BROOKLYN | ALBANY | 2025 | 6 | 6 | 823 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 823 |  |  |  | 31 | Yes | 0 | 6 |  |  | 0 | 6 | ALBANY
ALBANY II | BROOKLYN | ALBANY | 2025 | 3 | 3 | 400 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 400 |  |  |  | 85 | Yes | 3 | 3 |  |  | 3 | 3 | ALBANY II
AMSTERDAM | MANHATTAN | AMSTERDAM |  | 13 | 24 | 1084 | Zone 4 |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1084 |  |  |  | 22 |  | 3 | 24 |  |  | 3 | 24 | AMSTERDAM
AMSTERDAM ADDITION | MANHATTAN | AMSTERDAM |  | 1 | 1 | 175 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 175 |  |  |  | 187 |  | 0 | 2 |  |  | 0 | 2 | AMSTERDAM ADDITION
ARMSTRONG I | BROOKLYN | ARMSTRONG I |  | 11 | 58 | 369 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 369 |  |  |  | 210 | Yes | 0 | 6 |  |  | 0 | 6 | ARMSTRONG I
ARMSTRONG II | BROOKLYN | ARMSTRONG I |  | 5 | 17 | 248 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 248 |  |  |  | 228 | Yes | 0 | 10 |  |  | 0 | 10 | ARMSTRONG II
ASTORIA | QUEENS | ASTORIA | 2024 | 22 | 22 | 1104 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1104 |  |  |  | 26 |  | 3 | 22 |  |  | 3 | 22 | ASTORIA
ATLANTIC TERMINAL SITE 4B | BROOKLYN | WYCKOFF GARDENS |  | 1 | 1 | 299 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 299 |  |  |  | 256 |  | 1 | 2 |  |  | 1 | 2 | ATLANTIC TERMINAL SITE 4B
AUDUBON | MANHATTAN | HARLEM RIVER | 2020 | 1 | 1 | 167 | Zone 3 | $$$$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 167 |  |  |  | 125 |  | 0 | 2 |  |  | 0 | 2 | AUDUBON
BAILEY AVENUE-WEST 193RD STREET | BRONX | FORT INDEPENDENCE |  | 1 | 1 | 232 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 232 |  |  |  | 202 |  | 1 | 1 |  |  | 1 | 1 | BAILEY AVENUE-WEST 193RD STREET
BAISLEY PARK | QUEENS | BAISLEY PARK |  | 5 | 8 | 381 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 381 |  |  |  | 91 |  | 0 | 5 |  |  | 0 | 5 | BAISLEY PARK
BARUCH | MANHATTAN | BARUCH |  | 17 | 35 | 2193 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 2193 |  |  |  | 60 | Yes | 0 | 17 |  |  | 0 | 0 | BARUCH
BARUCH HOUSES ADDITION | MANHATTAN | BARUCH |  | 1 | 1 | 197 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 197 |  |  |  | 198 | Yes | 0 | 1 |  |  | 0 | 0 | BARUCH HOUSES ADDITION
BAY VIEW | BROOKLYN | BAY VIEW |  | 23 | 26 | 1609 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1609 |  |  |  | 92 |  | 4 | 23 |  |  | 4 | 23 | BAY VIEW
BEACH 41ST STREET-BEACH CHANNEL DRIVE | QUEENS | BEACH 41ST STREET-BEACH CHANNEL DRIVE |  | 4 | 7 | 712 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 712 |  |  |  | 165 |  | 1 | 6 |  |  | 1 | 6 | BEACH 41ST STREET-BEACH CHANNEL DRIVE
BEDFORD-STUYVESANT REHAB | BROOKLYN | SUMNER |  | 3 | 5 | 84 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 84 |  |  |  | 311 | Yes | 0 | 5 |  |  | 0 | 5 | BEDFORD-STUYVESANT REHAB
BELMONT-SUTTER AREA | BROOKLYN | BOULEVARD |  | 3 | 8 | 72 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 72 |  |  |  | 345 |  | 0 | 0 |  |  | 0 | 0 | BELMONT-SUTTER AREA
BERRY | STATEN ISLAND | BERRY |  | 8 | 17 | 506 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 506 |  |  |  | 52 |  | 1 | 15 |  |  | 1 | 15 | BERRY
BERRY STREET-SOUTH 9TH STREET | BROOKLYN | TOMPKINS |  | 4 | 15 | 150 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 150 |  |  |  | 357 | Yes | 1 | 1 |  |  | 1 | 1 | BERRY STREET-SOUTH 9TH STREET
BETHUNE GARDENS | MANHATTAN | HARLEM RIVER | 2020 | 1 | 1 | 210 | Zone 3 | $$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 210 |  |  |  | 160 |  | 1 | 1 |  |  | 1 | 1 | BETHUNE GARDENS
BLAND | QUEENS | LATIMER GARDENS |  | 5 | 5 | 399 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 399 |  |  |  | 54 |  | 0 | 5 |  |  | 0 | 5 | BLAND
BORINQUEN PLAZA I | BROOKLYN | BORINQUEN PLAZA I |  | 8 | 10 | 509 | Zone 3 | $$$$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 509 |  |  |  | 243 | Yes | 2 | 8 |  |  | 2 | 8 | BORINQUEN PLAZA I
BORINQUEN PLAZA II | BROOKLYN | BORINQUEN PLAZA I |  | 7 | 7 | 425 | Zone 3 | $$$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 425 |  |  |  | 271 | Yes | 0 | 7 |  |  | 0 | 7 | BORINQUEN PLAZA II
BOSTON ROAD PLAZA | BRONX | PELHAM PARKWAY | 2022 | 1 | 2 | 232 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 232 |  |  |  | 189 |  | 0 | 1 |  |  | 0 | 1 | BOSTON ROAD PLAZA
BOSTON SECOR | BRONX | BOSTON SECOR |  | 4 | 5 | 538 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 538 |  |  |  | 138 |  | 2 | 4 |  |  | 2 | 4 | BOSTON SECOR
BOULEVARD | BROOKLYN | BOULEVARD | 2020 | 18 | 30 | 1424 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1424 |  |  |  | 46 |  | 0 | 29 |  |  | 0 | 29 | BOULEVARD
BOYNTON AVENUE REHAB | BRONX | BRONX RIVER |  | 3 | 3 | 82 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 82 |  |  |  | 346 |  | 0 | 3 |  |  | 0 | 3 | BOYNTON AVENUE REHAB
BRACETTI PLAZA | MANHATTAN | LOWER EAST SIDE CONSOLIDATED | 2026 | 1 | 2 | 108 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 108 |  |  |  | 264 | Yes | 0 | 2 |  |  | 0 | 2 | BRACETTI PLAZA
BREUKELEN | BROOKLYN | BREUKELEN | 2021 | 30 | 97 | 1592 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1592 |  |  |  | 56 |  | 4 | 89 |  |  | 4 | 89 | BREUKELEN
BREVOORT | BROOKLYN | BREVOORT |  | 13 | 27 | 894 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 894 |  |  |  | 65 | Yes | 2 | 26 |  |  | 2 | 26 | BREVOORT
BRONX RIVER | BRONX | BRONX RIVER |  | 9 | 10 | 1245 | Zone 3 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1245 |  |  |  | 32 |  | 3 | 9 |  |  | 3 | 9 | BRONX RIVER
BRONX RIVER ADDITION | BRONX | BRONX RIVER |  | 2 | 2 | 226 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 226 |  |  |  | 157 |  | 0 | 2 |  |  | 0 | 2 | BRONX RIVER ADDITION
BROWN | BROOKLYN | GARVEY |  | 2 | 2 | 200 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 200 |  |  |  | 325 |  | 0 | 2 |  |  | 0 | 2 | BROWN
BROWNSVILLE | BROOKLYN | BROWNSVILLE |  | 27 | 46 | 1336 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1336 |  |  |  | 16 |  | 3 | 46 |  |  | 3 | 46 | BROWNSVILLE
BRYANT AVENUE-EAST 174TH STREET | BRONX | BUILDING MANAGEMENT ASSOCIATES (PRIVATE - BX 1) |  | 1 | 1 | 72 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 72 |  |  |  | 235 |  | 0 | 1 |  |  | 0 | 1 | BRYANT AVENUE-EAST 174TH STREET
BUSHWICK | BROOKLYN | BUSHWICK |  | 8 | 8 | 1219 | Zone 1 | $$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1219 |  |  |  | 86 | Yes | 2 | 8 |  |  | 2 | 8 | BUSHWICK
BUSHWICK II (GROUPS A & C) | BROOKLYN | HOPE GARDENS |  | 25 | 25 | 299 | Zone 1 |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 299 |  |  |  | 302 | Yes | 0 | 25 |  |  | 0 | 25 | #N/A
BUSHWICK II (GROUPS B & D) | BROOKLYN | HOPE GARDENS |  | 25 | 27 | 300 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 300 |  |  |  | 303 | Yes | 0 | 25 |  |  | 0 | 25 | #N/A
BUSHWICK II CDA (GROUP E) | BROOKLYN | HOPE GARDENS | 2019 | 5 | 37 | 276 | Zone 1 |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 276 |  |  |  | 324 | Yes | 0 | 0 |  |  | 0 | 0 | #N/A
BUTLER | BRONX | BUTLER |  | 6 | 7 | 1476 | Zone 1 | $$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1476 |  |  |  | 113 |  | 2 | 12 |  |  | 2 | 12 | BUTLER
CAMPOS PLAZA II | MANHATTAN | LOWER EAST SIDE CONSOLIDATED | 2026 | 2 | 3 | 224 | Zone 1 | $$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 224 |  |  |  | 286 | Yes | 0 | 3 |  |  | 0 | 3 | CAMPOS PLAZA II
CAREY GARDENS | BROOKLYN | CAREY GARDENS |  | 3 | 5 | 682 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 682 |  |  |  | 166 |  | 2 | 3 |  |  | 2 | 3 | CAREY GARDENS
CARLETON MANOR | QUEENS | HAMMEL |  | 1 | 1 | 169 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 169 |  |  |  | 164 |  | 0 | 1 |  |  | 0 | 1 | CARLETON MANOR
CARVER | MANHATTAN | CARVER |  | 13 | 13 | 1244 | Zone 2 | $$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1244 |  |  |  | 58 |  | 3 | 13 |  |  | 3 | 13 | CARVER
CASSIDY-LAFAYETTE | STATEN ISLAND | RICHMOND TERRACE |  | 4 | 5 | 378 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 378 |  |  |  | 206 |  | 1 | 4 |  |  | 1 | 4 | CASSIDY-LAFAYETTE
CASTLE HILL | BRONX | CASTLE HILL |  | 14 | 14 | 2022 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 2022 |  |  |  | 80 |  | 4 | 14 |  |  | 4 | 14 | CASTLE HILL
CHELSEA | MANHATTAN | CHELSEA |  | 2 | 4 | 425 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 425 |  |  |  | 134 |  | 0 | 4 |  |  | 0 | 4 | CHELSEA
CHELSEA ADDITION | MANHATTAN | CHELSEA |  | 1 | 1 | 96 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 96 |  |  |  | 176 |  | 0 | 1 |  |  | 0 | 1 | CHELSEA ADDITION
CLAREMONT PARKWAY-FRANKLIN AVENUE | BRONX | UNION AVENUE CONSOLIDATED | 2026 | 3 | 13 | 187 | Zone 3 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 187 |  |  |  | 334 |  | 1 | 1 |  |  | 1 | 1 | CLAREMONT PARKWAY-FRANKLIN AVENUE
CLAREMONT REHAB (GROUP 2) | BRONX | CLAREMONT CONSOLIDATED | 2025 | 6 | 6 | 106 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 106 |  |  |  | 307 |  | 0 | 5 |  |  | 0 | 5 | CLAREMONT REHAB (GROUP 2)
CLAREMONT REHAB (GROUP 3) | BRONX | CLAREMONT CONSOLIDATED | 2025 | 5 | 5 | 107 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 107 |  |  |  | 308 |  | 0 | 4 |  |  | 0 | 4 | CLAREMONT REHAB (GROUP 3)
CLAREMONT REHAB (GROUP 4) | BRONX | CLAREMONT CONSOLIDATED | 2025 | 9 | 9 | 147 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 147 |  |  |  | 335 |  | 0 | 9 |  |  | 0 | 9 | CLAREMONT REHAB (GROUP 4)
CLAREMONT REHAB (GROUP 5) | BRONX | CLAREMONT CONSOLIDATED | 2025 | 3 | 3 | 129 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 129 |  |  |  | 336 |  | 0 | 4 |  |  | 0 | 4 | CLAREMONT REHAB (GROUP 5)
CLASON POINT GARDENS | BRONX | SACK WERN | 2024 | 46 | 192 | 401 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 401 |  |  |  | 11 |  | 0 | 0 |  |  | 0 | 0 | CLASON POINT GARDENS
CLINTON | MANHATTAN | CLINTON |  | 6 | 8 | 748 | Zone 2 | $$$$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 748 |  |  |  | 123 |  | 1 | 6 |  |  | 1 | 6 | CLINTON
COLLEGE AVENUE-EAST 165TH STREET | BRONX | CLAREMONT CONSOLIDATED | 2025 | 1 | 1 | 95 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 95 |  |  |  | 236 |  | 0 | 1 |  |  | 0 | 1 | COLLEGE AVENUE-EAST 165TH STREET
CONEY ISLAND | BROOKLYN | SURFSIDE GARDENS |  | 5 | 5 | 530 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 530 |  |  |  | 94 |  | 0 | 5 |  |  | 0 | 5 | CONEY ISLAND
CONEY ISLAND I (SITE 1B) | BROOKLYN | CAREY GARDENS |  | 1 | 1 | 192 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 192 |  |  |  | 239 |  | 0 | 1 |  |  | 0 | 1 | CONEY ISLAND I (SITE 1B)
CONEY ISLAND I (SITE 8) | BROOKLYN | O'DWYER GARDENS |  | 1 | 2 | 124 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 124 |  |  |  | 238 |  | 0 | 1 |  |  | 0 | 1 | CONEY ISLAND I (SITE 8)
CONEY ISLAND I (SITES 4 & 5) | BROOKLYN | SURFSIDE GARDENS |  | 1 | 6 | 376 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 376 |  |  |  | 216 |  | 1 | 3 | 1 |  | 1 | 3 | CONEY ISLAND I (SITES 4 & 5)
CONLON LIHFE TOWER | QUEENS | BAISLEY PARK |  | 1 | 1 | 214 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 214 |  |  |  | 232 |  | 2 | 1 |  |  | 2 | 1 | CONLON LIHFE TOWER
COOPER PARK | BROOKLYN | COOPER PARK |  | 11 | 13 | 700 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 700 |  |  |  | 69 | Yes | 2 | 13 |  |  | 2 | 13 | COOPER PARK
CORSI HOUSES | MANHATTAN | JEFFERSON | 2026 | 1 | 1 | 171 | Zone 2 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 171 |  |  |  | 199 |  | 0 | 1 |  |  | 0 | 1 | CORSI HOUSES
CROWN HEIGHTS | BROOKLYN | PARK ROCK CONSOLIDATED | 2025 | 8 | 8 | 121 | Zone 4 |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 121 |  |  |  | 312 | Yes | 0 | 8 |  |  | 0 | 8 | CROWN HEIGHTS
CYPRESS HILLS | BROOKLYN | CYPRESS HILLS | 2023 | 15 | 30 | 1439 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1439 |  |  |  | 70 |  | 3 | 29 |  |  | 0 | 29 | CYPRESS HILLS
DAVIDSON | BRONX | UNION AVENUE CONSOLIDATED | 2026 | 1 | 2 | 175 | Zone 3 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 175 |  |  |  | 190 |  | 0 | 1 |  |  | 0 | 1 | DAVIDSON
DE HOSTOS APARTMENTS | MANHATTAN | WISE TOWERS |  | 1 | 1 | 219 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 219 |  |  |  | 155 |  | 0 | 2 |  |  | 0 | 2 | DE HOSTOS APARTMENTS
DOUGLASS | MANHATTAN | #N/A | #N/A | 17 | 17 | 2054 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 2054 |  |  |  | 082, 582 |  | 0 | 0 |  |  | 0 | 0 | #N/A
DOUGLASS ADDITION | MANHATTAN | DOUGLASS |  | 1 | 1 | 135 | Zone 3 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 135 |  |  |  | 148 |  | 0 | 1 |  |  | 0 | 1 | DOUGLASS ADDITION
DOUGLASS I | MANHATTAN | DOUGLASS |  | 11 | 11 | 1302 | Zone 3 | $$$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1302 |  |  |  | 82 |  | 0 | 11 |  |  | 0 | 11 | DOUGLASS I
DOUGLASS II | MANHATTAN | DOUGLASS |  | 6 | 6 | 752 | Zone 3 | $$$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 752 |  |  |  | 582 |  | 0 | 6 |  |  | 0 | 6 | DOUGLASS II
DREW-HAMILTON | MANHATTAN | DREW-HAMILTON |  | 5 | 5 | 1211 | Zone 2 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1211 |  |  |  | 111 |  | 2 | 5 |  |  | 2 | 5 | DREW-HAMILTON
DYCKMAN | MANHATTAN | DYCKMAN |  | 7 | 8 | 1167 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1167 |  |  |  | 41 |  | 2 | 14 |  |  | 0 | 14 | DYCKMAN
EAGLE AVENUE-EAST 163RD STREET | BRONX | FOREST |  | 1 | 1 | 65 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 65 |  |  |  | 224 |  | 0 | 1 |  |  | 0 | 1 | EAGLE AVENUE-EAST 163RD STREET
EAST 152ND STREET-COURTLANDT AVENUE | BRONX | MELROSE | 2023 | 2 | 2 | 221 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 221 |  |  |  | 237 |  | 1 | 2 |  |  | 1 | 2 | EAST 152ND STREET-COURTLANDT AVENUE
EAST 165TH STREET-BRYANT AVENUE | BRONX | BUILDING MANAGEMENT ASSOCIATES (PRIVATE - BX 1) |  | 5 | 19 | 111 | Zone 4 |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 111 |  |  |  | 304 |  | 0 | 0 |  |  | 0 | 0 | EAST 165TH STREET-BRYANT AVENUE
EAST 173RD STREET-VYSE AVENUE | BRONX | BUILDING MANAGEMENT ASSOCIATES (PRIVATE - BX 1) |  | 7 | 28 | 168 | Zone 4 |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 168 |  |  |  | 338 |  | 0 | 0 |  |  | 0 | 0 | EAST 173RD STREET-VYSE AVENUE
EAST 180TH STREET-MONTEREY AVENUE | BRONX | TWIN PARKS CONSOLIDATED |  | 1 | 3 | 239 | Zone 1 | $$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 239 |  |  |  | 208 |  | 1 | 2 |  |  | 1 | 2 | EAST 180TH STREET-MONTEREY AVENUE
EAST NEW YORK CITY LINE | BROOKLYN | CYPRESS HILLS | 2023 | 33 | 33 | 66 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 66 |  |  |  | 263 |  | 0 | 0 |  |  | 0 | 0 | EAST NEW YORK CITY LINE
EAST RIVER | MANHATTAN | EAST RIVER | 2024 | 10 | 30 | 1156 | Zone 2 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1156 |  |  |  | 9 |  | 2 | 29 |  |  | 2 | 29 | EAST RIVER
EASTCHESTER GARDENS | BRONX | EASTCHESTER GARDENS | 2026 | 10 | 15 | 877 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 877 |  |  |  | 34 |  | 2 | 15 |  |  | 2 | 15 | EASTCHESTER GARDENS
EDENWALD | BRONX | EDENWALD | 2022 | 40 | 71 | 2035 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 2035 |  |  |  | 57 |  | 5 | 62 |  |  | 0 | 3 | EDENWALD
ELLIOTT | MANHATTAN | CHELSEA |  | 4 | 8 | 606 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 606 |  |  |  | 15 |  | 2 | 8 |  |  | 0 | 8 | ELLIOTT
FARRAGUT | BROOKLYN | FARRAGUT | 2027 | 10 | 10 | 1389 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1389 |  |  |  | 29 | Yes | 1 | 10 |  |  | 1 | 10 | FARRAGUT
FENIMORE-LEFFERTS | BROOKLYN | REID APARTMENTS | 2021 | 18 | 18 | 36 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 36 |  |  |  | 205 |  | 0 | 0 |  |  | 0 | 0 | FENIMORE-LEFFERTS
FHA REPOSSESSED HOUSES (GROUP I) | 0 | BAISLEY PARK | #N/A | 26 | 0 | 21 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 21 |  |  |  | 209 |  | 0 | 0 |  |  | 0 | 0 | FHA REPOSSESSED HOUSES (GROUP I)
FHA REPOSSESSED HOUSES (GROUP II) | 0 | BAISELY PARK | #N/A | 12 | 0 | 10 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 10 |  |  |  | 212 |  | 0 | 0 |  |  | 0 | 0 | FHA REPOSSESSED HOUSES (GROUP II)
FHA REPOSSESSED HOUSES (GROUP III) | 0 | BAISLEY PARK | #N/A | 12 | 0 | 11 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 11 |  |  |  | 213 |  | 0 | 0 |  |  | 0 | 0 | FHA REPOSSESSED HOUSES (GROUP III)
FHA REPOSSESSED HOUSES (GROUP IV) | 0 | BAISLEY PARK | #N/A | 13 | 0 | 10 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 10 |  |  |  | 226 |  | 0 | 0 |  |  | 0 | 0 | FHA REPOSSESSED HOUSES (GROUP IV)
FHA REPOSSESSED HOUSES (GROUP IX) | 0 | BAISLEY PARK | #N/A | 16 | 0 | 16 | Zone 4 |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 16 |  |  |  | 283 | Yes | 0 | 0 |  |  | 0 | 0 | FHA REPOSSESSED HOUSES (GROUP IX)
FHA REPOSSESSED HOUSES (GROUP V) | 0 | BAISLEY PARK | #N/A | 31 | 0 | 29 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 29 |  |  |  | 260 |  | 0 | 0 |  |  | 0 | 0 | FHA REPOSSESSED HOUSES (GROUP V)
FHA REPOSSESSED HOUSES (GROUP VI) | 0 | BAISLEY PARK | #N/A | 7 | 0 | 6 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 6 |  |  |  | 273 |  | 0 | 0 |  |  | 0 | 0 | FHA REPOSSESSED HOUSES (GROUP VI)
FHA REPOSSESSED HOUSES (GROUP VII) | 0 | BAISLEY PARK | #N/A | 8 | 0 | 5 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 5 |  |  |  | 274 |  | 0 | 0 |  |  | 0 | 0 | FHA REPOSSESSED HOUSES (GROUP VII)
FHA REPOSSESSED HOUSES (GROUP VIII) | 0 | BAISLEY PARK | #N/A | 9 | 0 | 5 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 5 |  |  |  | 275 |  | 0 | 0 |  |  | 0 | 0 | FHA REPOSSESSED HOUSES (GROUP VIII)
FHA REPOSSESSED HOUSES (GROUP X) | 0 | BAISLEY PARK | #N/A | 20 | 0 | 16 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 16 |  |  |  | 284 |  | 0 | 0 |  |  | 0 | 0 | FHA REPOSSESSED HOUSES (GROUP X)
FIORENTINO PLAZA | BROOKLYN | UNITY PLAZA | 2026 | 8 | 10 | 158 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 158 |  |  |  | 207 |  | 0 | 3 |  |  | 0 | 3 | FIORENTINO PLAZA
FIRST HOUSES | MANHATTAN | LOWER EAST SIDE CONSOLIDATED | 2026 | 8 | 8 | 126 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 126 |  |  |  | 1 | Yes | 0 | 8 |  |  | 0 | 8 | FIRST HOUSES
FOREST | BRONX | FOREST |  | 15 | 15 | 1348 | Zone 4 |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1348 |  |  |  | 59 |  | 3 | 15 |  |  | 3 | 15 | FOREST
FORT INDEPENDENCE STREET-HEATH AVENUE | BRONX | FORT INDEPENDENCE |  | 1 | 2 | 342 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 342 |  |  |  | 197 |  | 1 | 2 |  |  | 1 | 2 | FORT INDEPENDENCE STREET-HEATH AVENUE
FORT WASHINGTON AVENUE REHAB | MANHATTAN | FORT WASHINGTON | 2019 | 1 | 2 | 226 | Zone 3 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 226 |  |  |  | 309 |  | 0 | 2 |  |  | 0 | 2 | FORT WASHINGTON AVENUE REHAB
FULTON | MANHATTAN | FULTON |  | 11 | 12 | 944 | Zone 3 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 944 |  |  |  | 136 |  | 2 | 19 |  |  | 2 | 19 | FULTON
GARVEY (GROUP A) | BROOKLYN | GARVEY |  | 3 | 6 | 320 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 320 |  |  |  | 252 |  | 0 | 5 |  |  | 0 | 5 | GARVEY (GROUP A)
GLEBE AVENUE-WESTCHESTER AVENUE | BRONX | SOTOMAYOR HOUSES | 2021 | 1 | 1 | 131 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 131 |  |  |  | 225 |  | 0 | 2 |  |  | 0 | 2 | GLEBE AVENUE-WESTCHESTER AVENUE
GLENMORE PLAZA | BROOKLYN | LOW HOUSES |  | 4 | 4 | 439 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 439 |  |  |  | 171 |  | 0 | 4 |  |  | 0 | 4 | GLENMORE PLAZA
GLENWOOD | BROOKLYN | GLENWOOD | 2028 | 20 | 40 | 1186 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1186 |  |  |  | 44 |  | 0 | 40 |  |  | 0 | 40 | GLENWOOD
GOMPERS | MANHATTAN | GOMPERS |  | 2 | 5 | 472 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 472 |  |  |  | 100 | Yes | 1 | 4 |  |  | 1 | 4 | GOMPERS
GOWANUS | BROOKLYN | GOWANUS |  | 15 | 25 | 1137 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1137 |  |  |  | 25 |  | 3 | 24 |  |  | 3 | 24 | GOWANUS
GRAMPION | MANHATTAN | KING TOWERS | 2019 | 1 | 1 | 35 | Zone 3 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 35 |  |  |  | 281 |  | 0 | 1 |  |  | 0 | 1 | GRAMPION
GRANT | MANHATTAN | GRANT |  | 9 | 10 | 1939 | Zone 2 | $$$$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1939 |  |  |  | 87 |  | 2 | 16 |  |  | 2 | 16 | GRANT
GRAVESEND | BROOKLYN | O'DWYER GARDENS |  | 15 | 15 | 627 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 627 |  |  |  | 68 |  | 0 | 15 |  |  | 0 | 2 | GRAVESEND
GUN HILL | BRONX | PARKSIDE |  | 6 | 6 | 732 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 732 |  |  |  | 40 |  | 2 | 6 |  |  | 2 | 6 | GUN HILL
HABER | BROOKLYN | CAREY GARDENS |  | 3 | 3 | 380 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 380 |  |  |  | 142 |  | 0 | 3 |  |  | 0 | 3 | HABER
HAMMEL | QUEENS | HAMMEL |  | 14 | 14 | 710 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 710 |  |  |  | 75 |  | 2 | 14 |  |  | 2 | 14 | HAMMEL
HARBORVIEW TERRACE | MANHATTAN | AMSTERDAM |  | 2 | 2 | 377 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 377 |  |  |  | 262 |  | 1 | 2 |  |  | 1 | 2 | HARBORVIEW TERRACE
HARLEM RIVER | MANHATTAN | HARLEM RIVER | 2020 | 7 | 47 | 574 | Zone 3 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 574 |  |  |  | 3 |  | 0 | 43 |  |  | 0 | 43 | HARLEM RIVER
HARLEM RIVER II | MANHATTAN | HARLEM RIVER | 2020 | 1 | 1 | 116 | Zone 3 | $$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 116 |  |  |  | 147 |  | 0 | 1 |  |  | 0 | 1 | HARLEM RIVER II
HARRISON AVENUE REHAB (GROUP A) | BRONX | KRAUS MANAGEMENT (PRIVATE - BX 3) |  | 1 | 1 | 34 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 34 |  |  |  | 347 |  | 0 | 1 |  |  | 0 | 1 | HARRISON AVENUE REHAB (GROUP A)
HARRISON AVENUE REHAB (GROUP B) | BRONX | KRAUS MANAGEMENT (PRIVATE - BX 3) |  | 4 | 4 | 150 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 150 |  |  |  | 547 |  | 0 | 4 |  |  | 0 | 4 | HARRISON AVENUE REHAB (GROUP B)
HERNANDEZ | MANHATTAN | GOMPERS |  | 1 | 1 | 149 | Zone 1 | $$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 149 |  |  |  | 184 | Yes | 0 | 1 |  |  | 0 | 1 | HERNANDEZ
HIGHBRIDGE GARDENS | BRONX | HIGHBRIDGE GARDENS |  | 6 | 6 | 700 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 700 |  |  |  | 78 |  | 2 | 6 |  |  | 2 | 6 | HIGHBRIDGE GARDENS
HOE AVENUE-EAST 173RD STREET | BRONX | BUILDING MANAGEMENT ASSOCIATES (PRIVATE - BX 1) |  | 1 | 1 | 65 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 65 |  |  |  | 215 |  | 0 | 1 |  |  | 0 | 1 | HOE AVENUE-EAST 173RD STREET
HOLMES TOWERS | MANHATTAN | ISAACS |  | 2 | 2 | 536 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 536 |  |  |  | 159 |  | 0 | 2 |  |  | 0 | 2 | HOLMES TOWERS
HOPE GARDENS | BROOKLYN | HOPE GARDENS | 2019 | 4 | 4 | 323 | Zone 1 |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 323 |  |  |  | 247 | Yes | 0 | 4 |  |  | 0 | 4 | #N/A
HOWARD | BROOKLYN | HOWARD |  | 10 | 16 | 813 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 813 |  |  |  | 72 |  | 0 | 16 |  |  | 0 | 16 | HOWARD
HOWARD AVENUE | BROOKLYN | PARK ROCK CONSOLIDATED | 2025 | 5 | 25 | 148 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 148 |  |  |  | 339 |  | 0 | 0 |  |  | 0 | 0 | HOWARD AVENUE
HOWARD AVENUE-PARK PLACE | BROOKLYN | PARK ROCK CONSOLIDATED | 2025 | 8 | 159 | 155 | Zone 4 |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 155 |  |  |  | 365 |  | 0 | 0 |  |  | 0 | 0 | HOWARD AVENUE-PARK PLACE
HUGHES APARTMENTS | BROOKLYN | HUGHES APARTMENTS |  | 3 | 4 | 509 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 509 |  |  |  | 168 |  | 1 | 3 |  |  | 1 | 3 | HUGHES APARTMENTS
HUNTS POINT AVENUE REHAB | BRONX | BUILDING MANAGEMENT ASSOCIATES (PRIVATE - BX 1) |  | 13 | 13 | 131 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 131 |  |  |  | 367 |  | 0 | 1 |  |  | 0 | 1 | HUNTS POINT AVENUE REHAB
HYLAN | BROOKLYN | BUSHWICK |  | 1 | 1 | 209 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 209 |  |  |  | 109 | Yes | 0 | 1 |  |  | 0 | 1 | HYLAN
INDEPENDENCE | BROOKLYN | TAYLOR STREET-WYTHE AVENUE | 2019 | 6 | 6 | 741 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 741 |  |  |  | 140 | Yes | 2 | 6 |  |  | 2 | 6 | INDEPENDENCE
INGERSOLL | BROOKLYN | INGERSOLL |  | 20 | 46 | 1830 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1830 |  |  |  | 14 | Yes | 2 | 44 |  |  | 2 | 44 | INGERSOLL
INTERNATIONAL TOWER | QUEENS | BAISLEY PARK |  | 1 | 1 | 146 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 146 |  |  |  | 316 |  | 0 | 2 |  |  | 0 | 2 | INTERNATIONAL TOWER
ISAACS | MANHATTAN | ISAACS |  | 3 | 4 | 634 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 634 |  |  |  | 139 |  | 0 | 6 |  |  | 0 | 6 | ISAACS
JACKSON | BRONX | MORRISANIA AIR RIGHTS |  | 7 | 7 | 868 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 868 |  |  |  | 120 |  | 2 | 7 |  |  | 2 | 7 | JACKSON
JEFFERSON | MANHATTAN | JEFFERSON | 2026 | 18 | 35 | 1486 | Zone 2 | $$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1486 |  |  |  | 64 |  | 4 | 34 |  |  | 4 | 34 | JEFFERSON
JOHNSON | MANHATTAN | JOHNSON | 2028 | 10 | 17 | 1296 | Zone 2 | $$$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1296 |  |  |  | 17 |  | 2 | 17 |  |  | 0 | 17 | JOHNSON
KING TOWERS | MANHATTAN | KING TOWERS |  | 10 | 10 | 1377 | Zone 2 | $$$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1377 |  |  |  | 30 |  | 2 | 10 |  |  | 0 | 10 | KING TOWERS
KINGSBOROUGH | BROOKLYN | KINGSBOROUGH |  | 16 | 35 | 1154 | Zone 3 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1154 |  |  |  | 10 | Yes | 0 | 35 |  |  | 0 | 35 | KINGSBOROUGH
KINGSBOROUGH EXTENSION | BROOKLYN | KINGSBOROUGH |  | 1 | 1 | 182 | Zone 4 |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 182 |  |  |  | 161 | Yes | 0 | 2 |  |  | 0 | 2 | KINGSBOROUGH EXTENSION
LA GUARDIA | MANHATTAN | LA GUARDIA |  | 9 | 9 | 1091 | Zone 1 | $$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1091 |  |  |  | 76 | Yes | 2 | 9 |  |  | 2 | 9 | LA GUARDIA
LA GUARDIA ADDITION | MANHATTAN | LA GUARDIA |  | 1 | 1 | 149 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 149 |  |  |  | 152 | Yes | 0 | 1 |  |  | 0 | 1 | LA GUARDIA ADDITION
LAFAYETTE | BROOKLYN | LAFAYETTE |  | 7 | 7 | 882 | Zone 1 | $$$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 882 |  |  |  | 122 | Yes | 2 | 7 |  |  | 2 | 7 | LAFAYETTE
LATIMER GARDENS | QUEENS | LATIMER GARDENS |  | 4 | 4 | 423 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 423 |  |  |  | 186 |  | 1 | 4 |  |  | 1 | 4 | LATIMER GARDENS
LAVANBURG HOMES | MANHATTAN | #N/A | #N/A | 1 | 6 | 95 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 95 |  |  |  | 310 | Yes | 0 | 0 |  |  | 0 | 0 | #N/A
LEAVITT STREET-34TH AVENUE | QUEENS | LATIMER GARDENS |  | 1 | 1 | 83 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 83 |  |  |  | 201 |  | 0 | 1 |  |  | 0 | 1 | LEAVITT STREET-34TH AVENUE
LEHMAN VILLAGE | MANHATTAN | LEHMAN VILLAGE |  | 4 | 5 | 617 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 617 |  |  |  | 101 |  | 2 | 4 |  |  | 2 | 4 | LEHMAN VILLAGE
LENOX ROAD-ROCKAWAY PARKWAY | BROOKLYN | REID APARTMENTS | 2021 | 3 | 3 | 74 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 74 |  |  |  | 348 |  | 0 | 5 |  |  | 0 | 5 | LENOX ROAD-ROCKAWAY PARKWAY
LEXINGTON | MANHATTAN | WASHINGTON | 2023 | 4 | 4 | 448 | Zone 2 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 448 |  |  |  | 50 |  | 1 | 4 |  |  | 1 | 4 | LEXINGTON
LINCOLN | MANHATTAN | LINCOLN |  | 14 | 20 | 1280 | Zone 2 | $$$$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1280 |  |  |  | 20 |  | 2 | 20 |  |  | 2 | 20 | LINCOLN
LINDEN | BROOKLYN | LINDEN | 2020 | 19 | 21 | 1586 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1586 |  |  |  | 95 |  | 0 | 19 | 1 |  | 0 | 19 | LINDEN
LONG ISLAND BAPTIST HOUSES | BROOKLYN | UNITY PLAZA | 2026 | 4 | 4 | 229 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 229 |  |  |  | 276 |  | 0 | 4 |  |  | 0 | 4 | LONG ISLAND BAPTIST HOUSES
LONGFELLOW AVENUE REHAB | BRONX | BUILDING MANAGEMENT ASSOCIATES (PRIVATE - BX 1) |  | 2 | 2 | 75 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 75 |  |  |  | 362 |  | 0 | 5 |  |  | 0 | 5 | LONGFELLOW AVENUE REHAB
LOW HOUSES | BROOKLYN | LOW HOUSES |  | 4 | 4 | 534 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 534 |  |  |  | 169 |  | 0 | 3 |  |  | 0 | 3 | LOW HOUSES
LOWER EAST SIDE I INFILL | MANHATTAN | GOMPERS |  | 5 | 15 | 189 | Zone 1 | $$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 189 |  |  |  | 326 | Yes | 0 | 0 |  |  | 0 | 0 | LOWER EAST SIDE I INFILL
LOWER EAST SIDE II | MANHATTAN | LOWER EAST SIDE CONSOLIDATED | 2026 | 4 | 32 | 188 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 188 |  |  |  | 337 | Yes | 0 | 0 |  |  | 0 | 0 | LOWER EAST SIDE II
LOWER EAST SIDE III | MANHATTAN | KRAUS MANAGEMENT (PRIVATE - M/B1) |  | 2 | 3 | 56 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 56 |  |  |  | 364 | Yes | 0 | 0 |  |  | 0 | 0 | LOWER EAST SIDE III
LOWER EAST SIDE REHAB (GROUP 5) | MANHATTAN | LOWER EAST SIDE CONSOLIDATED | 2026 | 2 | 2 | 55 | Zone 1 | $$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 55 |  |  |  | 292 | Yes | 0 | 2 |  |  | 0 | 2 | LOWER EAST SIDE REHAB (GROUP 5)
MANHATTANVILLE | MANHATTAN | MANHATTANVILLE | 2028 | 6 | 6 | 1272 | Zone 2 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1272 |  |  |  | 81 |  | 3 | 6 |  |  | 3 | 6 | MANHATTANVILLE
MANHATTANVILLE REHAB (GROUP 2) | MANHATTAN | MANHATTANVILLE | 2019 | 3 | 3 | 46 | Zone 3 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 46 |  |  |  | 296 |  | 0 | 3 |  |  | 0 | 2 | MANHATTANVILLE REHAB (GROUP 2)
MANHATTANVILLE REHAB (GROUP 3) | MANHATTAN | MANHATTANVILLE | 2019 | 2 | 2 | 51 | Zone 3 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 51 |  |  |  | 297 |  | 0 | 2 |  |  | 0 | 2 | MANHATTANVILLE REHAB (GROUP 3)
MARBLE HILL | BRONX | MARBLE HILL |  | 11 | 12 | 1680 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1680 |  |  |  | 49 |  | 3 | 11 |  |  | 3 | 11 | MARBLE HILL
MARCY | BROOKLYN | MARCY | 2027 | 27 | 71 | 1716 | Zone 1 | $$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1716 |  |  |  | 21 | Yes | 3 | 69 |  |  | 3 | 69 | MARCY
MARCY AVENUE-GREENE AVENUE SITE A | BROOKLYN | KRAUS MANAGEMENT (PRIVATE - M/B 1) | 2019 | 2 | 7 | 48 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 48 |  |  |  | 363 |  | 0 | 0 |  |  | 0 | 0 | MARCY AVENUE-GREENE AVENUE SITE A
MARCY AVENUE-GREENE AVENUE SITE B | BROOKLYN | KRAUS MANAGEMENT (PRIVATE - M/B 1) | 2019 | 1 | 5 | 30 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 30 |  |  |  | 358 |  | 0 | 0 |  |  | 0 | 0 | MARCY AVENUE-GREENE AVENUE SITE B
MARINER'S HARBOR | STATEN ISLAND | MARINER'S HARBOR | 2028 | 22 | 32 | 606 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 606 |  |  |  | 77 |  | 2 | 27 |  |  | 0 | 27 | MARINER'S HARBOR
MARLBORO | BROOKLYN | MARLBORO |  | 28 | 30 | 1764 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1764 |  |  |  | 83 |  | 0 | 28 |  |  | 0 | 28 | MARLBORO
MARSHALL PLAZA | MANHATTAN | HARLEM RIVER | 2020 | 1 | 1 | 180 | Zone 3 | $$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 180 |  |  |  | 344 |  | 0 | 1 |  |  | 0 | 1 | MARSHALL PLAZA
MCKINLEY | BRONX | FOREST |  | 5 | 5 | 615 | Zone 4 |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 615 |  |  |  | 103 |  | 2 | 5 |  |  | 2 | 5 | MCKINLEY
MELROSE | BRONX | MELROSE | 2023 | 8 | 9 | 1021 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1021 |  |  |  | 28 |  | 2 | 8 |  |  | 2 | 8 | MELROSE
MELTZER TOWER | MANHATTAN | GOMPERS |  | 1 | 1 | 229 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 229 |  |  |  | 183 | Yes | 0 | 1 |  |  | 0 | 1 | MELTZER TOWER
METRO NORTH PLAZA | MANHATTAN | WILSON |  | 3 | 3 | 271 | Zone 2 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 271 |  |  |  | 181 |  | 0 | 3 |  |  | 0 | 3 | METRO NORTH PLAZA
MIDDLETOWN PLAZA | BRONX | EASTCHESTER GARDENS | 2026 | 1 | 1 | 177 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 177 |  |  |  | 191 |  | 0 | 1 |  |  | 0 | 1 | MIDDLETOWN PLAZA
MILL BROOK | BRONX | MILL BROOK |  | 9 | 9 | 1251 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1251 |  |  |  | 84 |  | 3 | 9 |  |  | 3 | 9 | MILL BROOK
MILL BROOK EXTENSION | BRONX | MILL BROOK |  | 1 | 1 | 125 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 125 |  |  |  | 132 |  | 0 | 1 |  |  | 0 | 1 | MILL BROOK EXTENSION
MITCHEL | BRONX | MITCHEL |  | 10 | 12 | 1732 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1732 |  |  |  | 145 |  | 4 | 20 |  |  | 4 | 20 | MITCHEL
MONROE | BRONX | MONROE |  | 12 | 20 | 1100 | Zone 3 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1100 |  |  |  | 88 |  | 2 | 18 |  |  | 2 | 18 | MONROE
MOORE | BRONX | SAINT MARY'S PARK |  | 2 | 4 | 463 | Zone 3 | $$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 463 |  |  |  | 129 |  | 1 | 4 |  |  | 1 | 4 | MOORE
MORRIS I | BRONX | MORRIS |  | 10 | 10 | 1083 | Zone 1 | $$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1083 |  |  |  | 102 |  | 3 | 10 |  |  | 3 | 10 | MORRIS I
MORRIS II | BRONX | MORRIS |  | 7 | 7 | 802 | Zone 1 | $$$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 802 |  |  |  | 502 |  | 2 | 7 |  |  | 2 | 7 | MORRIS II
MORRIS PARK SENIOR CITIZENS HOME | MANHATTAN | ROBINSON |  | 1 | 1 | 97 | Zone 2 | $$$$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 97 |  |  |  | 277 |  | 0 | 1 |  |  | 0 | 1 | MORRIS PARK SENIOR CITIZENS HOME
MORRISANIA | BRONX | WEBSTER |  | 2 | 2 | 206 | Zone 1 | $$$$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 206 |  |  |  | 130 |  | 0 | 2 |  |  | 0 | 2 | MORRISANIA
MORRISANIA AIR RIGHTS | BRONX | MORRISANIA AIR RIGHTS |  | 3 | 5 | 841 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 841 |  |  |  | 267 |  | 0 | 5 |  |  | 0 | 5 | MORRISANIA AIR RIGHTS
MOTT HAVEN | BRONX | MOTT HAVEN |  | 8 | 9 | 992 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 992 |  |  |  | 121 |  | 2 | 8 |  |  | 2 | 8 | MOTT HAVEN
NEW LANE AREA | STATEN ISLAND | SOUTH BEACH |  | 1 | 2 | 276 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 276 |  |  |  | 314 |  | 0 | 2 |  |  | 0 | 2 | NEW LANE AREA
NOSTRAND | BROOKLYN | SHEEPSHEAD BAY | 2028 | 16 | 33 | 1146 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1146 |  |  |  | 43 |  | 0 | 32 |  |  | 0 | 32 | NOSTRAND
OCEAN BAY APARTMENTS (OCEANSIDE) | QUEENS | BEACH 41ST STREET-BEACH CHANNEL DRIVE |  | 7 | 14 | 417 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 417 |  |  |  | 51 |  | 0 | 13 |  |  | 0 | 13 | OCEAN BAY APARTMENTS (OCEANSIDE)
OCEAN HILL APARTMENTS | BROOKLYN | OCEAN HILL APARTMENTS |  | 3 | 4 | 238 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 238 |  |  |  | 162 | Yes | 0 | 3 |  |  | 0 | 3 | OCEAN HILL APARTMENTS
OCEAN HILL-BROWNSVILLE | BROOKLYN | PARK ROCK CONSOLIDATED | 2025 | 5 | 5 | 125 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 125 |  |  |  | 313 | Yes | 0 | 6 |  |  | 0 | 6 | OCEAN HILL-BROWNSVILLE
O'DWYER GARDENS | BROOKLYN | O'DWYER GARDENS |  | 6 | 7 | 570 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 570 |  |  |  | 172 |  | 0 | 6 |  |  | 0 | 6 | O'DWYER GARDENS
PALMETTO GARDENS | BROOKLYN | HOPE GARDENS | 2019 | 1 | 1 | 113 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 113 |  |  |  | 195 | Yes | 0 | 1 |  |  | 0 | 1 | #N/A
PARK AVENUE-EAST 122ND, 123RD STREETS | MANHATTAN | ROBINSON | 2019 | 2 | 2 | 90 | Zone 3 | $$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 90 |  |  |  | 204 |  | 0 | 2 |  |  | 0 | 2 | PARK AVENUE-EAST 122ND, 123RD STREETS
PARK ROCK REHAB | BROOKLYN | PARK ROCK CONSOLIDATED | 2025 | 9 | 9 | 134 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 134 |  |  |  | 351 | Yes | 0 | 6 |  |  | 0 | 6 | PARK ROCK REHAB
PARKSIDE | BRONX | PARKSIDE |  | 14 | 20 | 879 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 879 |  |  |  | 47 |  | 2 | 21 |  |  | 2 | 21 | PARKSIDE
PATTERSON | BRONX | PATTERSON | 2025 | 15 | 25 | 1789 | Zone 3 | $$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1789 |  |  |  | 24 |  | 4 | 25 |  |  | 0 | 0 | PATTERSON
PELHAM PARKWAY | BRONX | PELHAM PARKWAY | 2022 | 23 | 38 | 1265 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1265 |  |  |  | 39 |  | 3 | 38 |  |  | 3 | 38 | PELHAM PARKWAY
PENNSYLVANIA AVENUE-WORTMAN AVENUE | BROOKLYN | PENNSYLVANIA-WORTMAN |  | 3 | 3 | 336 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 336 |  |  |  | 194 |  | 0 | 3 |  |  | 0 | 3 | PENNSYLVANIA AVENUE-WORTMAN AVENUE
PINK | BROOKLYN | PINK |  | 22 | 25 | 1500 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1500 |  |  |  | 89 |  | 0 | 22 |  |  | 0 | 22 | PINK
POLO GROUNDS TOWERS | MANHATTAN | POLO GROUNDS TOWERS |  | 4 | 12 | 1614 | Zone 2 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1614 |  |  |  | 149 |  | 3 | 9 |  |  | 3 | 9 | POLO GROUNDS TOWERS
POMONOK | QUEENS | POMONOK | 2027 | 35 | 121 | 2069 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 2069 |  |  |  | 53 |  | 5 | 121 |  |  | 5 | 121 | POMONOK
PSS GRANDPARENT FAMILY APARTMENTS | BRONX | #N/A | #N/A | 1 | 1 | 50 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 50 |  |  |  | 560 |  | 0 | 0 |  |  | 0 | 0 | #N/A
PUBLIC SCHOOL 139 (CONVERSION) | MANHATTAN | DREW-HAMILTON | 2019 | 1 | 2 | 125 | Zone 3 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 125 |  |  |  | 340 |  | 0 | 1 |  |  | 0 | 1 | PUBLIC SCHOOL 139 (CONVERSION)
QUEENSBRIDGE NORTH | QUEENS | QUEENSBRIDGE NORTH |  | 13 | 48 | 1542 | Zone 3 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1542 |  |  |  | 505 |  | 0 | 47 |  |  | 0 | 47 | QUEENSBRIDGE NORTH
QUEENSBRIDGE SOUTH | QUEENS | QUEENSBRIDGE SOUTH |  | 13 | 50 | 1603 | Zone 3 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1603 |  |  |  | 5 |  | 12 | 49 |  |  | 6 | 49 | QUEENSBRIDGE SOUTH
RALPH AVENUE REHAB | BROOKLYN | REID APARTMENTS | 2021 | 5 | 5 | 118 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 118 |  |  |  | 352 |  | 0 | 9 |  |  | 0 | 9 | RALPH AVENUE REHAB
RANDALL AVENUE-BALCOM AVENUE | BRONX | THROGGS NECK | 2022 | 3 | 3 | 251 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 251 |  |  |  | 245 |  | 0 | 3 |  |  | 0 | 3 | RANDALL AVENUE-BALCOM AVENUE
RANDOLPH SOUTH | MANHATTAN | #N/A | #N/A | 2 | 0 | 147 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 147 |  |  |  | 561 |  | 0 | 0 |  |  | 0 | 0 | #N/A
RANGEL | MANHATTAN | RANGEL |  | 8 | 9 | 982 | Zone 2 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 982 |  |  |  | 37 |  | 3 | 10 |  |  | 3 | 10 | RANGEL
RAVENSWOOD | QUEENS | RAVENSWOOD |  | 31 | 45 | 2164 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 2164 |  |  |  | 48 |  | 0 | 39 |  |  | 0 | 39 | RAVENSWOOD
RED HOOK EAST | BROOKLYN | RED HOOK EAST | 2024 | 16 | 51 | 1404 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1404 |  |  |  | 4 |  | 0 | 47 |  |  | 0 | 47 | RED HOOK EAST
RED HOOK WEST | BROOKLYN | RED HOOK WEST | 2025 | 14 | 50 | 1471 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1471 |  |  |  | 79 |  | 2 | 43 |  |  | 2 | 43 | RED HOOK WEST
REDFERN | QUEENS | REDFERN | 2022 | 9 | 16 | 599 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 599 |  |  |  | 55 |  | 0 | 16 |  |  | 0 | 16 | REDFERN
REHAB PROGRAM (COLLEGE POINT) | QUEENS | LATIMER GARDENS |  | 1 | 1 | 13 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 13 |  |  |  | 143 |  | 0 | 0 |  |  | 0 | 0 | REHAB PROGRAM (COLLEGE POINT)
REHAB PROGRAM (DOUGLASS REHABS) | MANHATTAN | KRAUS MANAGEMENT (PRIVATE - M/B 1) |  | 4 | 9 | 112 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 112 |  |  |  | 515 |  | 0 | 3 |  |  | 0 | 3 | REHAB PROGRAM (DOUGLASS REHABS)
REHAB PROGRAM (TAFT REHABS) | MANHATTAN | KRAUS MANAGEMENT (PRIVATE - M/B 1) |  | 4 | 4 | 156 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 156 |  |  |  | 516 |  | 0 | 4 |  |  | 0 | 4 | REHAB PROGRAM (TAFT REHABS)
REHAB PROGRAM (WISE REHAB) | MANHATTAN | WISE TOWERS |  | 1 | 1 | 40 | Zone 4 |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 40 |  |  |  | 517 |  | 0 | 1 |  |  | 0 | 1 | REHAB PROGRAM (WISE REHAB)
REID APARTMENTS | BROOKLYN | REID APARTMENTS | 2021 | 1 | 1 | 227 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 227 |  |  |  | 167 |  | 0 | 1 |  |  | 0 | 1 | REID APARTMENTS
RICHMOND TERRACE | STATEN ISLAND | RICHMOND TERRACE |  | 6 | 7 | 488 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 488 |  |  |  | 117 |  | 2 | 6 |  |  | 0 | 6 | RICHMOND TERRACE
RIIS | MANHATTAN | RIIS |  | 13 | 18 | 1191 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1191 |  |  |  | 18 | Yes | 2 | 15 |  |  | 2 | 15 | RIIS
RIIS II | MANHATTAN | RIIS |  | 6 | 8 | 577 | Zone 1 | $$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 577 |  |  |  | 19 | Yes | 1 | 7 |  |  | 1 | 7 | RIIS II
ROBBINS PLAZA | MANHATTAN | ISAACS |  | 1 | 1 | 150 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 150 |  |  |  | 218 |  | 0 | 1 |  |  | 0 | 1 | ROBBINS PLAZA
ROBINSON | MANHATTAN | ROBINSON |  | 1 | 2 | 188 | Zone 2 | $$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 188 |  |  |  | 241 |  | 0 | 2 |  |  | 0 | 2 | ROBINSON
ROOSEVELT I | BROOKLYN | ROOSEVELT |  | 6 | 6 | 761 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 761 |  |  |  | 135 | Yes | 0 | 6 |  |  | 0 | 6 | ROOSEVELT I
ROOSEVELT II | BROOKLYN | ROOSEVELT |  | 3 | 3 | 342 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 342 |  |  |  | 177 | Yes | 0 | 3 |  |  | 0 | 3 | ROOSEVELT II
RUTGERS | MANHATTAN | RUTGERS |  | 5 | 5 | 721 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 721 |  |  |  | 99 | Yes | 1 | 5 |  |  | 1 | 5 | RUTGERS
RUTLAND TOWERS | BROOKLYN | REID APARTMENTS | 2021 | 1 | 1 | 60 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 60 |  |  |  | 282 |  | 0 | 1 |  |  | 0 | 1 | RUTLAND TOWERS
SACK WERN | BRONX | SACK WERN | 2024 | 7 | 8 | 411 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 411 |  |  |  | 280 |  | 0 | 7 |  |  | 0 | 7 | SACK WERN
SAINT MARY'S PARK | BRONX | SAINT MARY'S PARK |  | 6 | 6 | 1005 | Zone 3 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1005 |  |  |  | 93 |  | 2 | 6 |  |  | 2 | 6 | SAINT MARY'S PARK
SAINT NICHOLAS | MANHATTAN | SAINT NICHOLAS |  | 13 | 14 | 1525 | Zone 2 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1525 |  |  |  | 38 |  | 3 | 14 |  |  | 3 | 14 | SAINT NICHOLAS
SAMUEL (CITY) | MANHATTAN | SAMUEL | 2026 | 40 | 43 | 664 | Zone 2 | $$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 664 |  |  |  | 377 |  | 0 | 40 |  |  | 0 | 40 | SAMUEL (CITY)
SAMUEL (MHOP) I | MANHATTAN | KRAUS MANAGEMENT (PRIVATE - M/B 1) | 2019 | 5 | 5 | 24 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 24 |  |  |  | 389 |  | 0 | 1 |  |  | 0 | 1 | SAMUEL (MHOP) I
SAMUEL (MHOP) II | MANHATTAN | KRAUS MANAGEMENT (PRIVATE - M/B 1) | 2019 | 1 | 1 | 4 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 4 |  |  |  | 398 |  | 0 | 0 |  |  | 0 | 0 | SAMUEL (MHOP) II
SAMUEL (MHOP) III | MANHATTAN | KRAUS MANAGEMENT (PRIVATE - M/B 1) | 2019 | 1 | 1 | 1 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | 399 |  | 0 | 1 |  |  | 0 | 1 | SAMUEL (MHOP) III
SARATOGA VILLAGE | BROOKLYN | OCEAN HILL APARTMENTS |  | 1 | 1 | 125 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 125 |  |  |  | 158 | Yes | 0 | 1 |  |  | 0 | 1 | SARATOGA VILLAGE
SEDGWICK | BRONX | SEDGWICK |  | 7 | 7 | 783 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 783 |  |  |  | 45 |  | 2 | 7 |  |  | 2 | 7 | SEDGWICK
SEWARD PARK EXTENSION | MANHATTAN | GOMPERS |  | 2 | 5 | 360 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 360 |  |  |  | 192 | Yes | 0 | 2 |  |  | 0 | 2 | SEWARD PARK EXTENSION
SHEEPSHEAD BAY | BROOKLYN | SHEEPSHEAD BAY | 2028 | 18 | 36 | 1054 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1054 |  |  |  | 36 |  | 6 | 35 |  |  | 6 | 35 | SHEEPSHEAD BAY
SHELTON HOUSE | QUEENS | BAISLEY PARK |  | 1 | 1 | 153 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 153 |  |  |  | 279 |  | 0 | 1 |  |  | 0 | 1 | SHELTON HOUSE
SMITH | MANHATTAN | SMITH |  | 12 | 12 | 1934 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1934 |  |  |  | 27 | Yes | 4 | 13 |  |  | 4 | 12 | SMITH
SOTOMAYOR HOUSES | BRONX | SOTOMAYOR HOUSES | #N/A | 28 | 31 | 1495 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1495 |  |  |  | 67 |  | 3 | 28 |  |  | 3 | 0 | SOTOMAYOR HOUSES
SOUNDVIEW | BRONX | SOUNDVIEW | 2023 | 13 | 28 | 1258 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1258 |  |  |  | 71 |  | 4 | 22 |  |  | 4 | 22 | SOUNDVIEW
SOUTH BEACH | STATEN ISLAND | SOUTH BEACH |  | 8 | 15 | 421 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 421 |  |  |  | 35 |  | 1 | 15 |  |  | 1 | 15 | SOUTH BEACH
SOUTH BRONX AREA (SITE 402) | BRONX | UNION AVENUE CONSOLIDATED | 2026 | 4 | 19 | 112 | Zone 3 | $$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 112 |  |  |  | 305 |  | 0 | 0 |  |  | 0 | 0 | SOUTH BRONX AREA (SITE 402)
SOUTH JAMAICA I | QUEENS | SOUTH JAMAICA I | 2021 | 11 | 33 | 448 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 448 |  |  |  | 8 |  | 0 | 33 |  |  | 0 | 33 | SOUTH JAMAICA I
SOUTH JAMAICA II | QUEENS | SOUTH JAMAICA I | 2021 | 16 | 27 | 598 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 598 |  |  |  | 66 |  | 4 | 27 |  |  | 4 | 27 | SOUTH JAMAICA II
STANTON STREET | MANHATTAN | KRAUS MANAGEMENT (PRIVATE - M/B 1) |  | 1 | 1 | 13 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 13 |  |  |  | 559 | Yes | 0 | 1 |  |  | 0 | 1 | STANTON STREET
STAPLETON | STATEN ISLAND | STAPLETON |  | 6 | 12 | 693 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 693 |  |  |  | 114 |  | 2 | 12 |  |  | 2 | 12 | STAPLETON
STEBBINS AVENUE-HEWITT PLACE | BRONX | UNION AVENUE CONSOLIDATED | 2026 | 2 | 14 | 119 | Zone 3 | $$$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 119 |  |  |  | 353 |  | 0 | 0 |  |  | 0 | 0 | STEBBINS AVENUE-HEWITT PLACE
STERLING PLACE REHABS (SAINT JOHNS-STERLING) | BROOKLYN | PARK ROCK CONSOLIDATED | 2025 | 5 | 5 | 83 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 83 |  |  |  | 366 | Yes | 0 | 5 |  |  | 0 | 5 | STERLING PLACE REHABS (SAINT JOHNS-STERLING)
STERLING PLACE REHABS (STERLING-BUFFALO) | BROOKLYN | PARK ROCK CONSOLIDATED | 2025 | 7 | 7 | 125 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 125 |  |  |  | 368 | Yes | 0 | 7 |  |  | 0 | 7 | STERLING PLACE REHABS (STERLING-BUFFALO)
STRAUS | MANHATTAN | STRAUS |  | 2 | 2 | 267 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 267 |  |  |  | 153 | Yes | 0 | 2 |  |  | 0 | 2 | STRAUS
STUYVESANT GARDENS I | BROOKLYN | STUYVESANT GARDENS I |  | 5 | 25 | 329 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 329 |  |  |  | 221 | Yes | 0 | 11 |  |  | 0 | 11 | STUYVESANT GARDENS I
STUYVESANT GARDENS II | BROOKLYN | STUYVESANT GARDENS I |  | 1 | 1 | 150 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 150 |  |  |  | 333 | Yes | 0 | 1 |  |  | 0 | 1 | STUYVESANT GARDENS II
SUMNER | BROOKLYN | SUMNER |  | 13 | 24 | 1098 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1098 |  |  |  | 73 | Yes | 2 | 24 |  |  | 2 | 24 | SUMNER
SURFSIDE GARDENS | BROOKLYN | SURFSIDE GARDENS |  | 5 | 5 | 594 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 594 |  |  |  | 170 |  | 1 | 5 |  |  | 1 | 5 | SURFSIDE GARDENS
SUTTER AVENUE-UNION STREET | BROOKLYN | REID APARTMENTS | 2021 | 3 | 3 | 100 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 100 |  |  |  | 369 |  | 0 | 5 |  |  | 0 | 5 | SUTTER AVENUE-UNION STREET
TAFT | MANHATTAN | TAFT |  | 9 | 19 | 1463 | Zone 2 | $$$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1463 |  |  |  | 97 |  | 4 | 11 |  |  | 4 | 11 | TAFT
TAPSCOTT STREET REHAB | BROOKLYN | REID APARTMENTS | 2021 | 8 | 8 | 155 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 155 |  |  |  | 354 |  | 0 | 9 |  |  | 0 | 9 | TAPSCOTT STREET REHAB
TAYLOR STREET-WYTHE AVENUE | BROOKLYN | TAYLOR STREET-WYTHE AVENUE |  | 5 | 6 | 525 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 525 |  |  |  | 234 | Yes | 0 | 6 |  |  | 0 | 1 | TAYLOR STREET-WYTHE AVENUE
TELLER AVENUE-EAST 166TH STREET | BRONX | CLAREMONT CONSOLIDATED | 2025 | 1 | 1 | 90 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 90 |  |  |  | 223 |  | 0 | 2 |  |  | 0 | 2 | TELLER AVENUE-EAST 166TH STREET
THOMAS APARTMENTS | MANHATTAN | WISE TOWERS |  | 1 | 1 | 87 | Zone 4 |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 87 |  |  |  | 268 |  | 0 | 1 |  |  | 0 | 1 | THOMAS APARTMENTS
THROGGS NECK | BRONX | THROGGS NECK | 2022 | 29 | 66 | 1182 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1182 |  |  |  | 63 |  | 6 | 60 |  |  | 6 | 60 | THROGGS NECK
THROGGS NECK ADDITION | BRONX | THROGGS NECK | 2022 | 4 | 4 | 287 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 287 |  |  |  | 193 |  | 0 | 4 |  |  | 0 | 4 | THROGGS NECK ADDITION
TILDEN | BROOKLYN | TILDEN |  | 8 | 9 | 998 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 998 |  |  |  | 96 |  | 2 | 8 |  |  | 2 | 8 | TILDEN
TODT HILL | STATEN ISLAND | BERRY |  | 7 | 14 | 502 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 502 |  |  |  | 42 |  | 0 | 13 |  |  | 0 | 13 | TODT HILL
TOMPKINS | BROOKLYN | TOMPKINS |  | 8 | 13 | 1045 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1045 |  |  |  | 131 | Yes | 0 | 12 |  |  | 0 | 11 | TOMPKINS
TWIN PARKS EAST (SITE 9) | BRONX | TWIN PARKS CONSOLIDATED |  | 1 | 1 | 219 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 219 |  |  |  | 287 |  | 0 | 1 |  |  | 0 | 1 | TWIN PARKS EAST (SITE 9)
TWO BRIDGES URA (SITE 7) | MANHATTAN | LA GUARDIA |  | 1 | 1 | 250 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 250 |  |  |  | 266 | Yes | 0 | 1 |  |  | 0 | 1 | TWO BRIDGES URA (SITE 7)
UNION AVENUE-EAST 163RD STREET | BRONX | UNION AVENUE CONSOLIDATED | 2026 | 1 | 1 | 199 | Zone 3 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 199 |  |  |  | 342 |  | 0 | 1 |  |  | 0 | 1 | UNION AVENUE-EAST 163RD STREET
UNION AVENUE-EAST 166TH STREET | BRONX | UNION AVENUE CONSOLIDATED | 2026 | 6 | 20 | 120 | Zone 3 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 120 |  |  |  | 356 |  | 1 | 0 |  |  | 1 | 0 | UNION AVENUE-EAST 166TH STREET
UNITY PLAZA (SITES 17,24,25A) | BROOKLYN | UNITY PLAZA | 2026 | 3 | 3 | 167 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 167 |  |  |  | 240 |  | 0 | 3 |  |  | 0 | 3 | UNITY PLAZA (SITES 17,24,25A)
UNITY PLAZA (SITES 4-27) | BROOKLYN | UNITY PLAZA | 2026 | 5 | 13 | 460 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 460 |  |  |  | 261 |  | 0 | 12 |  |  | 0 | 12 | UNITY PLAZA (SITES 4-27)
UNIVERSITY AVENUE REHAB | BRONX | KRAUS MANAGEMENT (PRIVATE - BX 3) |  | 4 | 5 | 230 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 230 |  |  |  | 341 |  | 0 | 5 |  |  | 0 | 5 | UNIVERSITY AVENUE REHAB
UPACA (SITE 5) | MANHATTAN | ROBINSON |  | 1 | 1 | 179 | Zone 2 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 179 |  |  |  | 343 |  | 0 | 1 |  |  | 0 | 1 | UPACA (SITE 5)
UPACA (SITE 6) | MANHATTAN | ROBINSON |  | 1 | 1 | 150 | Zone 2 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 150 |  |  |  | 355 |  | 0 | 1 |  |  | 0 | 1 | UPACA (SITE 6)
VAN DYKE I | BROOKLYN | VAN DYKE I | 2024 | 22 | 32 | 1603 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1603 |  |  |  | 61 |  | 0 | 31 |  |  | 0 | 31 | VAN DYKE I
VAN DYKE II | BROOKLYN | WOODSON |  | 1 | 1 | 111 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 111 |  |  |  | 146 |  | 0 | 1 |  |  | 0 | 1 | VAN DYKE II
VANDALIA AVENUE | BROOKLYN | PENNSYLVANIA-WORTMAN |  | 2 | 3 | 288 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 288 |  |  |  | 315 |  | 0 | 2 |  |  | 0 | 2 | VANDALIA AVENUE
VLADECK | MANHATTAN | VLADECK |  | 20 | 46 | 1527 | Zone 1 | $$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1527 |  |  |  | 6 | Yes | 0 | 45 |  |  | 0 | 2 | VLADECK
VLADECK II | MANHATTAN | VLADECK |  | 4 | 8 | 240 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 240 |  |  |  | 7 | Yes | 0 | 7 |  |  | 0 | 7 | VLADECK II
WAGNER | MANHATTAN | WAGNER |  | 22 | 22 | 2151 | Zone 2 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 2151 |  |  |  | 74 |  | 4 | 22 |  |  | 4 | 22 | WAGNER
WALD | MANHATTAN | WALD |  | 16 | 19 | 1861 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1861 |  |  |  | 23 | Yes | 3 | 17 |  |  | 3 | 17 | WALD
WASHINGTON | MANHATTAN | WASHINGTON | 2023 | 14 | 18 | 1515 | Zone 2 | $$$ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1515 |  |  |  | 62 |  | 1 | 14 | 1 |  | 1 | 14 | WASHINGTON
WASHINGTON HEIGHTS REHAB (GROUPS 1&2) | MANHATTAN | FORT WASHINGTON | 2019 | 5 | 6 | 215 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 215 |  |  |  | 293 |  | 0 | 6 |  |  | 0 | 6 | WASHINGTON HEIGHTS REHAB (GROUPS 1&2)
WASHINGTON HEIGHTS REHAB PHASE III | MANHATTAN | HARLEM RIVER | 2019 | 8 | 8 | 102 | Zone 3 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 102 |  |  |  | 329, 523 |  | 0 | 0 |  |  | 0 | 0 | #N/A
WASHINGTON HEIGHTS REHAB PHASE III (FORT WASHINGTON) | MANHATTAN | #N/A | #N/A | 7 | 7 | 88 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 88 |  |  |  | 523 |  | 0 | 3 |  |  | 0 | 3 | WASHINGTON HEIGHTS REHAB PHASE III (FORT WASHINGTON)
WASHINGTON HEIGHTS REHAB PHASE III (HARLEM RIVER) | MANHATTAN | #N/A | #N/A | 1 | 1 | 14 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 14 |  |  |  | 329 |  | 0 | 1 |  |  | 0 | 1 | WASHINGTON HEIGHTS REHAB PHASE III (HARLEM RIVER)
WASHINGTON HEIGHTS REHAB PHASE IV (C) | MANHATTAN | FORT WASHINGTON | 2019 | 2 | 2 | 32 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 32 |  |  |  | 330 |  | 0 | 2 |  |  | 0 | 2 | WASHINGTON HEIGHTS REHAB PHASE IV (C)
WASHINGTON HEIGHTS REHAB PHASE IV (D) | MANHATTAN | FORT WASHINGTON | 2019 | 2 | 2 | 32 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 32 |  |  |  | 331 |  | 0 | 2 |  |  | 0 | 2 | WASHINGTON HEIGHTS REHAB PHASE IV (D)
WEBSTER | BRONX | WEBSTER |  | 5 | 6 | 606 | Zone 1 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 606 |  |  |  | 141 |  | 2 | 5 |  |  | 2 | 5 | WEBSTER
WEEKSVILLE GARDENS | BROOKLYN | ALBANY | 2019 | 2 | 14 | 256 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 256 |  |  |  | 229 | Yes | 0 | 0 |  |  | 0 | 0 | WEEKSVILLE GARDENS
WEST BRIGHTON I | STATEN ISLAND | WEST BRIGHTON I |  | 8 | 9 | 487 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 487 |  |  |  | 116 |  | 2 | 8 |  |  | 2 | 8 | WEST BRIGHTON I
WEST BRIGHTON II | STATEN ISLAND | WEST BRIGHTON I |  | 8 | 8 | 120 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 120 |  |  |  | 175 |  | 0 | 0 |  |  | 0 | 0 | WEST BRIGHTON II
WEST FARMS ROAD REHAB | BRONX | BUILDING MANAGEMENT ASSOCIATES (PRIVATE - BX 1) |  | 4 | 7 | 208 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 208 |  |  |  | 360 |  | 0 | 7 |  |  | 0 | 7 | WEST FARMS ROAD REHAB
WEST FARMS SQUARE CONVENTIONAL | BRONX | BUILDING MANAGEMENT ASSOCIATES (PRIVATE - BX 1) |  | 1 | 1 | 20 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 20 |  |  |  | 526 |  | 0 | 1 |  |  | 0 | 1 | WEST FARMS SQUARE CONVENTIONAL
WEST TREMONT AVENUE-SEDGWICK AVENUE AREA | BRONX | SEDGWICK |  | 1 | 1 | 148 | Zone 4 |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 148 |  |  |  | 246 |  | 0 | 1 |  |  | 0 | 1 | WEST TREMONT AVENUE-SEDGWICK AVENUE AREA
WHITE | MANHATTAN | WILSON |  | 1 | 1 | 246 | Zone 2 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 246 |  |  |  | 124 |  | 0 | 2 |  |  | 0 | 2 | WHITE
WHITMAN | BROOKLYN | WHITMAN |  | 15 | 48 | 1651 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1651 |  |  |  | 514 | Yes | 3 | 32 |  |  | 3 | 32 | WHITMAN
WILLIAMS PLAZA | BROOKLYN | WILLIAMS PLAZA | 2019 | 5 | 5 | 577 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 577 |  |  |  | 128 | Yes | 0 | 5 | 1 |  | 0 | 5 | WILLIAMS PLAZA
WILLIAMSBURG | BROOKLYN | WILLIAMSBURG | 2020 | 20 | 137 | 1627 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1627 |  |  |  | 2 | Yes | 0 | 134 |  |  | 0 | 134 | WILLIAMSBURG
WILSON | MANHATTAN | WILSON |  | 3 | 3 | 398 | Zone 2 | $ | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 398 |  |  |  | 112 |  | 2 | 5 |  |  | 2 | 5 | WILSON
WISE TOWERS | MANHATTAN | WISE TOWERS | 2019 | 2 | 5 | 397 | Zone 4 |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 397 |  |  |  | 127 |  | 0 | 4 |  |  | 0 | 4 | WISE TOWERS
WOODSIDE | QUEENS | WOODSIDE |  | 20 | 55 | 1355 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1355 |  |  |  | 33 |  | 3 | 56 |  |  | 3 | 56 | WOODSIDE
WOODSON | BROOKLYN | WOODSON |  | 2 | 2 | 407 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 407 |  |  |  | 182 |  | 0 | 2 |  |  | 0 | 2 | WOODSON
WSUR (BROWNSTONES) | MANHATTAN | WISE TOWERS |  | 36 | 36 | 236 | Zone 4 |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 236 |  |  |  | 178 |  | 0 | 0 |  |  | 0 | 0 | WSUR (BROWNSTONES)
WSUR (SITE A) 120 WEST 94TH STREET | MANHATTAN | WISE TOWERS |  | 1 | 1 | 69 | Zone 4 |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 69 |  |  |  | 151 |  | 0 | 1 |  |  | 0 | 1 | WSUR (SITE A) 120 WEST 94TH STREET
WSUR (SITE B) 74 WEST 92ND STREET | MANHATTAN | WISE TOWERS |  | 1 | 1 | 168 | Zone 4 |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 168 |  |  |  | 173 |  | 0 | 2 |  |  | 0 | 2 | WSUR (SITE B) 74 WEST 92ND STREET
WSUR (SITE C) 589 AMSTERDAM AVENUE | MANHATTAN | WISE TOWERS |  | 1 | 1 | 158 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 158 |  |  |  | 174 |  | 0 | 2 |  |  | 0 | 2 | WSUR (SITE C) 589 AMSTERDAM AVENUE
WYCKOFF GARDENS | BROOKLYN | WYCKOFF GARDENS |  | 3 | 3 | 528 |  |  | 0 | 0 |  |  | 0 | 1 | 1 | 1 | 1 | 1 | 528 |  |  |  | 163 |  | 0 | 6 |  |  | 0 | 6 | WYCKOFF GARDENS

## Data Key
Data Source | Data
2017 PNA | Interior/exterior compactor count, RUL
MRST Interior/Exterior Compactor List
PAIS Prioritization
NYCHA Development Data Book 2019
Investment Continuum